## Sheet1
STATUS OF NEC FUNDED ONGOIN PROJECTS/SCHEMES (PRIORITY LIST)
(Rs. in Lakh)
Sl. No. | Name of the Project | Department | Date of Administrative Approval of the Project by NEC | Total Estimated Cost of the Project | NEC's Share Amount | Target Date of Completion | Instalment Released by NEC |  | Amount recommended by T & D | Deptt. yet to move for fund against NEC release | Amount released by FD |  | UC submitted | UC pending against the NEC release | UC pending against the FD release | State Share
[7 empty] | Date | Amount |  |  | Date | Amount |  |  |  | Total State Share | Amount recommended by P & D | State share recommended by T&D | State Share Released by FD | State Share UC Submitted
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 11 | 12 | 13 | 15 | 16 | 14 | 17 | 15 | 16 | 17
During 12th Plan
1 | Estt. Of Deori Tribel Cultural Complex at Narayanpur, Lakhimpur | CULTURAL AFFAIRS | 25-04-2012 | 497 | 447.3 | March'2017 | 2012-02-04 | 120 | 120 | 0 | 2014-15 | 120 | 85.03 | 34.97 | 34.97 | 49.7 |  | 12 | 12 | 0
2 | Tai Education & Cultural Centre at Niz-Kadamoni, Dibrugarh | CULTURAL AFFAIRS | 25/2/2014 | 333.49 | 300.14 | 3 years from the date of approval | 25/2/2014 | 120 | 76.8546 | 43.1454 |  | 76.806 | 76.8061 | 43.1939 | -0.0001 | 33.35 |  |  | 0 | 0
| Sub -Total Cultural Affairs |  |  | 830.49 | 747.44 |  |  | 240 | 196.8546 | 43.1454 |  | 196.806 | 161.8361 | 78.1639 | 34.9699 | 83.05 |  | 12 | 12 | 0