## Sheet1
STATUS OF NEC FUNDED ONGOIN PROJECTS/SCHEMES (PRIORITY LIST)
(Rs. in Lakh)
Sl. No. | Name of the Project | Department | Date of Administrative Approval of the Project by NEC | Total Estimated Cost of the Project | NEC's Share Amount | Target Date of Completion | Instalment Released by NEC |  | Amount recommended by T & D | Amount released by FD |  | UC submitted | State Share
[7 empty] | Date | Amount |  | Date | Amount |  | Total State Share | State share recommended by T&D | State Share Released by FD | State Share UC Submitted
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 12 | 13 | 14 | 17 | 15 | 16 | 17
During 11th Plan
54 | Dhankhunda FIS Kamrup | IRRIGATION | 22/09/2010 | 485 | 436.5 | Completed | 22/9/2010 | 145.5 | 436.5 |  | 436.5 | 392.85 | 48.5 | 48.5 | 48.5 | 44.14
[7 empty] | 22/8/2012 | 174.6
[7 empty] | 2014-03-06 | 72.75
[7 empty] | 24/11/2015 | 43.65
[7 empty] | Total | 436.5
55 | Modernisation and Extension of Longparpam MIS, Karbi- Anglong District | IRRIGATION | 22/09/2010 | 213 | 191.7 | Completed in March 2013 | 22/9/2010 | 64 | 140.68 |  | 140.68 | 140.68 | 21.3 | 15.63 | 15.63 | 15.63
[7 empty] | 2012-07-08 | 76.68
[7 empty] | Total | 140.68
56 | Construction of Gilabwr-FIS | IRRIGATION | 23/3/2012 | 418 | 376.2 | Completed | 23/3/2012 | 100 | 325.48 |  | 325.48 | 325.48 | 41.8 | 27.83 | 27.83 | 27.83
[7 empty] | 25/04/2014 | 150.48
[7 empty] | 2015-16 | 75
[7 empty] | 23/2/2017 | 50.72
[7 empty] | Total | 376.2
During 12th Plan
57 | Ram Englee Minor Irrigation scheme in Karbi-Anglong Dist. Assam | IRRIGATION | 25/3/2013 | 494.7 | 445.23 | 25/3/2015 | 25/3/2013 | 140 | 318 |  | 318 | 318 | 49.47 | 15.55 | 15.55
[7 empty] | 2015-05-01 | 178
[7 empty] | 23/2/2017 | 127.23
[7 empty] | Total | 445.23
| Sub Total Irrigation |  |  | 1610.7 | 1449.63 |  |  | 1398.61 | 1220.66 |  | 1220.66 | 1177.01 | 161.07 | 107.51 | 107.51 | 87.6