**Government of India**

**Ministry of Developemnt of North Eastern Region**

**Vigyan Bhawan Annex, Maulana Azad Road, New Delhi-110011**

Dated : 2nd July,2012

**OFFICE MEMORANDUM**

**Subject :** **Guidelines for release of funds under Karbi Anglong Autonomous Territorial Council (KAATC) package**

To fulfill aspirations of people of Karbi Anglong for all round development by facilitating devolution of economic development, while preserving and promoting their cultural identity and language, a tripartite Memorandum of Statement (MoS) was signed between Central Government , Government of Assam and UPDS on 25.11.2011, to initiate time bound steps for devolution of power to grass root level in Karbi Anglong , and ensuring increased capacity building for development activities at all levels. As per para 9.4 of this agreement, a special economic package of Rs. 350 crore ( Rs. 70 crores per annum) over and above Plan fund over next five years will be provided to KAATC to provided through State Government.

2. In order to expedite release of funds for KAATC projects, Ministry of DONER has, after careful consideration , finalized following guidelines to process such cases. These guidelines will come into force with immediate effect.

1. KAATC will prepare an annual list of priority projects ( hereinafter referred as ‘Priority List’), keeping in view MoS for Karbi Anglong Autonomous Territotial Council area for balanced development of socio-economic infrastructure and will submit same to Ministry of DONER through Government of Assam.

Priority List should be accompanied with Concept Papers of each project will include details of major components of projects alongwith Estimated Cost of the item of works, Benefits to accrue from the projects, Implementing Department, completion Schedule, work Plan etc.

1. NLCPR Committee under Chairmanship of Secretary, DONER will consider these projects in overall context of Accord and recommend retention of projects for sanction.
2. Government of Assam/ KAATC will be intimated regarding retention of Projects after which Detailed Project Reports (DPRs) will be prepared by State Government /KAATC in accordance with Concept Papers for each of Projects and State Government will carry out techno economic examination of these DPRs by a competent technical authority.
3. State Government will constitute a Standing Committee under Chairmanship of Chief Secretary, Assam with following members :
4. Principal Secretary/ Commissioner, Planning Department.
5. Principal Secretary/ Commissioner, Finance Department.
6. Principal Secretary/ Commissioner, Hill Areas Department.
7. Principal Secretary, KAATC.
8. Principal Secretary , Home & Political Department.
9. Commissioner/ Secretary to the Chief Minister.

This Committee may co-opt any other officer/ representative of Government for assistance. The Standing Committee will consider DPRs along with comments/reports of competent authority regarding techno-economic examination of the project.

1. Standing Committee while approving DPR (s) will firm up cost of Project(s). Copy of DPR, alongwith copy of techno-economic analysis and recommendation of Standing Committee will be sent to the Ministry of DONER.
2. Work of preparation of DPRs, their techno-economic examination and their approval by Standing Committee will be completed within a period of 3 months from date of retention of the Project.
3. Standing Committee will also decide implementing agency and fix time limit for implementation of the project.
4. On receipt of approval of Standing Committee aor a project , 50% of firmed up cost will be released by Ministry of DONER to state Government immediately.
5. Tate Government will send a copy of Administrative & Financial approval of each project to Ministry of DONER immediately on receipt of release of 1st installment.
6. After 75% of released amount of first installment is utilized, KAATC through Govt. of Assam will send a proposal to Ministry of DONER with relevant UCs, QPRs ( on the proforma already prescribed for NLCPR projects), Inspection Report, Work Plan and Photographs etc. of completed works (depicting mandatory signboards) for release of balance 50% or balance amount of approved project cost.
7. Standing Committee will monitor, review and evaluate progress of implementation periodically with special reference to time limits fixed for various stages of implementation. Standing Committee will also ensure thet completion report of project is sent to Ministry of DONER immediately after project amount of approved project cost.
8. KAATC / Government of Assam will ensure timely implementation/ completion of the projects in accordance with the approved cost and no revision/ escalation in the project cost will be entertained.

Sd/-

( Rajesh Kumar)

Director

Tele. : 2379 4689, Fax : 2301 5360

Copy to :

1. Chief secretary, Government of Assam,
2. Shri Bhupen Nath Sharma, Principal Secretary, Karbi Anglong Autonomous Territorial Council, Diphu.
3. Joint Secretary & Financial Adviser, Ministry of Development of North Eastern Region,Vigyan Bhawan annexe, New Delhi.
4. Shri Shambhu Singh, JS-NE, Ministry of Home Affairs, North Block, New Delhi.
5. Shri S.N. Brohmo Choudhury, Adviser (NE), Planning Commission, Yojana Bhavan, Sansad Marg, New Delhi-110001.
6. Shri Rajiv Kumar, Joint Secretary (PF.I), Department of Expenditure,M/o Finance, North Block, New Delhi.
7. CCA (Home), North Block, New Delhi.
8. PS to Hon’ble Minister, M/o DoNER, New Delhi.
9. Director (IFD), M/o DoNER, NEW Delhi.
10. Director (PRP), M/o DoNER, NEW Delhi.
11. PPS to Secretary, M/o DoNER, NEW Delhi
12. Guard File.