## Sheet1
STATUS OF NEC FUNDED ONGOIN PROJECTS/SCHEMES (PRIORITY LIST)
(Rs. in Lakh)
Sl. No. | Name of the Project | Department | Date of Administrative Approval of the Project by NEC | Total Estimated Cost of the Project | NEC's Share Amount | Target Date of Completion | Instalment Released by NEC |  | Amount recommended by T & D | Deptt. yet to move for fund against NEC release | Amount released by FD |  | UC submitted | UC pending against the NEC release | UC pending against the FD release | State Share |  |  |  |  | Physical Progress | Remark
[7 empty] | Date | Amount |  |  | Date | Amount |  |  |  | Total State Share | Amount recommended by P & D | State share recommended by T&D | State Share Released by FD | State Share UC Submitted
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 11 | 12 | 13 | 15 | 16 | 14 | 17 | 15 | 16 | 17 | 21 | 22
Prior to 11th Plan
1 | Construction of double lane R.C.C. Bridge & approaches over river Barak at Fulertal in Assam. | PWD | 11.09.2012 | 1927 | 1734.3 |  | 2004-05 to 2013-14 (Rs.1706.10 lakh) + 21-2-2017 (Rs.57.50 lakh) | 1763.6 | 1706.1 | 57.5 | 2006-07 to 2013-14 | 1706.1 | 1706.1 | 57.5 | 0 | 192.7 |  | 192.7 | 192.6 | 189.57 | 100% | Deptt. to move for balance G.S. Closure certificate awaited.
2 | Bhanga-Anipur-Kanaibazar Road | PWD | 18.08.2004 | 8649.88 | 7814.89 |  | 2003-04 to 2011-12 | 7670 | 7476.92 | 193.08 | 2004-05 to 2013-14 | 7476.92 | 7432.3 | 237.7 | 44.62 | 834.99 |  | 834.99 | 834.99 | 834.99 | 100% | Deptt. to move for balance amount of CS. UC and Closure certificate awaited.
During 11th Plan
3 | Mairang-Ranigodown-Azara Road | PWD | 22.12.2010 | 2494 | 2244.6 |  | 2009-10 to 2011-12 | 1985 | 2244.6 | 0 | 2010-11 to 2013-14 | 2244.6 | 1985 | 259.6 | 259.6 | 249.4 |  | 249.4 | 249.4 | 249.4 | 100% | Deptt. to move for balance GS. UC and CC awaited.
[7 empty] | 2016-17 | 259.6 |  | 259.6 |  |  |  |  | 0
[7 empty] | Total | 2244.6 |  | 2244.6 |  |  |  |  | 0
4 | Improvement of Jowai Natrang Khanduli Baithalangso Road | P.W.D | 23.02.2011 | 7100 | 6390 | March, 2011 | 27/05/2011 | 1050 | 4180.0637 | 369.9363 | 2011-12 to 2012-13 | 4096.96 | 3588.968 | 961.032 | 507.992 | 710 |  | 105 | 105 | 105 | 33% | Due to court case the project was delayed. Now it is solved and work is in progress. UC of Rs.486.09 lakh is under process.
[7 empty] | 18/10/2012 | 1500 |  | 1500 |  |  |  |  | 0
[7 empty] | 2013-07-08 | 2000 |  | 2000 |  |  |  |  | 0
[7 empty] | Total | 4550 |  | 4550 |  |  |  |  | 0
[10 empty] | 0 |  |  |  |  | 0
5 | Improvement & Widening from one half lane to double lane of Silchar - Kalain Road connecting to NH-44 at Kalain | P.W.D | 18.02.2010 | 5925 | 5332.5 | March, 2010 (O) March, 2013 (R) | 18/02/2010 | 1200 | 5214.56 | 85.44 | 2009-10 to 2014-15 | 5205.23 | 5104.9 | 195.1 | 100.33 | 592.5 |  | 592.5 | 592.5 | 592.5 | 100% | UC of Rs.100.32 lakh is under process. Closure certificate awaited.
[10 empty] | 0 |  |  |  |  | 0
[7 empty] | 25/04/2012 | 2000 |  | 2000 |  |  |  |  | 0
[7 empty] | 24/09/2013 | 1000 |  | 1000 |  |  |  |  | 0
[7 empty] | 16/12/2014 | 1100 |  | 1100 |  |  |  |  | 0
[7 empty] | Total | 5300 |  | 5300 |  |  |  |  | 0
6 | Construction of Bhawanipur NH-31 to Manas National Park via Saudarvitha Ananda Bazar Road in Assam | P.W.D | Rs.5838.00 lakh (original) 19.02.2013. Rs.5777.00 lakh (Revised) 6.02.2017 | 5777 | 5199.3 | 2016-07-12 | 2013-14 | 1000 | 4800 | 0 | 2013-14 to 2015-16 | 4799.9983 | 4799 | 1 | 0.99827 | 577.7 |  | 380 | 380 | 379.6238 | 92%
[10 empty] | 0 |  |  |  |  | 0
[7 empty] | 2014-15 | 2000 |  | 2000 |  |  |  |  | 0
[7 empty] | 2015-16 | 800 |  | 800 |  |  |  |  | 0
[7 empty] | 2016-17 | 1000 |  | 1000 |  |  |  |  | 0
[7 empty] | Total | 4800 |  | 4800 |  |  |  |  | 0
During 12th Plan
7 | Improvement/Upgradation of Pakke-Seijosa-Itakhola Road | PWD | 02.06.2015 | 1376 | 1238 |  | 2/6/2015 (Rs.500.00 lakh) + 29-3-2017 (Rs.679.39 lakh) | 1179.39 | 500 | 679.39 | 2015-16 | 497.2 | 497.155 | 682.235 | 0.04502 | 137.6 |  | 51.18 |  | 0 | 36% | Deptt. to move for NEC share and to submit UC.
| Sub Total PWD |  |  | 33248.88 | 29953.59 |  |  | 27507.59 | 26122.2437 | 1385.3463 |  | 26027.0083 | 25113.423 | 2394.167 | 913.5853 | 3294.89 |  | 2405.77 | 2354.49 | 2351.0838
Prior to 11th Plan
8 | Preparation of project profile for Tourism infrastructure development in BTC. | *WPT & BC | 29/8/2006 | 200 | 180 | 3 years from the date of approval | 29/8/2006 | 180 | 90 | 90 |  | 90 | 90 | 90 | 0 | 20 |  |  | 0 | 0 | 50% | In the review meeting the Deptt. was asked to close the project.
During 12th Plan
9 | Pineapple cultivation at Athiabari, Kokrajhar | *WPT & BC | 2012-03-12 | 210.37 | 189.33 | 3 years from the date of approval | 2012-03-12 | 70 | 70 | 0 | 2014-15 | 43.1 |  | 70 | 43.1 | 21.04 |  |  | 0 | 0 | 44.3% | latest QPR and UC and photographs are awaited. Deptt. is requested to move for release of State Share and to submit UC.
10 | Horticulture and Floriculture in BTAD area | *WPT & BC | 03/12/2012 | 362.87 | 326.58 | 3 years from the date of approval | 2012-03-12 | 120 | 120 | 0 | 2013-14 | 120 | 120 | 0 | 0 | 36.29 |  |  | 0 | 0 | 78% | 2nd installment is awaited from NEC. Deptt to move for SS. Deptt. is asked to submit monitoring report.
11 | Development of the Socio-Economic Status of Rural Tribal Women at Sidli Dev. Block of Kajalgaon Sub-Division, Chirang | *WPT & BC | 4th March, 2014 | 466.76 | 420.08 | 3 years from the date of approval | 4/3/2014 Rs.100.00 lakh + 28/2/2017 Rs.168.00 lakh | 268 | 100 | 168 |  | 100 | 100 | 168 | 0 | 46.68 |  | 10 | 0 | 0 | 55% | Deptt. to move for GS and submit UC, QPR and photographs. Deptt. is asked to submit monitoring report before revalidation of A/A.
12 | Construction of Market Shed at Salbari bazar at Mushalpur | *WPT & BC | 4th March, 2014 | 187.55 | 168.8 | 3 years from the date of approval | Rs.50.64 lakh 4/3/2014 + Rs.67.52 lakh | 118.16 | 50.64 | 67.52 |  | 50.64 | 50.64 | 67.52 | 0 | 18.75 |  | 5.064 |  | 0 | 43% | Deptt. to move for GS and submit UC, QPR and photographs.
13 | Construction of Fish Farm at Bherabari, part-I, Assam | *WPT & BC | 28-01-2013 | 449.85 | 404.86 | 3 years from the date of approval | 28-01-2013 | 130 | 130 | 0 | 2014-15 | 65 | 65 | 65 | 0 | 44.99 |  |  | 0 | 0 | 32% | Deptt. to move for S.S and submit UC, QPR and photographs for onward submission to NEC. Deptt. is asked to submit monitoring report.
14 | Construction of Saviour Orphan Children Home at Gossaigaon, Kokrajhar | *WPT & BC | 5th March, 2014 | 294.33 | 264.9 |  | Rs.106.00 lakh 5/3/2014 + Rs.35.00 lakh 30/3/2016 | 141 | 106 | 35 |  | 106 | 0 | 141 | 106 | 29.43 |  |  |  |  | 67% | Deptt. is requested to submit UC. QPR etc. Deptt. is requested to move for release of SS and to submit UC, QPR and photograph.
15 | Augmentation f Rubber Plantation and Production for Economic Development of Educated Unemployed Indegeneous Tribal Communities in BTAD Area, Chirang Dist (BTC) | *WPT & BC | 28/2/2017 | 96.8 | 87.12 |  |  | 34.84 |  | 34.84 |  |  |  | 34.84 | 0 | 9.68 | [5 empty] | New scheme
| Sub Total WPT & BC |  |  | 2268.53 | 2041.67 |  |  | 1062 | 666.64 | 395.36 |  | 574.74 | 425.64 | 636.36 | 149.1 | 226.86 | 0 | 15.064 | 0 | 0
During 12th Plan
16 | Estt. Of Deori Tribel Cultural Complex at Narayanpur, Lakhimpur | CULTURAL AFFAIRS | 25-04-2012 | 497 | 447.3 | March'2017 | 2012-02-04 | 120 | 120 | 0 | 2014-15 | 120 | 85.03 | 34.97 | 34.97 | 49.7 |  | 12 | 12 | 0 | 50% | UC is awaited for remaining amount.
17 | Tai Education & Cultural Centre at Niz-Kadamoni, Dibrugarh | CULTURAL AFFAIRS | 25/2/2014 | 333.49 | 300.14 | 3 years from the date of approval | 25/2/2014 | 120 | 76.8546 | 43.1454 |  | 76.806 | 76.8061 | 43.1939 | -0.0001 | 33.35 |  |  | 0 | 0 | 47% | Deptt. to move for remaining CS and SS and submit UC, QPR and photographs.
| Sub -Total Cultural Affairs |  |  | 830.49 | 747.44 |  |  | 240 | 196.8546 | 43.1454 |  | 196.806 | 161.8361 | 78.1639 | 34.9699 | 83.05 |  | 12 | 12 | 0
18 | Yatri Niwas, Paltanbazar | TRANSPORT : | 25-07-2005 | 1124.47 | 1012.02 | Project is already completed. | 25/07/2005 | 90 | 990 |  | 2005-06 to 2008-09 | 990 | 990 | 0 | 0 | 112.45 | 94.21 | 94.21 | 94.21 | 94.21 | 100% | Project is already completed. NEC informed that Deptt. had not handed over the space to NEC as per MOU. Department is intimated. Deptt. is asked to conduct and enquiry. NEC has requested to refund the amount of Rs.990.00 lakh as it is deviated as per letter no.NEC/IND/RM/195/2012, dated 8-6-2017.
0
[7 empty] | 28/03/2007 | 300 | [6 empty] | 0
[7 empty] | 13/03/2008 | 500 | [6 empty] | 0
[7 empty] | 30/03/2009 | 100 | [6 empty] | 0
[7 empty] | Total | 990 | [6 empty] | 0
| Sub Total Transport |  |  | 1124.47 | 1012.02 |  |  | 990 | 990 | 0 |  | 990 | 990 | 0 | 0 | 112.45 |  | 94.21 | 94.21 | 94.21
19 | Construction of Regional Multi-Utility Town hall and Cultural Centre in Tinsukia | URBAN DEVELOPMENT | 28-2-14 | 798 | 718.2 | Dec'2017 | 28-02-2014 | 287.28 | 286.18 | 1.1 |  | 286.18 | 286.18 | 1.1 | 0 | 79.8 |  |  |  |  | 42% upto October,16 | UC submitted in June 2017. Deptt. to move for S.S
| Sub Total Urban Development |  |  | 798 | 718.2 |  |  | 287.28 | 286.18 | 1.1 |  | 286.18 | 286.18 | 1.1 | 0 | 79.8 |  | 0 | 0 | 0
During 12th Plan
20 | Setting up of a Handloom Trade Centre at Dibrugarh, Assam | HANDLOOM & TEXTILE | 26/3/2013 | 991.7 | 892.53 | 28-2-2017 | 26/3/2013 | 49.57 | 49.57 | 0 |  | 49.57 |  | 49.57 | 49.57 | 99.17 | 99.17 | 4.95 | 4.95 |  | 10% | Deptt. has submitted UC and it is under process.
21 | Economic Upliftment through Innovative value added handloom Weaving in Jorhat, Golaghat and Lakhimpur District, Assam | HANDLOOM & TEXTILE | 2014-04-03 | 415.54 | 373.99 | 2016-04-03 | 2014-04-03 | 149.59 | 149.59 | 0 |  | 90 |  | 149.59 | 90 | 41.56 | 41.56 |  |  |  | 20% | UC is awaited.
| Sub Total Handloom & Textile |  |  | 1407.24 | 1266.52 |  |  | 199.16 | 199.16 | 0 |  | 139.57 | 0 | 199.16 | 139.57 | 140.73 | 140.73 | 4.95 | 4.95 | 0
During 12th Plan
22 | Employable Skill Development ,Assam | SERICULTURE | 15th Feb., 2014 | 383.53 | 345.18 |  | 15/3/2014 Rs.69.00 lakh + 28/2/2017 Rs.80.00 lakh | 149 | 69 | 80 |  | 69 | 69 | 80 | 0 | 38.35 |  |  |  |  | 100%
23 | Up-gradation of Serculture Training Institute at Titabor, Jorhat | SERICULTURE | 18th Dec., 2014 | 1281.81 | 1153.63 | 31/3/2018 (date of commencement 7/2/2015) | 18/12/2014 | 283.62 | 283.62 | 0 |  | 283.62 | 283.62 | 0 | 0 | 128.18 |  | 28.362 | 28.362 | 28.362 | 33% | 2nd installment is awaited from NEC.
| Sub Total Sericulture |  |  | 1665.34 | 1498.81 |  |  | 432.62 | 352.62 | 80 |  | 352.62 | 352.62 | 80 | 0 | 166.53 |  | 28.362 | 28.362 | 28.362
Support to Devlt..of Addl. Facilities for Specialisation and Super-Speciality in three Medical Colleges in Assam
Prior to 11th Plan
24 | a) G.M.C, Guwahati (Capital) | HEALTH & FAMILY WELFARE | 2005-09-09 | 728.85 | 1111.82 | 31/3/2010 |  |  | 729.19 | 0
| Capital | [5 empty] | 17/3/2003 | 27.71 |  | 27.71 |  | 729.19 | 729.19 | 0 | 0 | 72.89 |  | 34.48 | 34.48 | 34.48 | 95% | UC is awaited.
[7 empty] | 24/4/2003 | 29.7 |  | 29.7 |  |  |  |  | 0
[7 empty] | 27/08/2003 | 70.53 |  | 70.53 |  |  |  |  | 0
[7 empty] | 13/2/2004 | 10.79 |  | 10.79 |  |  |  |  | 0
[7 empty] | 31/3/2004 | 1.2 |  | 1.2 |  |  |  |  | 0
[7 empty] | 31/3/2004 | 14.78 |  | 14.78 |  |  |  |  | 0
[7 empty] | 2005-09-09 | 315 |  | 315 |  |  |  |  | 0
[7 empty] | 28/3/2007 | 225 |  | 225 |  |  |  |  | 0
[7 empty] | Total | 729.19 |  | 729.19 |  |  |  |  | 0
| Revenue |  |  | 506.5 |  |  |  |  | 406.64 | 0.82 |  | 419.21 | 353.17 | 66.86 | 66.04 | 50.65 |  | 46.66 | 27.11 | 27.11
[7 empty] | 2003-04-03 | 178.66 | 12.57 | 166.09 |  |  |  |  | 0
[7 empty] | 21/6/2004 | 57.6 |  | 57.6 |  |  |  |  | 0
[7 empty] | 19/3/2009 | 183.77 |  | 183.77 |  |  |  |  | 0
[7 empty] | Total | 420.03 | 419.21 | 0.82 |  |  |  |  | 0
25 | b) A.M.C, Dibrugarh | HEALTH & FAMILY WELFARE | 15-03-2005 | 300.87 | 740.67 | 31/3/2012 | 15/3/2005 | 90 | 270.78 | 0 |  | 270.78 | 270.78 | 0 | 0 | 30.09 |  | 12.47 | 12.47 | 12.47 | 95%
| Capital | [8 empty] | 0 |  |  |  |  | 0
[10 empty] | 0 |  |  |  |  | 0
[7 empty] | 2008-11-03 | 100 |  | 100 |  |  |  |  | 0
[7 empty] | 2009-07-09 | 80.78 |  | 80.78 |  |  |  |  | 0
[7 empty] | Total | 270.78 |  | 270.78 |  |  |  |  | 0
| Revenue |  |  | 522.1 |  |  |  |  | 225.26 | 0 |  | 225.26 | 221.73 | 3.53 | 3.53 | 52.21 |  |  | 0 | 0
[7 empty] | 15/3/2005 | 165.15 |  | 165.15 |  |  |  |  | 0
[7 empty] | 23/2/2011 | 60.11 |  | 60.11 |  |  |  |  | 0
[7 empty] | Total | 225.26 |  | 225.26 |  |  |  |  | 0
26 | c) S.M.C, Silchar | HEALTH & FAMILY WELFARE | 9/9/05 | 682.9 | 1257.38 | 31/3/2012 |  |  | 614.61 | 0 |  | 614.61 | 614.57 | 0.04 | 0.04 | 68.29 |  |  |  |  | 95%
| Capital | [8 empty] | 0 |  |  |  |  | 0
[7 empty] | 23/3/2004 | 45 |  | 45 |  |  |  |  | 0
[7 empty] | 2004-08-09 | 180 |  | 180 |  |  |  |  | 0
[7 empty] | 2005-09-09 | 180 |  | 180 |  |  |  |  | 0
[7 empty] | 16/10/2009 | 119.22 |  | 119.22 |  |  |  |  | 0
[7 empty] | 2011-08-02 | 90.39 |  | 90.39 |  |  |  |  | 0
[7 empty] | Total | 614.61 |  | 614.61 |  |  |  |  | 0
| Revenue |  |  | 714.19 |  |  |  |  | 593.15 | 49.62 |  | 593.15 | 593.15 | 49.62 | 0 | 71.42 |  | 25.62 | 25.62 | 25.62
[7 empty] | 2005-09-09 | 137.7 |  | 137.7 |  |  |  |  | 0
[7 empty] | 24/3/2009 | 225 |  | 225 |  |  |  |  | 0
[7 empty] | 2011-08-02 | 49.5 |  | 49.5 |  |  |  |  | 0
[7 empty] | 16/10/2009 | 230.57 |  | 230.57 |  |  |  |  | 0
[7 empty] | Total | 642.77 |  | 642.77 |  |  |  |  | 0
27 | Regional Dental College, Guwahati. | HEALTH & FAMILY WELFARE | 16-03-2005 | 436.95 | 1179.85 | 31/3/2012 |  |  | 393.4 | 0 |  | 393.4 | 393.4 | 0 | 0 | 43.7 |  | 0.14 | 0.14 | 0.14 | 95%
| Capital | [8 empty] | 0 |  |  |  |  | 0
[7 empty] | 16/3/2005 | 90 |  | 90 |  |  |  |  | 0
[7 empty] | 28/3/2007 | 80 |  | 80 |  |  |  |  | 0
[7 empty] | 13/9/2007 | 62.58 |  | 62.58 |  |  |  |  | 0
[7 empty] | 18/3/2008 | 76.84 |  | 76.84 |  |  |  |  | 0
[7 empty] | 23/11/2009 | 83.84 |  | 83.84 |  |  |  |  | 0
[7 empty] | Total | 393.4 |  | 393.4 |  |  |  |  | 0
| Revenue |  |  | 873.99 |  |  |  |  | 325 | 0 |  | 325 | 325 | 0 |  | 87.4 |  | 15 | 15 | 15
[7 empty] | 16/3/2005 | 135 | [6 empty] | 0
[7 empty] | 23/6/2008 | 90 | [6 empty] | 0
[7 empty] | 25/1/2011 | 100 | [6 empty] | 0
[7 empty] | Total | 325 | [6 empty] | 0
28 | Regional Nursing College, Guwahati. | HEALTH & FAMILY WELFARE | 16-03-2005 | 437.31 | 516.1 | 31/3/2010 |  |  | 423.8 | 0 |  | 423.8 | 423.8 | 0 | 0 | 43.73 |  | 30.22 | 30.22 | 30.22 | 95%
| Capital | [8 empty] | 0 |  |  |  |  | 0
[7 empty] | 16/3/2005 | 99 |  | 99 |  |  |  |  | 0
[7 empty] | 2007-03-09 | 135 |  | 135 |  |  |  |  | 0
[7 empty] | 17/3/2008 | 90 |  | 90 |  |  |  |  | 0
[7 empty] | 2009-12-11 | 69.58 |  | 69.58 |  |  |  |  | 0
[7 empty] | Total | 423.8 |  | 423.8 |  |  |  |  | 0
| Revenue |  |  | 135.83 |  |  |  |  | 119.84 | 2.41 |  | 119.84 | 115.86 | 6.39 | 3.98 | 13.58 |  | 4 | 4 | 4
[7 empty] | 16/3/2005 | 36 |  | 36 |  |  |  |  | 0
[7 empty] | 2008-02-06 | 86.25 |  | 86.25 |  |  |  |  | 0
[7 empty] | Total | 122.25 |  | 122.25 |  |  |  |  | 0
During 11th Plan
29 | Infrastructure Dev. of Academic facilities at Down Town College of allied Health Science at Panikheti | HEALTH & FAMILY WELFARE | 20/3/2010 | 460 | 414 | 31/3/2012 | 21/3/2011 | 100.58 | 300.58 | 0 |  | 300.58 | 200 | 100.58 | 100.58 | 46 |  | 22.29 | 22.29 | 22.29 | 60% | UC awaited.
0
[7 empty] | 2011-05-09 | 100 | [6 empty] | 0
[7 empty] | 2013-14 | 100 | [6 empty] | 0
[7 empty] | Total | 300.58 | [6 empty] | 0
30 | Estt. of Modern Burn Care Centre at Nemcare Hospital, Guwahati | HEALTH & FAMILY WELFARE | 26/02/09 | 300 | 270 |  | 26/02/09 | 90 | 270 | 0 |  | 270 | 190 | 80 | 80 | 30 |  | 30 | 30 | 29.79 |  | UC awaited.
[7 empty] | 31/01/11 | 100 |  | 100 |  |  |  |  | 0
[7 empty] | 2012-05-01 | 80 |  | 80 |  |  |  |  | 0
[7 empty] | Total | 270 |  | 270 |  |  |  |  | 0
[10 empty] | 0 |  |  |  |  | 0
31 | Support to Govt. Hospitalship on the river Brahmaputra by centre for NE studies and Research | HEALTH & FAMILY WELFARE | 2009-11-03 | 400 | 360 | 31/12/2012 | 31/11/2009 | 40 | 219.31 | 20.69 |  | 219.91 | 90 | 150 | 129.91 | 40 |  |  |  |  | 34% | UC awaited.
[10 empty] | 0 |  |  |  |  | 0
[7 empty] | 19/10/2012 | 200 |  | 200 |  |  |  |  | 0
[7 empty] | Total | 240 |  | 240 |  |  |  |  | 0
32 | Constn.of 100 Beded Hospital at Sonari | HEALTH & FAMILY WELFARE | 15/3/2004 | 417.31 | 375.58 | 31/3/2012 | 2005-03-01 | 135 | 286.08 | 0 |  | 312.09 | 312.09 | 0 | 0 | 41.73 |  | 41.73 | 41.73 | 32.83 | 95% | Deptt. was requested for early completion of civil constn. & submit UC & CC.
[9 empty] | 9.33 | -9.33 |  |  |  |  | 0
[7 empty] | 22/7/2005 | 106.97 |  | 106.97 |  |  |  |  | 0
[7 empty] | 2011-11-01 | 53.44 |  | 53.44 |  |  |  |  | 0
[7 empty] | Total | 312.09 | 312.09 | 0 |  |  |  |  | 0
33 | Constn. of Vertical Extn. of 1st floor (Part) 2nd & 3rd floors of MDS Building at RDC, Ghy | HEALTH & FAMILY WELFARE | 2012-03-09 | 461.82 | 415.64 | 31/3/2015 |  |  | 291.82 | 0 |  | 269.59 | 265.59 | 26.23 | 4 | 46.18 |  | 37.8 | 37.8 | 32.42 | 100% | Fund awaited from NEC.
[7 empty] | 2012-03-09 | 130 |  | 130 |  | 22.23 |  |  | 22.23
[7 empty] | 16/03/2015 | 161.82 |  | 161.82 |  |  |  |  | 0
[7 empty] | Total | 291.82 |  | 291.82 |  | 291.82 |  |  | 291.82
34 | Strengthing of Ortho Deptt. at GMC | HEALTH & FAMILY WELFARE | 26/11/2012 | 1493.77 | 1344.39 | 31/3/2015 | 26/11/2012 | 400 | 400 | 0 |  | 278.16 | 396.51 | 3.49 | 0.01 | 149.38 | [5 empty] | Deptt. is yet to submit U.C of grant share. Deptt. may move for release of S/S
[10 empty] | 0 |  | 118.36 |  |  | 118.36
[10 empty] | 0 |  | 396.52 |  |  | 396.52
| Sub Total Health & FW |  |  | 8872.39 | 7985.43 |  |  | 5981.58 | 5908.04 | 73.54 |  | 5905.16 | 5494.84 | 486.74 | 410.32 | 887.25 |  | 300.41 | 280.86 | 266.37
During 11th Plan
35 | Construction of 132/33 KV,1.16 MVA Umrangshu Dima Hassao (N.C. Hills) Dist., Assam | POWER | 2011-03-01 | 1344 | 1209.6 | June'2013 (O) Sept'2016 (R) |  |  | 1087 | 0 | 2013-14 | 1087 | 1087 | 0 | 0 | 134.4 | 59.67 | 59.67 | 59.67 | 59.67 | 95%
[7 empty] | 2011-03-01 | 537 |  | 537 |  |  |  |  | 0
[7 empty] | 21/11/2013 | 550 |  | 550 |  |  |  |  | 0
[7 empty] | Total | 1087 |  | 1087 |  |  |  |  | 0
36 | Lugnit small H.E. project in Karbi Anglong | POWER | 25-03-2008 | 500 | 450 | March, 2012 (O) March, 2015 (R ) | 25/3/2008 | 150 | 150 | 0 |  | 150 | 150 | 0 | 0 | 50 |  |  | 0 | 0 | 17% | NEC decided to close the project.
37 | Amring small H.E. project in Karbi Anglong. | POWER | 25-11-2008 | 211 | 189.9 | Work completed in all respects in 30/09/2014 | 25/11/2008 | 40 | 79.072 | 10.928 |  | 40 | 79.07 | 10.93 | 0 | 21.1 |  |  | 0 | 0 |  | Project completed. No more fund is required. NEC decided to close the project.
[10 empty] | 0 |  | 15 |  |  | 15
[7 empty] | 2014-04-06 | 50 |  | 50 |  | 24.07 |  |  | 24.07 | [5 empty] | 100%
[7 empty] | Total | 90 |  | 90 |  | 79.07 |  |  | 79.07
During 12th Plan
38 | Augmentation of transformer capacity of 220X132 kv BTPS Sub-Station from 1x160MVA+IX80MVA to 2x160 | POWER | 20-5-2016 | 678 | 610.2 |  | Rs.240.00 lakh 20/5/2016 + Rs.240.00 lakh 18/7/2017 | 480 | 240 | 240 |  | 240 | 240 | 240 | 0 | 67.8
39 | Construction of 33/11kv,2x5MVA Sub-Station alongwith associated 33kv,11kv &LT Feeders at Bishnupur Panch ali under Dhemaji Electrical Division APDCL, Dhemaji. | POWER | 20-5-2016 | 1025 | 922.5 |  | 20/5/2016 | 370 | 370 | 0 |  | 370 |  | 370 | 370 | 102.5 | [5 empty] | UC is awaited.
40 | Augmentation of transformer capacity of 132/33 kv Biswanath Chariali (Pavoi) Sub-Station from2x16MVA to 2x40 MVA | POWER | 20-5-2016 | 709 | 638.1 |  | Rs.260.00 lakh 20/5/2016 + Rs.250.00 lakh 18/7/2017 | 510 | 260 | 250 |  | 260 | 260 | 250 | 0 | 70.9
| Sub Total Power |  |  | 4467 | 4020.3 |  |  | 2687 | 2186.072 | 500.928 |  | 2186.07 | 1816.07 | 870.93 | 370 | 446.7 |  | 59.67 | 59.67 | 59.67
| During 12th Plan | [13 empty] | 0
41 | Financial support for students of NER | EDUCATION |  | 112.72 |  | continuing process | 17/1/2017 | 112.72 |  |  |  |  | 0 |  | 0 | [6 empty] | Fund directly released by Deptt. and UC submitted directely.
42 | Construction of RCC(G+2) building for Seminar Hall,Computer Centre and facilitates for car parking at Darrang College, Tezpur,Assam. | EDUCATION | 21-11-2012 | 229.55 | 206.6 | Dec,2016 | Rs.82.64 lakh 21/11/2012 + Rs.39.60 lakh 22/2/2017 | 122.24 | 82.64 | 39.6 |  | 82.64 | 82.64 | 39.6 | 0 | 22.96 | 9.18 | 9.18 | 9.18 |  | 50% | 2nd installment of Rs.39.60 lakh released by NEC 22/2/2017
43 | Infra-structure Development of Bagnibar Nilamoni Phukan H.S. School, Dibrugarh, Victoria Girl's H.S. School and A.R.T. High School at Margherita, Assam. | EDUCATION | 18-02-2013 | 400 | 360 | June, 2016 | Rs.120.00 lakh 18-02-2013 + Rs.119.42 lakh 22/2/2017 | 239.42 | 120 | 119.42 |  | 120 | 120 | 119.42 | 0 | 40 |  | 12 | 12 |  | Bagnibar - 76% Victoria - 73% A.R.T. - 43% | fund awaited from NEC
44 | Construction of Auditorium Hall at Chamata Higher Secondary School, Nalbari | EDUCATION | 18/12/14 | 205 | 184.5 | March, 2017 | Rs.73.8 lakh 18/12/14 + Rs.73.8 lakh | 147.6 | 73.8 | 73.8 |  | 73.8 | 73.8 | 73.8 | 0 | 20.5 |  | 7.38 | 7.38 | 7.3 | 85%
45 | Construction of Chandranath Sarmah Higher Secondary School, at Bihaguri, sonitpur | EDUCATION | 5/3/15 | 318.3 | 286.47 | March, 2018 | 5/3/15 | 62.24 | 62.24 | 0 |  | 62.24 |  | 62.24 | 62.24 | 31.83 |  | 6.92 | 6.9155 | 6.92 |  | UC is awaited.
46 | Const./Re-modeling of RCC building including development of Library,Vocational Centre etc of Madhab Dev Higher Secondary School at Tulsimukh, Nagaon | EDUCATION | 20/5/16 | 318.88 | 287 |  | 20/5/16 | 115 |  | 115 |  |  |  | 115 | 0 | 31.88 | [5 empty] | Deptt. to move for fund.
| Sub Total Education |  |  | 1584.45 | 1324.57 |  |  | 799.22 | 338.68 | 460.54 |  | 338.68 | 276.44 | 410.06 | 62.24 | 147.17 |  | 35.48 | 35.4755 | 14.22
47 | Construction of Home for Cancer Affected Children by Dipshikha, Guwahati | SOCIAL WELFARE | 3/3/2014 | 389.68 | 350.71 |  | 2014-03-03 | 140.28 | 320.28 | 0 |  | 320.28 | 320.28 | 0 | 0 | 38.97 |  |  |  |  | 55%
[10 empty] | 0 |  |  |  |  | 0
[7 empty] | 22/3/2016 | 180 |  | 180 |  |  |  |  | 0
[7 empty] | Total | 320.28 |  | 320.28 |  |  |  |  | 0
| Sub Total Social Welfare |  |  | 389.68 | 350.71 |  |  | 320.28 | 320.28 | 0 |  | 320.28 | 320.28 | 0 | 0 | 38.97 |  | 0 | 0 | 0
During 12th Plan
48 | Organisation of International Conference on Look (Act) East Policy and North East India on 25th and 26th Sept. 2015 at Guwahati. | OKD and P&D |  | 5 |  |  |  | 4 | 4 | 0 |  | 4 | 4 | 0 | 0 | 0.5
| Sub Total OKD & P&D |  |  | 5 | 0 |  |  | 4 | 4 | 0 |  | 4 | 4 | 0 | 0 | 0.5 |  | 0 | 0 | 0
During 11th Plan
49 | Bio-diversity conservation Bashistha Bahini conservation watershed | SOIL CONSERVATION | 25-08-2009 | 496.76 | 447.08 | 25/8/2012 | 25/08/2009 | 40 | 320 | 127.08 |  | 320 | 320 | 127.08 | 0 | 49.68 | 32 | 32 | 32 | 32 | 100% | 4th and final installment Rs.127.08 lakh released on 22-03-2017 (Final installment) by NEC
[7 empty] | 14/03/2011 | 100 |  | 100 |  |  |  |  | 0
[7 empty] | 2013-03-11 | 180 |  | 180 |  |  |  |  | 0
[7 empty] | 22/3/2017 | 127.08 |  | 127.08 |  |  |  |  | 0
[7 empty] | Total | 447.08 |  | 447.08 |  |  |  |  | 0
| Sub Total Soil Conservation |  |  | 496.76 | 447.08 |  |  | 447.08 | 320 | 127.08 |  | 320 | 320 | 127.08 | 0 | 49.68 |  | 32 | 32 | 32
Prior to 11th Plan
50 | Controlling of jiadhal river in Dhemaji Dist. Ph-I | Water Resources | 27-02-2006 | 1493.57 | 1344.21 | Completed | 27/02/2006 | 547 | 945.61 | 0 |  | 945.61 | 945.61 | 0 | 0 | 149.36 | 143.38 | 143.38 | 143.38 | 143.38 | 100% | Remaining fund awaited from NEC
[7 empty] | 30/12/2013 | 398.61 | [6 empty] | 0
[7 empty] | Total | 945.61 | [6 empty] | 0
0
During 11th Plan
51 | Protection of Raimona village and its adjoining area from erosion of river Janali river in Kokrajhar Dist., Assam | Water Resources | 2011-01-02 | 374 | 336.6 | Completed | 2011-01-02 | 120 | 254.64 | 81.96 |  | 254.64 | 254.64 | 81.96 | 0 | 37.4 | 28.29 | 28.29 | 28.29 | 28.29 | 100% | 3rd and final installment of Rs.81.96 lakh released on 24-02-2017 (Final installment) by NEC
[7 empty] | 14/8/2012 | 134.64 | [6 empty] | 0
[7 empty] | 24/2/2017 | 81.96 | [6 empty] | 0
[7 empty] | Total | 336.6 | [6 empty] | 0
52 | Anti erosion measures to protect Ranipur and its adjoining areas from the erosion of river Pekua. | Water Resources | 23/03/2012 | 343.39 | 309.05 | Completed | 23/3/2012 | 100 | 223 | 86.05 |  | 223 | 223 | 86.05 | 0 | 34.34 | 11.11 | 11.11 | 11.11 | 11.11 | 100% | 3rd and final installment of Rs.86.05 lakh released on 27-02-2017 (Final installment) by NEC
[7 empty] | 2014-12-02 | 123 | [6 empty] | 0
[7 empty] | 27/2/2017 | 86.05 | [6 empty] | 0
[7 empty] | Total | 309.05 | [6 empty] | 0
53 | Anti erosion measures at different reaches on both bank of river Pomra | Water Resources | 4th June, 2014 | 227.94 | 205.15 | March, 2017 | 4/6/2014 Rs.82.06 03/06/16 Rs.82.00 | 164.06 | 164.06 | 0 |  | 164.06 | 164.06 | 0 | 0 | 22.79 | 9.18 | 9.12 | 9.12 | 9.12 | 68% | Fund awaited from NEC.
| Sub Total Water Resource |  |  | 2438.9 | 2195.01 |  |  | 1755.32 | 1587.31 | 168.01 |  | 1587.31 | 1587.31 | 168.01 | 0 | 243.89 |  | 191.9 | 191.9 | 191.9
During 11th Plan
54 | Dhankhunda FIS Kamrup | IRRIGATION | 22/09/2010 | 485 | 436.5 | Completed | 22/9/2010 | 145.5 | 436.5 | 0 |  | 436.5 | 392.85 | 43.65 | 43.65 | 48.5 | 48.5 | 48.5 | 48.5 | 44.14 | 100% | UC of last installment is awaited. (Final installment)
[10 empty] | 0 |  |  |  |  | 0
[7 empty] | 22/8/2012 | 174.6 |  | 174.6 |  |  |  |  | 0
[7 empty] | 2014-03-06 | 72.75 |  | 72.75 |  |  |  |  | 0
[7 empty] | 24/11/2015 | 43.65 |  | 43.65 |  |  |  |  | 0
[7 empty] | Total | 436.5 |  | 436.5 |  |  |  |  | 0
55 | Modernisation and Extension of Longparpam MIS, Karbi- Anglong District | IRRIGATION | 22/09/2010 | 213 | 191.7 | Completed in March 2013 | 22/9/2010 | 64 | 140.68 | 0 |  | 140.68 | 140.68 | 0 | 0 | 21.3 | 15.63 | 15.63 | 15.63 | 15.63 | Completed in March 2013 | project completed. Subsequent installment is awaited from NEC.
[7 empty] | 2012-07-08 | 76.68 |  | 76.68 |  |  |  |  | 0
[7 empty] | Total | 140.68 |  | 140.68 |  |  |  |  | 0
[10 empty] | 0 |  |  |  |  | 0
[10 empty] | 0 |  |  |  |  | 0
[10 empty] | 0 |  |  |  |  | 0
56 | Construction of Gilabwr-FIS | IRRIGATION | 23/3/2012 | 418 | 376.2 | Completed | 23/3/2012 | 100 | 325.48 | 50.72 |  | 325.48 | 325.48 | 50.72 | 0 | 41.8 | 27.83 | 27.83 | 27.83 | 27.83 | 100% | 4th and final installment of Rs.50.72 lakh released on 23-02-2017 by NEC
[7 empty] | 25/04/2014 | 150.48 |  | 150.48 |  |  |  |  | 0
[7 empty] | 2015-16 | 75 |  | 75 |  |  |  |  | 0
[7 empty] | 23/2/2017 | 50.72 |  | 50.72 |  |  |  |  | 0
[7 empty] | Total | 376.2 |  | 376.2 |  |  |  |  | 0
[10 empty] | 0 |  |  |  |  | 0
| During 12th Plan | [13 empty] | 0
57 | Ram Englee Minor Irrigation scheme in Karbi-Anglong Dist. Assam | IRRIGATION | 25/3/2013 | 494.7 | 445.23 | 25/3/2015 | 25/3/2013 | 140 | 318 | 127.23 |  | 318 | 318 | 127.23 | 0 | 49.47 | 15.55 | 15.55 | 15.55 |  | 100% | 3rd and final installment of Rs.127.23 lakh released on 23-02-2017 by NEC
[7 empty] | 2015-05-01 | 178 |  | 178 |  |  |  |  | 0
[7 empty] | 23/2/2017 | 127.23 |  | 127.23 |  |  |  |  | 0
[7 empty] | Total | 445.23 |  | 445.23 |  |  |  |  | 0
| Sub Total Irrigation |  |  | 1610.7 | 1449.63 |  |  | 1398.61 | 1220.66 | 177.95 |  | 1220.66 | 1177.01 | 221.6 | 43.65 | 161.07 |  | 107.51 | 107.51 | 87.6
During 11th Plan
58 | Estt. Of Cold Storage at Jorhat | AGRICULTURE | 21-10-2010 | 490.65 | 441.58 | October,2012 (O) 01/10/2016 (R) | 21/10/2010 | 176.63 | 441.58 | 0 |  | 254.08 | 254.08 | 187.5 | 0 | 49.07 | 28.23 | 28.23 | 28.23 | 28.23 | 98% | Project completed. Expenditure of excess amount from their own sources. Subsequent installment is awaited from NEC.
[7 empty] | 2015-16 | 77.45 |  | 77.45
[8 empty] | 187.5 |  | 187.5
[7 empty] | Total | 441.58 |  | 441.58
During 12th Plan
59 | Development of Fruits & Vegetable Market at Pamohi (Garchuk),Kamrup, Phase-III | AGRICULTURE | 20-05-2016 | 1401.28 | 1261.15 |  | 20/5/2016 | 100 |  | 100 |  |  |  | 100 | 0 | 140.13 | [5 empty] | A/A accorded by P & D.
| Sub Total Agriculture |  |  | 1891.93 | 1702.73 |  |  | 541.58 | 441.58 | 100 |  | 254.08 | 254.08 | 287.5 | 0 | 189.2 |  | 28.23 | 28.23 | 28.23
During 12th Plan
60 | Promotion of an Environmentally Sound Approach for Sustainable Water Management Optimizing Usage Rain Water Harvesting for Roof Tops in Institutions, Health centres & Community Centre. | PHE | 2015-01-12 | 1248 | 1235.52 |  | 2015-01-12 | 162.168 | 162.168 |  |  |  |  | 162.168 | 0 | 124.8 | [5 empty] | Deptt. is requested to release the fund early and submit UC.
| Sub Total PHE |  |  | 1248 | 1235.52 |  |  | 162.168 | 162.168 |  |  | 0 | 0 | 162.168 | 0 | 124.8 |  | 0 | 0 | 0
During 11th Plan
61 | Assam Polyster Cooperative Society Ltd. For Upgradation/Replacement of machineries of its spinning unit located atTulsibari, Rangia, Assam | CO-OPERATION | 22/11/2011 | 457.34 | 411.6 | 2 years from the date of approval | 22/11/2011 | 164.64 | 329.28 | 82.32 |  | 329.28 | 329.28 | 82.32 | 0 | 45.73 | 36.58 | 36.58 | 36.58 |  | 50% | Final installment of Rs.82.32 lakh released on 16/3/2017 by NEC
[7 empty] | 20/11/2013 | 164.64 | [6 empty] | 0
[7 empty] | 16/3/2017 | 82.32 | [6 empty] | 0
[7 empty] | Total | 411.6 | [6 empty] | 0
| Sub Total Co-operation |  |  | 457.34 | 411.6 |  |  | 411.6 | 329.28 | 82.32 |  | 329.28 | 329.28 | 82.32 | 0 | 45.73 |  | 36.58 | 36.58 | 0
During 11th Plan
62 | Publicity and Promotion of Tourism products of Assam with an innovative approach integrating advertisement through print and electronic media, outdoor media, organization of events and facelift of few tourist destinations | TOURISM | 28/3/2011 | 245.31 | 220.78 | 31/3/2012 | 28/3/2011 | 188.31 | 188.31 | 0 |  | 186.7131 | 89.16 | 99.15 | 97.5531 | 24.53 |  |  |  |  | 100% | Part UC received and Deptt. is requested to submit UC of entire amount.
During 12th Plan
63 | Tea Museum at Dibrugarh | TOURISM | 2014-05-03 | 314.41 | 282.97 |  | 2014-05-03 | 113.19 | 113.19 | 0 |  | 113.19 |  | 113.19 | 113.19 | 31.44 | [5 empty] | UC is awaited from Deptt.
64 | Destination North East - 2016 to be held on 12 -14 Feb. 2016 at Pragati Maidan, New Delhi. | TOURISM | 15/2/2016 | 10 |  |  | 15/2/12016 | 8 | 8 | 0 |  | 8 |  | 8 | 8 | 1 | [5 empty] | UC is awaited.
| Sub Total Tourism |  |  | 569.72 | 503.75 |  |  | 309.5 | 309.5 | 0 |  | 307.9031 | 89.16 | 220.34 | 218.7431 | 56.97 |  | 0 | 0 | 0
| During 11th Plan | [13 empty] | 0
65 | Eco-Tourism cum Botanical Garden and Orchid Culture at Jokai, Dibrugarh Assam. | ENVIRONMENT & FOREST | 22/3/2010 | 264.57 | 238.11 | 22/3/2011 | 2010-03-22 | 71.43 | 71.43 | 0 |  | 71.43 |  | 71.43 | 71.43 | 26.46 | [5 empty] | NEC approved Revised DPR in 2016. UC awaited from Deptt.
| Sub Total Forest |  |  | 264.57 | 238.11 |  |  | 71.43 | 71.43 | 0 |  | 71.43 | 0 | 71.43 | 71.43 | 26.46 |  |  | 0 | 0
66 | Beel Dev. For sustainable Livelihood in Dibrugarh, Golaghat, Nagaon and Darrang Districts of Assam | FISHERY | 2013-06-01 | 486.67 | 438 | 31-3-2016 | 6-3-2013 | 130 | 130 | 0 |  | 107.13 | 107.13 | 22.87 | 0 | 48.67 |  |  |  |  | Dibrugarh-38% Golaghat- 7% Nagaon - 35% Darrang - 81% | UC of balance along with S/S amount are awaited.
| Sub Total Fishery |  |  | 486.67 | 438 |  |  | 130 | 130 | 0 |  | 107.13 | 107.13 | 22.87 | 0 | 48.67 |  | 0 | 0 | 0
[10 empty] | 0 |  |  |  |  | 0
[10 empty] | 0 |  |  |  |  | 0
[10 empty] | 0 |  |  |  |  | 0
[10 empty] | 0 |  |  |  |  | 0
[10 empty] | 0 |  |  |  |  | 0
[10 empty] | 0 |  |  |  |  | 0
[10 empty] | 0 |  |  |  |  | 0
| During 12th Plan | [8 empty] | 0
67 | Construction of Titlagarh Sports Complex, Sonari,Sibsagar | SPORTS & YOUTH WELFARE | 25/4/2012 | 272 | 244.8 | 31-3-2018 | 25/4/2012 29-2-2016 | 100 | 100 | 0 |  | 100 | 85 | 15 | 15 | 27.2 |  | 11.11 | 11.11 |  | 34% | UC is awaited from Deptt. of Rs.15.00 lakh
68 | Construction of Mini Stadium at Bihaguri, Sonitpur | SPORTS & YOUTH WELFARE | 2014-03-03 | 431.81 | 388.63 |  | 2014-03-03 | 155.45 | 155.45 | 0 |  | 155.45 | 0 | 155.45 | 155.45 | 43.18 |  |  |  |  | 35% | UC is awaited from Deptt. and requested to submit early.
69 | Modernisation of Assam Flying Club | SPORTS & YOUTH WELFARE | 2006-02-06 | 11.55 | 10.05 |  | 2/6/2006 and 27/3/2008 | 10.4 | 10.395 | 0.005 |  | 10.395 | 6.3 | 4.1 | 4.095 | 1.16 |  | 0.46 |  |  |  | Under Court Case. Deptt. is requested to take action.
70 | Development of Composite sports stadium complex at Silchar DSA Ground. | SPORTS & YOUTH WELFARE | 25/10/2002 revised 17/3/2004 | 353 | 317.7 |  |  | 247.8 | 243 | 4.8 |  | 243 | 243 | 4.8 | 0 | 35.3 |  | 14.8 | 14.8 |  |  | Deptt. to submit UC against state share.
| Sub Total Sports & YW |  |  | 1068.36 | 961.18 |  |  | 513.65 | 508.845 | 4.805 |  | 508.845 | 334.3 | 179.35 | 174.545 | 106.84 |  | 26.37 | 25.91 | 0
71 | Setting up of Common Facility Center for Gold and Assamese Traditional Jewellery, Assam. | Industries and Commerce | 20/2/2017 | 593.23 | 533.907 |  |  | 179.9 |  | 179.9 |  |  |  |  | 0 | 59.323
| Sub Total Industries and Commerce |  |  | 593.23 | 533.907 |  |  | 179.9 | 0 | 179.9 |  | 0 | 0 | 0 | 0 | 59.323 |  | 0 | 0 | 0
| Grand Total |  |  | 67787.65 | 61035.777 |  |  | 46431.568 | 42651.5433 | 3780.0247 |  | 42027.7524 | 39439.5991 | 6991.9689 | 2588.1533 | 6737.533 | 140.73 | 3378.506 | 3292.1476 | 3153.6458

## Sheet2 (hidden)
STATUS OF NEC FUNDED ONGOIN PROJECTS/SCHEMES THROUGH PRIORITY LIST
(Rs. in Lakh)
Sl. No. | Name of the Project | Department | Name of projects | Estimated Cost of the Project | Target Date of Completion | Fund released by NEC |  | Amount recommended by P & D | Fund released by FD |  | UC submitted | UC pending on NEC share |  |  |  | Physical Progress | Remark
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Prior to 11th Plan
1 | Construction of double lane R.C.C. Bridge & approaches over river Barak at Fuler tal in Assam. | PWD | 11.09.2012(NEC share 1734.30) | 1927 |  | 2004-05 to 2013-14 | 1706.1 | 1706.1 | 2006-07 to 2013-14 | 1706.1 | 1691.61 | 192.7 |  | 189.57 | 189.57 | 100%
2 | Bhanga-Anipur-Kanaibazar Road | PWD | 4.02.2005(NEC share 7814.89) | 8649.88 |  | 2003-04 to 2009-10 | 7670 | 7432.3 | 2004-05 to 2013-14 | 7432.3 | 7432.3 | 834.99 |  | 834.99 | 834.99 | 100%
3 | Upgradation / Improvement of Rymbai Betwa Borsora Jallalpur Road | P.W.D | 26.12.05 (NEC Share =2099.27) | 2332.52 | March, 2009 (O) March, 2013 (R) | 18/03/2008 | 400 | 1800 | 2007-08 to 2012-13 | 1800 | 1800 | 233.3 |  | 132.48 | 132.48 | 88% | The scope of work is 14.8 km along with 5 Nos. of RCC Bridges. Out of which 12.00 km was completed. The balance 2.8km could not complete due to boundary dispute between Assam and Meghalaya.
[6 empty] | 20/03/2009 | 500
[6 empty] | 29/10/2009 | 400
[6 empty] | 2010-04-06 | 400
[6 empty] | 2012-09-07 | 100
[6 empty] | Total | 1800
During 11th Plan
4 | Mairang-Ranigodown-Azara Road | PWD | 22.12.2010 (NEC share 224.60) | 2494 |  | 2009-10 to 2011-12 | 1985 | 1985 | 2010-11 to 2013-14 | 1985 | 1935.45 | 249.4 |  | 249.4 | 249.4 | 100%
5 | Improvement of Jowai Natrang Khanduli Baithalangso Road | P.W.D | 23.02.11 NEC Share 6390.00 | 7100 | March, 2011 | 27/05/2011 | 1050 | 3610.87 | 2011-12 to 2012-13 | 3610.87 | 3193.36 | 710 |  | 105 | 105 | 68% | Out of 3 packages: Pkg. No. 1: Work is completed. Pkg. No. 2: 39% work done. Pkg. No. 3: 46% work done. Balance work is in progress .QPR received upto December,2016.
[6 empty] | 18/10/2012 | 1500
[6 empty] | 2013-07-08 | 2000
[6 empty] | Total | 4550
6 | Improvement & Widening from one half lane to double lane of Silchar - Kalain Road connecting to NH-44 at Kalain | P.W.D | 18.02.10 NEC Share 5332.50 | 5925 | March, 2010 (O) March, 2013 (R) | 18/02/2010 | 1200 | 5170.9 | 2009-10 to 2014-15 | 5170.9 | 4975.81 | 592.5 |  | 592.5 | 592.5 | 100% | Work is completed . Completion Certificate not submitted.
[6 empty] | 25/04/2012 | 2000
[6 empty] | 24/09/2013 | 1000
[6 empty] | 16/12/2014 | 1100
[6 empty] | Total | 5300
7 | Construction of Bhawnipur NH-31 to Manas National Park via Saudarvitha Ananda Bazar Road in Assam | P.W.D | 19.02.13NEC Share 5254.20 | 5838 | 2016-07-12 | 2013-14 | 1000 | 3800 | 2013-14 to 2015-16 | 3799.9983 | 2953.07 | 583.8 |  | 302.16 | 302.16 | 81% | Stipulated date of completion is 7-12-2016 QPR received upto Deceber,2015 .
[6 empty] | 2014-15 | 2000
[6 empty] | 2015-16 | 800
[6 empty] | Total | 3800
During 12th Plan
8 | Improvement/Upgradation of Pakke-Seijosa-Itakhola Road | PWD | 02.06.2015 NEC Share 1238.00 | 1376 |  | 2015-02-06 | 500 | 204.01 | 2015-16 | 204.0091 | 0 | 138 |  | - | 0 | 37.31% | Scheme sanctioned by NEC during June ,2015 . FD released Rs18.36 lakh during 2015-16
1 | Sub Total PWD | PWD | 8 | 35642.4 |  |  | 27311.1 | 25709.18 |  | 25709.1774 | 23981.6 | 3534.69 |  | 2406.1 | 3329.5
Prior to 11th Plan
| Preparation of project profile for Tourism infrastructure development in BTC. | *WPT & BC |  | 250 | 3 years from the date of approval | 29/8/2006 | 180 | 90 |  | 90 | 90 | 20 |  | 0 |  | 50% | Deptt. may be requested to release remaining amount of NEC's G/S along-with S/S and to submit U.C. for both G/S & S/S.
During 12th Plan
| Pineapple cultivation at Athiabari, Kokrajhar | *WPT & BC |  | 210.37 | 3 years from the date of approval | 2012-03-12 | 70 | 70 | 2014-15 | 43.1 |  | 21.04 |  | 0 |  | 21.52% | UC is awaited. Deptt. is requested to move for release of State Share and to submit UC.
| Horticulture and Floriculture in BTAD area | *WPT & BC |  | 362.87 | 3 years from the date of approval | 2012-03-12 | 120 | 120 | 2013-14 | 120 |  | 36.29 |  | 0 |  | 65% | 2nd installment is awaited from NEC
| Development of the Socio-Economic Status of Rural Tribal Women at Sidli Dev. Block of Kajalgaon Sub-Division, Chirang | *WPT & BC |  | 466.76 | 3 years from the date of approval | 2014-04-03 | 100 | 100 |  | 100 | 100 | 46.66 |  | 0 |  | 53% | 2nd installment is awaited from NEC
| Construction of Market Shed at Salbari bazar at Mushalpur | *WPT & BC |  | 187.55 | 3 years from the date of approval | 2014-04-03 | 50.64 | 50.64 |  | 15.29 | 15.19 | 18.75 |  | 0 |  | 39% | UC of remaining grant share is awaited. Deptt. is requested to move for release of State Share and to submit UC.
| Construction of Fish Farm at Bherabari, part-I, Assam | *WPT & BC |  | 449.85 | 3 years from the date of approval | 28-01-2013 | 130 | 130 | 2014-15 | 65 |  | 44.99 |  | 0 |  | 53% | Entire grant share is awaited. Deptt. is requested to move for release of State Share and to submit UC.
| Construction of Saviour Orphan Children Home at Gossaigaon, Kokrajhar | *WPT & BC |  | 294.33 |  | 2014-05-03 | 141 | 106 |  | 30 | 0 | 29.43 |  |  |  | 65% | Deptt. is requested to submit UC. QPR etc. Deptt. is requested to move for release of State Share and to submit UC..
2 | Sub Total WPT & BC | WPT & BC | 7 | 2221.73 |  |  | 791.64 | 666.64 |  | 463.39 | 205.19 | 217.16 |  | 0 | 586.45
| During 12th Plan | [13 empty] | 0
| Estt. Of Deori Tribel Cultural Complex at Narayanpur, Lakhimpur | CULTURAL AFFAIRS |  | 497 | March'2017 | 2012-02-04 | 120 | 120 | 2014-15 | 120 | 85.03 | 49.7 |  | 0 | 34.97 | 50% | Deptt. has already utilised Rs 85.03 lakh against NEC,s released amount of Rs120 lakh.
| Tai Education & Cultural Centre at Niz-Kadamoni, Dibrugarh | CULTURAL AFFAIRS |  | 333.49 | 3 years from the date of approval | 25/2/2014 | 120 |  |  | 0 | 0 | 33.35 |  | 0 | 120 | 10% | A/A accorded for Rs. 333.49 lakh and financial sanction of Rs.120.00 lakh was approved by P & D deptt. on 18th Nov. 2014
3 | Sub -Total Cultural Affairs | Cultural Affairs | 2 | 830.49 |  |  | 240 | 120 |  | 120 | 85.03 | 83.05 |  | 0 | 154.97
| Construction of Regional Multi-Utility Town hall and Cultural Centre in Tinsukia | URBAN DEVELOPMENT |  | 798 | Dec'2017 | 28-02-2014 | 287.28 |  |  | 86.18 |  | 79.8 |  |  | 287.28 | 40% | Work not yet started
4 | Sub Total Urban Development | Urban Development | 1 | 798 |  |  | 287.28 | 86.18 |  | 86.18 | 0 | 79.8 |  | 0 | 287.28
| During 11th Plan | [13 empty] | 0
| Construction of 132/33 KV,1.16 MVA Umrangshu Dima Hassao (N.C. Hills) Dist., Assam | POWER |  | 1344 | June'2013(O) Sept'2016( R) |  |  | 550 | 2013-14 | 537 | 537 | 134.4 | 59.67 | 0 | -537 | 95% | UC of Rs.550.00 lakh is awaited along with Rs.59.67 lakh of state share.
[6 empty] | 2011-03-01 | 537 | [7 empty] | 537
[6 empty] | 21/11/2013 | 550 | [7 empty] | 550
[6 empty] | Total | 1087 | [7 empty] | 1087
| Lugnit small H.E. project in Karbi Anglong | POWER |  | 500 | March, 2012 (O) March, 2015 (R ) | 25/3/2008 | 150 | 150 |  | 150 | 150 | 50 |  | 0 | 0 | 17% | 17% work completed. The project was taken over by APGCL on 28/01/2013. Re tendering and evaluation terget have been completed. Fund awaited from NEC.
| Amring small H.E. project in Karbi Anglong. | POWER |  | 211 | Work completed in all respects in 30/09/2014 | 25/11/2008 | 40 | 89.0719 |  | 40 | 40 | 21.1 |  | 0 | 0 |  | UC of 2nd instalment of is awaited. No S/S is released so far. Deptt. intimated that no further fund is required from NEC. Deptt is request to close the project.
[10 empty] | 15 |  |  |  |  | 0
[6 empty] | 2014-04-06 | 50 | [7 empty] | 50 | 100%
[6 empty] | Total | 90 |  |  | 55 |  |  |  |  | 90
| During 12th Plan | [13 empty] | 0
| Augmentation of transformer capacity of 220X132 kv BTPS Sub-Station from 1x160MVA+IX80MVA to 2x160 | POWER |  | 678 |  | 20/5/2016 | 240 |  |  |  |  | 67.8 |  |  | 240 |  | New scheme
| Construction of 33/11kv,2x5MVA Sub-Station alongwith associated 33kv,11kv &LT Feeders at Bishnupur Panch ali under Dhemaji Electrical Division APDCL, Dhemaji. | POWER |  | 1025 |  | 20/5/2016 | 370 |  |  |  |  | 102.5 |  |  | 370 |  | New scheme
| Augmentation of transformer capacity of 132/33 Biswanath Chariali (Pavoi) Sub-Station from2x16MVA to 2x40 MVA | POWER |  | 709 |  | 20/5/2016 | 260 |  |  |  |  | 70.9 |  |  | 260 |  | New scheme
5 | Sub Total Power | Power | 6 | 4467 |  |  | 2197 | 789.0719 |  | 742 | 727 | 446.7 |  | 0 | 1470
| During 12th Plan | [13 empty] | 0
| Financial support for students of NER | EDUCATION |  | 237.81 | continuing process | 13/07/2015 | 222.06 |  |  |  | 0 |  |  |  | 222.06 |  | Higher Education Deptt. never approched from P & D Deptt. recommendation.
| Construction of RCC(G+2) building for Seminar Hall,Computer Centre and facilitates for car parking at Darrang College, Tezpur,Assam. | EDUCATION |  | 229.55 | Dec,2016 | 21/11/2012 | 82.64 | 82.64 |  | 82.64 | 82.64 | 22.96 | 9.18 |  | 0 | 50% | fund awaited from NEC. UC of state shatre is awaited.
| Infra-structure Development of Bagnibar Nilamoni Phukan H.S. School, Dibrugarh, Victoria Girl's H.S. School and A.R.T. High School at Margherita, Assam. | EDUCATION |  | 400 | June, 2016 | 18-02-2013 | 120 | 120 |  | 116.74 |  | 40 |  |  | 120 | Bagnibar - 76% Victoria - 73% A.R.T. - 43% | UC of balanced amount is awaited. Resease of state share is awaited.
| Construction of Auditorium Hall at Chamata Higher Secondary School, Nalbari | EDUCATION |  | 205 | March, 2017 | 18/12/14 | 73.8 |  |  |  |  | 20.5 |  |  | 73.8 | 30% | A/A recommended by P & D on 03.10.2015.
| Construction of Chandranath Sarmah Higher Secondary School, at Bihaguri, sonitpur | EDUCATION |  | 318.3 | March, 2018 | 5/3/15 | 62.24 |  |  |  |  | 31.83 |  |  | 62.24 |  | A/A recommended by P & D on 03.10.2015.
| Const./Re-modeling of RCC building including development of Library,Vocational Centre etc of Madhab Dev Higher Secondary School at Tulsimukh, Nagaon | EDUCATION |  | 318.88 |  | 20/5/16 | 115 |  |  |  |  | 31.88 |  |  | 115 |  | New project
6 | Sub Total Education | Education | 6 | 1709.54 |  |  | 675.74 | 202.64 |  | 199.38 | 82.64 | 147.17 |  | 0 | 593.1
| Construction of Home for Cancer Affected Children by Dipshikha, Guwahati | SOCIAL WELFARE |  | 389.68 |  | 2014-03-03 | 140.28 | 320.28 |  | 140.28 | 140.28 | 38.97 |  |  | 0 | 55% | UC of Rs.180.00 lakh is awaited requested to release of state share.
0
[6 empty] | 22/3/2016 | 180 | [7 empty] | 180
[6 empty] | Total | 320.28 | [7 empty] | 320.28
7 | Sub Total Social Welfare | Social Welfare | 1 | 389.68 |  |  | 320.28 | 320.28 |  | 140.28 | 140.28 | 38.97 |  | 0 | 180
| During 12th Plan | [13 empty] | 0
| Organisation of International Conference on Look (Act) East Policy and North East India on 25th and 26th Sept. 2015 at Guwahati. | OKD and P&D |  | 5 |  |  | 4 | 2 |  |  |  | 0.5 |  |  | 4 |  | UC is awaited
8 | Sub Total OKD & P&D | OKD & P&D | 1 | 5 |  |  | 4 | 2 |  | 0 | 0 | 0.5 |  | 0 | 4
| During 11th Plan | [13 empty] | 0
| Bio-diversity conservation Bashistha Bahini conservation watershed | SOIL CONSERVATION |  | 496.76 | 25/8/2012 | 25/08/2009 | 40 | 320 |  | 303.732 | 140 | 49.68 | 32 | 32 | -100 | 68% | Clarification of UC of 2nd installment is sought from the Deptt. UC of S/S is awaited.
0
[6 empty] | 14/03/2011 | 100 | [7 empty] | 100
[6 empty] | 2013-03-11 | 180 | [7 empty] | 180
[6 empty] | Total | 320 | [7 empty] | 320
9 | Sub Total Soil Conservation | Soil Conservation | 1 | 496.76 |  |  | 320 | 320 |  | 303.732 | 140 | 49.68 |  | 32 | 180
| Priot to 11th Plan | [13 empty] | 0
| Yatri Niwas, Paltanbazar | TRANSPORT : |  | 1124.47 | Project is already completed. | 25/07/2005 | 90 | 990 | 2005-06 to 2008-09 | 990 | 990 | 112.45 | 94.21 | 94.21 | -900 | 100% | Project is already completed. NEC informed that Deptt. had not handed over the space to NEC as per MOU. Reply is awaited.
0
[6 empty] | 28/03/2007 | 300 | [7 empty] | 300
[6 empty] | 13/03/2008 | 500 | [7 empty] | 500
[6 empty] | 30/03/2009 | 100 | [7 empty] | 100
[6 empty] | Total | 990 | [7 empty] | 990
10 | Sub Total Transport | Transport | 1 | 1124.47 |  |  | 990 | 990 |  | 990 | 990 | 112.45 |  | 94.21 | 0
| Priot to 11th Plan | [13 empty] | 0
| Controlling of jiadhal river in Dhemaji Dist. Ph-I | Water Resources |  | 1493.57 | Completed | 27/02/2006 | 547 | 945.61 |  | 945.61 | 945.61 | 149.36 | 143.38 | 143.38 | -398.61 | 100% | UC submitted vide letter no. PD/NEC/33/2005/pt/285 dtd 4/5/2006. Remaining fund awaited from NEC
[6 empty] | 30/12/2013 | 398.61 | [7 empty] | 398.61
[6 empty] | Total | 945.61 | [7 empty] | 945.61
0
| During 11th Plan | [13 empty] | 0
| Protection of Raimona village and its adjoining area from erosion of river Janali river in Kokrajhar Dist., Assam | Water Resources |  | 374 | Completed | 2011-01-02 | 120 | 254.64 |  | 254.64 | 254.64 | 37.4 | 28.29 | 28.29 | -134.64 | 100% | UC submitted vide letter no. PD/NEC/33/2005/pt/285 dtd 4/5/2006. Remaining fund awaited from NEC
0
[6 empty] | 14/8/2012 | 134.64 | [7 empty] | 134.64
[6 empty] | Total | 254.64 | [7 empty] | 254.64
| Anti erosion measures to protect Ranipur and its adjoining areas from the erosion of river Pekua. | Water Resources |  | 343.39 | Completed | 23/3/2012 | 100 | 223 |  | 223 | 223 | 34.34 | 11.11 | 11.11 | -123 | 100% | UC submitted vide letter no. PD/NEC/33/2005/pt/285 dtd 4/5/2006. Remaining fund awaited from NEC
0
[6 empty] | 2014-12-02 | 123 | [7 empty] | 123
[6 empty] | Total | 223 | [7 empty] | 223
| Anti erosion measures at different reaches on both bank of river Pomra | Water Resources |  | 227.94 | March, 2017 | 4/6/2014 Rs.82.06 03/06/16 Rs.82.00 | 164.06 | 82.06 |  | 82.06 | 82.06 | 22.79 | 9.18 |  | 82 | 68%
11 | Sub Total Water Resource | Water Resource | 4 | 2438.9 |  |  | 1587.31 | 1505.31 |  | 1505.31 | 1505.31 | 243.89 |  | 182.78 | 82
| During 11th Plan | [13 empty] | 0
| Dhankhunda FIS Kamrup | IRRIGATION |  | 485 | Completed | 22/9/2010 | 145.5 | 436.5 |  | 392.85 | 392.85 | 48.5 | 48.5 | 44.14 | -247.35 | 100% | UC of last installment is awaited.
0
[6 empty] | 22/8/2012 | 174.6 | [7 empty] | 174.6
[6 empty] | 2014-03-06 | 72.75 | [7 empty] | 72.75
[6 empty] | 24/11/2015 | 43.65 | [7 empty] | 43.65
[6 empty] | Total | 436.5 | [7 empty] | 436.5
| Modernisation and Extension of Longparpam MIS, Karbi- Anglong District | IRRIGATION |  | 213 | Completed in March 2013 | 22/9/2010 | 64 | 140.68 |  | 140.68 | 140.68 | 21.3 | 15.63 | 15.63 | -76.68 | Completed in March 2013 | project completed. Subsequent installment is awaited from NEC.
[6 empty] | 2012-07-08 | 76.68 | [7 empty] | 76.68
[6 empty] | Total | 140.68 | [7 empty] | 140.68
0
0
0
| Construction of Gilabwr-FIS | IRRIGATION |  | 418 | Completed | 23/3/2012 | 100 | 325.48 |  | 325.48 | 250 | 41.8 | 27.83 | 27.83 | -150 | 100% | UC is awaited.
0
[6 empty] | 25/04/2014 | 150.48 | [7 empty] | 150.48
[6 empty] | 2015-16 | 75 | [7 empty] | 75
[6 empty] | Total | 325.48 | [7 empty] | 325.48
0
| During 12th Plan | [13 empty] | 0
| Ram Englee Minor Irrigation scheme in Karbi-Anglong Dist. Assam | IRRIGATION |  | 494.7 | 25/3/2015 | 25/3/2013 | 140 | 318 |  | 140 | 140 | 49.47 | 15.55 | 15.55 | 0 | 100% | UC f is awaited.
0
[6 empty] | 2015-05-01 | 178 | [7 empty] | 178
[6 empty] | Total | 318 | [7 empty] | 318
12 | Sub Total Irrigation | Irrigation | 4 | 1610.7 |  |  | 1220.66 | 1220.66 |  | 999.01 | 923.53 | 161.07 |  | 103.15 | 297.13
| During 11th Plan | [13 empty] | 0
| Estt. Of Cold Storage at Jorhat | AGRICULTURE |  | 490.65 | October,2012 (O) 01/10/2016 (R ) | 21/10/2010 | 176.63 | 254.08 |  | 147 | 298.63 | 49.07 | 28.23 |  | -122 | 98% | Expenditure of excess amount from their own sources
0
[6 empty] | 2015-16 | 77.45 | [7 empty] | 77.45
[6 empty] | Total | 254.08 | [7 empty] | 254.08
| During 12th Plan | [13 empty] | 0
| Development of Fruits & Vegetable Market at Pamohi (Garchuk),Kamrup, Phase-III | AGRICULTURE |  | 1401.28 |  | 20/5/2016 | 100 |  |  |  |  | 140.13 |  |  | 100 |  | New project
13 | Sub Total Agriculture | Agriculture | 2 | 1891.93 |  |  | 354.08 | 254.08 |  | 147 | 298.63 | 189.2 |  | 0 | 55.45
| During 12th Plan | [13 empty] | 0
| Promotion of an Environmentally Sound Approach for Sustainable Water Management Optimizing Usage Rain Water Harvesting for Roof Tops in Institutions, Health centres & Community Centre. | PHE |  | 1248 |  | 1/12/205 | 162.168 | 162.168 |  |  |  | 12.48 |  |  | 162.168 |  | A. A is awaited.
14 | Sub Total PHE | PHE | 1 | 1248 |  |  | 162.168 | 162.168 |  | 0 | 0 | 12.48 |  | 0 | 162.168
| During 11th Plan | [13 empty] | 0
| Assam Polyster Cooperative Society Ltd. For Upgradation/Replacement of machineries of its spinning unit located atTulsibari, Rangia, Assam | CO-OPERATION |  | 457.34 | 2 years from the date of approval | 22/11/2011 | 164.64 | 329.28 |  | 329.28 | 164.64 | 45.74 | 36.58 | 36.58 | 0 | 50% | UC is awaited
0
[6 empty] | 20/11/2013 | 164.64 | [7 empty] | 164.64
[6 empty] | Total | 329.28 | [7 empty] | 329.28
15 | Sub Total Co-operation | Co-operation | 1 | 457.34 |  |  | 329.28 | 329.28 |  | 329.28 | 164.64 | 45.74 |  | 36.58 | 164.64
| During 11th Plan | [13 empty] | 0
| Publicity and Promotion of Tourism products of Assam with an innovative approach integrating advertisement through print and electronic media, outdoor media, organization of events and facelift of few tourist destinations | TOURISM |  | 245.31 | 31/3/2012 | 28/3/2011 | 188.31 | 188.31 |  | 89.16 |  | 24.53 |  |  | 188.31 | 100% | UC of entire grant share is awaited. Deptt is requested to release of state share and to submit UC
| During 12th Plan | [13 empty] | 0
| Tea Museum at Dibrugarh | TOURISM |  | 314.41 |  | 2014-05-03 | 113.19 |  |  |  |  | 31.44 |  |  | 113.19 |  | AA accorded.
| Destination North East - 2016 to be held on 12 -14 Feb. 2016 at Pragati Maidan, New Delhi. | TOURISM |  | 10 |  | 15/2/12016 | 8 |  |  |  |  | 1 |  |  | 8
16 | Sub Total Tourism | Tourism | 3 | 569.72 |  |  | 309.5 | 188.31 |  | 89.16 | 0 | 56.97 |  | 0 | 309.5
| During 11th Plan | [13 empty] | 0
| Eco-Tourism cum Botanical Garden and Orchid Culture at Jokai, Dibrugarh Assam. | ENVIRONMENT & FOREST |  | 264.57 | 22/3/2011 | 2010-03-22 | 71.43 | 71.43 |  |  |  | 26.46 |  |  | 71.43 |  | NEC approved Revised DPR recently. Deptt. is requested to release fund at the earliest.
17 | Sub Total Forest | Forest | 1 | 264.57 |  |  | 71.43 | 71.43 |  | 0 | 0 | 26.46 |  | 0 | 71.43
| During 12th Plan | [13 empty] | 0
| Setting up of a Handloom Trade Centre at Dibrugarh, Assam | HANDLOOM & TEXTILE |  | 991.7 | 28-2-2017 | 26/3/2013 | 49.57 | 49.57 |  |  | 0 | 99.17 | 99.17 | 4.95 | 49.57 | 10% | AA accorded.
| Economic Upliftment through Innovative value added handloom Weaving in Jorhat, Golaghat and Lakhimpur District, Assam | HANDLOOM & TEXTILE |  | 415.54 | 2016-04-03 | 2014-04-03 | 149.59 | 149.59 |  | 90 | 0 | 41.56 | 41.56 |  | 149.59 | 20% | UC is awaited.
18 | Sub Total Handloom & Textile | Handloom & Textile | 2 | 1407.24 |  |  | 199.16 | 199.16 |  | 90 | 0 | 140.73 | 140.73 | 4.95 | 199.16
| During 12th Plan | [13 empty] | 0
| Employable Skill Development ,Assam | SERICULTURE |  | 383.53 |  | 15/3/2014 | 69 | 69 |  | 69 | 69 | 38.35 |  |  | 0 | 100% | 2nd installment is awaited from NEC.
| Up-gradation of Serculture Training Institute at Titabor, Jorhat | SERICULTURE |  | 1281.81 |  | 18/12/2014 | 283.62 | 283.62 |  | 190.09 | 0 | 128.18 |  |  | 283.62 | 30% against total estimated cost | UC is awaited.
19 | Sub Total Sericulture | Sericulture | 2 | 1665.34 |  |  | 352.62 | 352.62 |  | 259.09 | 69 | 166.53 |  | 0 | 283.62
| Beel Dev. For sustainable Livelihood in Dibrugarh, Golaghat, Nagaon and Darrang Districts of Assam | FISHERY |  | 486.67 | 31-3-2016 | 6-3-2013 | 130 | 130 |  | 107.13 |  | 48.67 |  |  | 130 | Dibrugarh-38% Golaghat- 7% Nagaon - 35% Darrang - 81% | Deptt is requested to resubmit UC of Rs.107.13 lakh as directed. Alternative DPRs for shifting of project side to be submitted to NEC for approval.
20 | Sub Total Fishery | Fishery | 1 | 486.67 |  |  | 130 | 130 |  | 107.13 | 0 | 48.67 |  | 0 | 130
| Prior to 11th Plan | [13 empty] | 0
| Dev. Of Composit Stadium at Silchar | SPORTS & YOUTH WELFARE |  | 353 | completed | 25/1/2002 | 52.8 | 243 |  | 243 | 243 | 35.3 |  | 14.8 | -190.2 | 100% | UC and CC are awaited
0
[6 empty] | 2004-06-01 | 55 | [7 empty] | 55
[6 empty] | 15/5/2006 | 50 | [7 empty] | 50
[6 empty] | 29/1/2008 | 90 | [7 empty] | 90
[6 empty] | Total | 247.8 | [7 empty] | 247.8
| During 12th Plan | [13 empty] | 0
| Construction of Titlagarh Sports Complex, Sonari,Sibsagar | SPORTS & YOUTH WELFARE |  | 272 | 31-3-2018 | 25/4/2012 29-2-2016 | 100 | 100 |  | 100 | 100 | 27.2 |  | 11.11 | 0 | 35% | UC is awaited.
| Construction of Mini Stadium at Bihaguri, Sonitpur | SPORTS & YOUTH WELFARE |  | 431.81 |  | 2014-03-03 | 155.45 |  |  |  | 0 | 43.18 |  |  | 155.45 | 10% | AA accorded.
| Modernisation of Assam Flying Club | SPORTS & YOUTH WELFARE |  | 11.55 |  | 2/6/2006 27/3/2008 | 6.3 | 6.3 |  | 6.3 | 6.3 | 1.15 |  |  | 0
21 | Sub Total Sports & YW | Sports & YW | 4 | 1068.36 |  |  | 509.55 | 386.2 |  | 349.3 | 349.3 | 106.83 |  | 25.91 | 160.25
| Support to Devlt..of Addl. Facilities for Specialisation and Super-Speciality in three Medical Colleges in Assam | [13 empty] | 0
| Prior to 11th Plan | [13 empty] | 0 |  | surrendered Rs79.64 lakh against 10th plan scheme by PWD building
| a) G.M.C, Guwahati (Capital) | HEALTH & FAMILY WELFARE |  | 728.85 | 31/3/2010 |  |  | 694.71 | [6 empty] | 0
| Capital |  |  |  |  | 17/3/2003 | 27.71 |  |  | 694.71 | 694.71 | 72.88 |  | 34.48 | -667 | 95% | Deptt. is requested to submit for Audit Certificate and also move for release of State share and also submit the UC of remaining amount of NEC release. QPR not received. If fund not required, Deptt. may surrender fund and give C/C.
[6 empty] | 24/4/2003 | 29.7 | [7 empty] | 29.7
[6 empty] | 27/08/2003 | 70.53 | [7 empty] | 70.53
[6 empty] | 13/2/2004 | 10.79 | [7 empty] | 10.79
[6 empty] | 31/3/2004 | 1.2 | [7 empty] | 1.2
[6 empty] | 31/3/2004 | 14.78 | [7 empty] | 14.78
[6 empty] | 2005-09-09 | 315 | [7 empty] | 315
[6 empty] | 28/3/2007 | 225 | [7 empty] | 225
[6 empty] | Total | 694.71 | [7 empty] | 694.71
| Revenue |  |  | 506.5 |  |  |  | 406.64 |  | 406.64 | 353.17 | 50.65 |  | 26.24 | -353.17
[6 empty] | 2003-04-03 | 178.66 | [7 empty] | 178.66
[6 empty] | 21/6/2004 | 57.6 | [7 empty] | 57.6
[6 empty] | 19/3/2009 | 183.77 | [7 empty] | 183.77
[6 empty] | Total | 420.03 | [7 empty] | 420.03
| b) A.M.C, Dibrugarh | HEALTH & FAMILY WELFARE |  | 300.87 | 31/3/2012 | 15/3/2005 | 90 | 270.78 |  | 270.78 | 270.78 | 30.09 |  | 12.47 | -180.78 | 95% | Deptt. is requested to submit A.G. Audit Certificate and also move for release of remaining state share and also submit the UC of remaining amount of NEC release . QPR not received. If fund not required, Deptt. may surrender fund and give C/C.
| Capital | [13 empty] | 0
0
[6 empty] | 2008-11-03 | 100 | [7 empty] | 100
[6 empty] | 2009-07-09 | 80.78 | [7 empty] | 80.78
[6 empty] | Total | 270.78 | [7 empty] | 270.78
| Revenue |  |  | 522.1 |  |  |  | 225.26 |  | 225.26 | 221.73 | 52.21 |  | 0 | -221.73
[6 empty] | 15/3/2005 | 165.15 | [7 empty] | 165.15
[6 empty] | 23/2/2011 | 60.11 | [7 empty] | 60.11
[6 empty] | Total | 225.26 | [7 empty] | 225.26
| c) S.M.C, Silchar | HEALTH & FAMILY WELFARE |  | 682.9 | 31/3/2012 |  |  | 614.61 |  | 614.61 | 614.57 | 68.29 |  |  | -614.57 | 95% | Deptt. is requested to submit AG Audit Certificate and also move for release of state share and also submit the UC of remaining amount of NEC share. QPR not received. If fund not required, Deptt. may surrender fund and give C/C.
| Capital | [13 empty] | 0
[6 empty] | 23/3/2004 | 45 | [7 empty] | 45
[6 empty] | 2004-08-09 | 180 | [7 empty] | 180
[6 empty] | 2005-09-09 | 180 | [7 empty] | 180
[6 empty] | 16/10/2009 | 119.22 | [7 empty] | 119.22
[6 empty] | 2011-08-02 | 90.39 | [7 empty] | 90.39
[6 empty] | Total | 614.61 | [7 empty] | 614.61
| Revenue |  |  | 714.19 |  |  |  | 593.15 |  | 593.15 | 593.15 | 71.42 |  | 25.62 | -593.15
[6 empty] | 2005-09-09 | 137.7 | [7 empty] | 137.7
[6 empty] | 24/3/2009 | 225 | [7 empty] | 225
[6 empty] | 2011-08-02 | 49.5 | [7 empty] | 49.5
[6 empty] | 16/10/2009 | 230.57 | [7 empty] | 230.57
[6 empty] | Total | 642.77 | [7 empty] | 642.77
| Regional Dental College, Guwahati. | HEALTH & FAMILY WELFARE |  | 436.95 | 31/3/2012 |  |  | 393.26 |  | 393.26 | 393.26 | 43.7 |  | 0.14 | -393.26 | 95% | Deptt. is requested submit for Audit Certificate and also to move for release of NEC share & coresponding State share also submit the UC of remaining amount of NEC release . QPR not received
| Capital | [13 empty] | 0
[6 empty] | 16/3/2005 | 90 | [7 empty] | 90
[6 empty] | 28/3/2007 | 80 | [7 empty] | 80
[6 empty] | 13/9/2007 | 62.58 | [7 empty] | 62.58
[6 empty] | 18/3/2008 | 76.84 | [7 empty] | 76.84
[6 empty] | 23/11/2009 | 83.84 | [7 empty] | 83.84
[6 empty] | Total | 393.26 | [7 empty] | 393.26
| Revenue |  |  | 873.99 |  |  |  | 325 |  | 325 | 325 | 87.4 |  | 15 | -325
[6 empty] | 16/3/2005 | 135 | [7 empty] | 135
[6 empty] | 23/6/2008 | 90 | [7 empty] | 90
[6 empty] | 25/1/2011 | 100 | [7 empty] | 100
[6 empty] | Total | 325 | [7 empty] | 325
| Regional Nursing College, Guwahati. | HEALTH & FAMILY WELFARE |  | 437.31 | 31/3/2010 |  |  | 393.58 |  | 393.58 | 393.58 | 43.73 |  | 30.22 | -393.58 | 95% | Deptt. is requested submit for Audit Certificate and also to move for release of balance NEC share & coresponding state share and also submit UC of state share . QPR not received. If fund not required, Deptt. may surrender fund and give C/C.
| Capital | [13 empty] | 0
[6 empty] | 16/3/2005 | 99 | [7 empty] | 99
[6 empty] | 2007-03-09 | 135 | [7 empty] | 135
[6 empty] | 17/3/2008 | 90 | [7 empty] | 90
[6 empty] | 2009-12-11 | 69.58 | [7 empty] | 69.58
[6 empty] | Total | 393.58 | [7 empty] | 393.58
| Revenue |  |  | 135.83 |  |  |  | 119.84 |  | 119.84 | 115.86 | 13.58 |  | 4 | -115.86
[6 empty] | 16/3/2005 | 36 | [7 empty] | 36
[6 empty] | 2008-02-06 | 86.25 | [7 empty] | 86.25
[6 empty] | Total | 122.25 | [7 empty] | 122.25
| During 11th Plan | [13 empty] | 0
| Infrastructure Dev. of Academic facilities at Down Town College of allied Health Science at Panikheti | HEALTH & FAMILY WELFARE |  | 460 | 31/3/2012 | 21/3/2011 | 100.58 | 300..58 |  | 300.58 | 200 | 46 |  | 22.29 | -99.42 | 60% | P & D Deptt. approved sanction of Rs. 100.58 lakh under grant share and deptt. is requested to move for release of state share.MOA is yet to be signed.
0
[6 empty] | 2011-05-09 | 100 | [7 empty] | 100
[6 empty] | 2013-14 | 100 | [7 empty] | 100
[6 empty] | Total | 300.58 | [7 empty] | 300.58
| Estt. of Modern Burn Care Centre at Nemcare Hospital, Guwahati | HEALTH & FAMILY WELFARE |  | 300 |  | 26/02/09 | 90 | 270 |  | 270 | 190 | 30 |  | 30 | -100 |  | UC of Rs.80.00 lakh under grant share and UC of Rs.0.21 lakh under state share is awated.
[6 empty] | 31/01/11 | 100 | [7 empty] | 100
[6 empty] | 2012-05-01 | 80 | [7 empty] | 80
[6 empty] | Total | 270 | [7 empty] | 270
| Support to Govt. Ayurvedic College for constn. of Basic Science Building at GMCH, Ghy | HEALTH & FAMILY WELFARE |  | 398.09 |  | 14/12/2009 | 50 |  |  | 0 | 0 | 39.81 |  | 0 | 50 | Work not yet started | PWD express their inability to implement the project with the approved cost of Rs.398.09 lakh. As advised by NEC in the last review meeting of Health Sector revised DPR of RS.698.09 lakh was submitted.But NEC has advised to droped the project & adjustend the released amount of Rs.50.00 lakh in other Health peoject.In this regard Health Deptts view is awaited.
| Support to Govt. Hospitalship on the river Brahmaputra by centre for NE studies and Research | HEALTH & FAMILY WELFARE |  | 400 | 31/12/2012 | 31/11/2009 | 40 | 219.31 |  | 219.91 | 90 | 40 |  |  | -50 | 34% | Deptt. is requested to clarify NEC's observation after the scrutiny of DPR and other documents . . QPR not received
0
[6 empty] | 19/10/2012 | 200 | [7 empty] | 200
[6 empty] | Total | 240 | [7 empty] | 240
| Constn.of 100 Beded Hospital at Sonari | HEALTH & FAMILY WELFARE |  | 417.31 | 31/3/2012 | 2005-03-01 | 135 | 286.08 |  | 286.08 | 241.97 | 41.73 |  | 32.83 | -106.97 | 95% | Deptt. was requested for early completion of civil constn. & submit UC & Audit Certificate. QPR not received otherwise Deptt. may surrender.
0
[6 empty] | 22/7/2005 | 106.97 | [7 empty] | 106.97
[6 empty] | 2011-11-01 | 53.44 | [7 empty] | 53.44
[6 empty] | Total | 295.41 | [7 empty] | 295.41
| Constn. of Vertical Extn. of 1st floor (Part) 2nd & 3rd floors of MDS Building at RDC, Ghy | HEALTH & FAMILY WELFARE |  | 461.82 | 31/3/2015 |  |  | 269.59 |  | 269.59 | 265.59 | 46.18 |  | 32.42 | -265.59 | 100% | Further release of fund from NEC is awaited.
[6 empty] | 2012-03-09 | 130 | [7 empty] | 130
[6 empty] | 16/03/2015 | 161.82 | [7 empty] | 161.82
[6 empty] | Total | 291.82 | [7 empty] | 291.82
| Strengthing of Ortho Deptt. at GMC | HEALTH & FAMILY WELFARE |  | 1493.77 | 31/3/2015 | 26/11/2012 | 400 | 278.16 |  | 278.16 | 0 | 149.38 |  |  | 400 | 30% | Deptt. is yet to submit U.C of grant share. Deptt. may move for release of S/S
22 | Sub Total Health & FW | Health & FW | 12 | 9270.48 |  |  | 5950.06 | 5661.15 |  | 5661.15 | 4963.37 | 927.05 |  | 265.71 | 986.69
MH 3601 Grand Total |  |  | 71 | 70064.32 |  |  | 44312.858 | 39666.3599 |  | 38290.5694 | 34625.52 | 6835.79 | 140.73 | 3151.39 | 9687.338