## Sheet1
STATUS OF NEC FUNDED ONGOIN PROJECTS/SCHEMES (PRIORITY LIST)
(Rs. in Lakh)
Sl. No. | Name of the Project | Department | Date of Administrative Approval of the Project by NEC | Total Estimated Cost of the Project | NEC's Share Amount | Target Date of Completion | Instalment Released by NEC |  | Amount recommended by T & D | Deptt. yet to move for fund against NEC release | Amount released by FD |  | UC submitted | UC pending against the NEC release | UC pending against the FD release | State Share
[7 empty] | Date | Amount |  |  | Date | Amount |  |  |  | Total State Share | Amount recommended by P & D | State share recommended by T&D | State Share Released by FD | State Share UC Submitted
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 11 | 12 | 13 | 15 | 16 | 14 | 17 | 15 | 16 | 17
Prior to 11th Plan
1 | Construction of double lane R.C.C. Bridge & approaches over river Barak at Fulertal in Assam. | PWD | 11.09.2012 | 1927 | 1734.3 |  | 2004-05 to 2013-14 (Rs.1706.10 lakh) + 21-2-2017 (Rs.57.50 lakh) | 1763.6 | 1706.1 | 57.5 | 2006-07 to 2013-14 | 1706.1 | 1706.1 | 57.5 | 0 | 192.7 |  | 192.7 | 192.6 | 189.57
2 | Bhanga-Anipur-Kanaibazar Road | PWD | 18.08.2004 | 8649.88 | 7814.89 |  | 2003-04 to 2011-12 | 7670 | 7476.92 | 193.08 | 2004-05 to 2013-14 | 7476.92 | 7432.3 | 237.7 | 44.62 | 834.99 |  | 834.99 | 834.99 | 834.99
During 11th Plan
3 | Mairang-Ranigodown-Azara Road | PWD | 22.12.2010 | 2494 | 2244.6 |  | 2009-10 to 2011-12 | 1985 | 2244.6 | 0 | 2010-11 to 2013-14 | 2244.6 | 1985 | 259.6 | 259.6 | 249.4 |  | 249.4 | 249.4 | 249.4
[7 empty] | 2016-17 | 259.6 |  | 259.6 |  |  |  |  | 0
[7 empty] | Total | 2244.6 |  | 2244.6 |  |  |  |  | 0
4 | Improvement of Jowai Natrang Khanduli Baithalangso Road | P.W.D | 23.02.2011 | 7100 | 6390 | March, 2011 | 27/05/2011 | 1050 | 4180.0637 | 369.9363 | 2011-12 to 2012-13 | 4096.96 | 3588.968 | 961.032 | 507.992 | 710 |  | 105 | 105 | 105
[7 empty] | 18/10/2012 | 1500 |  | 1500 |  |  |  |  | 0
[7 empty] | 2013-07-08 | 2000 |  | 2000 |  |  |  |  | 0
[7 empty] | Total | 4550 |  | 4550 |  |  |  |  | 0
[10 empty] | 0 |  |  |  |  | 0
5 | Improvement & Widening from one half lane to double lane of Silchar - Kalain Road connecting to NH-44 at Kalain | P.W.D | 18.02.2010 | 5925 | 5332.5 | March, 2010 (O) March, 2013 (R) | 18/02/2010 | 1200 | 5214.56 | 85.44 | 2009-10 to 2014-15 | 5205.23 | 5104.9 | 195.1 | 100.33 | 592.5 |  | 592.5 | 592.5 | 592.5
[10 empty] | 0 |  |  |  |  | 0
[7 empty] | 25/04/2012 | 2000 |  | 2000 |  |  |  |  | 0
[7 empty] | 24/09/2013 | 1000 |  | 1000 |  |  |  |  | 0
[7 empty] | 16/12/2014 | 1100 |  | 1100 |  |  |  |  | 0
[7 empty] | Total | 5300 |  | 5300 |  |  |  |  | 0
6 | Construction of Bhawanipur NH-31 to Manas National Park via Saudarvitha Ananda Bazar Road in Assam | P.W.D | Rs.5838.00 lakh (original) 19.02.2013. Rs.5777.00 lakh (Revised) 6.02.2017 | 5777 | 5199.3 | 2016-07-12 | 2013-14 | 1000 | 4800 | 0 | 2013-14 to 2015-16 | 4799.9983 | 4799 | 1 | 0.99827 | 577.7 |  | 380 | 380 | 379.6238
[10 empty] | 0 |  |  |  |  | 0
[7 empty] | 2014-15 | 2000 |  | 2000 |  |  |  |  | 0
[7 empty] | 2015-16 | 800 |  | 800 |  |  |  |  | 0
[7 empty] | 2016-17 | 1000 |  | 1000 |  |  |  |  | 0
[7 empty] | Total | 4800 |  | 4800 |  |  |  |  | 0
During 12th Plan
7 | Improvement/Upgradation of Pakke-Seijosa-Itakhola Road | PWD | 02.06.2015 | 1376 | 1238 |  | 2/6/2015 (Rs.500.00 lakh) + 29-3-2017 (Rs.679.39 lakh) | 1179.39 | 500 | 679.39 | 2015-16 | 497.2 | 497.155 | 682.235 | 0.04502 | 137.6 |  | 51.18 |  | 0
| Sub Total PWD |  |  | 33248.88 | 29953.59 |  |  | 27507.59 | 26122.2437 | 1385.3463 |  | 26027.0083 | 25113.423 | 2394.167 | 913.5853 | 3294.89 |  | 2405.77 | 2354.49 | 2351.0838