## Sheet1
STATUS OF NEC FUNDED ONGOIN PROJECTS/SCHEMES (PRIORITY LIST)
(Rs. in Lakh)
Sl. No. | Name of the Project | Department | Date of Administrative Approval of the Project by NEC | Total Estimated Cost of the Project | NEC's Share Amount | Target Date of Completion | Instalment Released by NEC |  | Amount recommended by T & D | Amount released by FD |  | UC submitted | State Share
[7 empty] | Date | Amount |  | Date | Amount |  | Total State Share | State share recommended by T&D | State Share Released by FD | State Share UC Submitted
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 12 | 13 | 14 | 17 | 15 | 16 | 17
During 11th Plan
35 | Construction of 132/33 KV,1.16 MVA Umrangshu Dima Hassao (N.C. Hills) Dist., Assam | POWER | 2011-03-01 | 1344 | 1209.6 | June'2013 (O) Sept'2016 (R) |  |  | 1087 | 2013-14 | 1087 | 1087 | 134.4 | 59.67 | 59.67 | 59.67
[7 empty] | 2011-03-01 | 537
[7 empty] | 21/11/2013 | 550
[7 empty] | Total | 1087
36 | Lugnit small H.E. project in Karbi Anglong | POWER | 25-03-2008 | 500 | 450 | March, 2012 (O) March, 2015 (R ) | 25/3/2008 | 150 | 150 |  | 150 | 150 | 50 |  |  | 0
37 | Amring small H.E. project in Karbi Anglong. | POWER | 25-11-2008 | 211 | 189.9 | Work completed in all respects in 30/09/2014 | 25/11/2008 | 40 | 79.072 |  | 40 | 79.07 | 21.1 |  |  | 0
15
[7 empty] | 2014-04-06 | 50 |  |  | 24.07
[7 empty] | Total | 90 |  |  | 79.07
During 12th Plan
38 | Augmentation of transformer capacity of 220X132 kv BTPS Sub-Station from 1x160MVA+IX80MVA to 2x160 | POWER | 20-5-2016 | 678 | 610.2 |  | Rs.240.00 lakh 20/5/2016 + Rs.240.00 lakh 18/7/2017 | 480 | 240 |  | 240 | 240 | 67.8
39 | Construction of 33/11kv,2x5MVA Sub-Station alongwith associated 33kv,11kv &LT Feeders at Bishnupur Panch ali under Dhemaji Electrical Division APDCL, Dhemaji. | POWER | 20-5-2016 | 1025 | 922.5 |  | 20/5/2016 | 370 | 370 |  | 370 |  | 102.5
40 | Augmentation of transformer capacity of 132/33 kv Biswanath Chariali (Pavoi) Sub-Station from2x16MVA to 2x40 MVA | POWER | 20-5-2016 | 709 | 638.1 |  | Rs.260.00 lakh 20/5/2016 + Rs.250.00 lakh 18/7/2017 | 510 | 260 |  | 260 | 260 | 70.9
| Sub Total Power |  |  | 4467 | 4020.3 |  |  | 2687 | 2186.072 |  | 2186.07 | 1816.07 | 446.7 | 59.67 | 59.67 | 59.67