## Cultural Affairs
Cultural Affairs Department (as on June ,2019)
Sl. No. | NLCPR Project | Sanction Date | Approved Cost | Release by MDoNER | G/S recommended byT&D | UC Submitted to MDoNER(G/S) | UC pending G/S) | Fund yet to be moved/received by deptt (G/S) | Total S/S | S/S recom by T&D |  | Physical progress
2007-2008
1 | Construction of Sankar Madhab Cultural Complex at Letekupukhuri at Bhogpur Chariali Lakhimpur District, Assam | 2007-10-25 | 401.45 | 126.45 | 126.45 | 126.45 | 0 | 0 | 40.14 | 12.64 |  | 43
2 | Development and Upgradation of Jyoti Chitraban Film and Television Institute | 2007-12-20 | 1346.77 | 693.48 | 693.48 | 693.48 | 0 | 0 | 134.2 | 134.2 | 0 | 90
3 | Bodoland Indigenous Tribal Art & Cultural Complex-cum Film Studio at Kathalguri, Kokrajhar | 2007-12-24 | 495.14 | 320.37 | 320.37 | 160.66 | 159.71 | 0 | 49.51 | 20 | 0 | 90
4 | Construction of Cultural Centre/Complex at Dotma in Kokrajhar | 2007-12-26 | 221.06 | 99.05 | 99.05 | 99.05 | 0 | 0 | 22.1 | 9.905 |  | 90
Sub Total 2007-2008:- |  |  | 2464.42 | 1239.35 | 1239.35 | 1079.64 | 159.71 | 0 | 245.95 | 176.745 | 0
2008-2009
5 | Preservation of cultural Heritage of Majuli Natun Kamalabari satra (Phase-I) | 2009-11-05 | 618.97 | 436.92 | 218.46 | 218.46 | 0 | 218.46 | 61.89 | 22 |  | 52
2010-2011
6 | Socio-Literary Cultural Complex of Bodo Sahitya Sabha at Bathooupuri, Gorchuk, Guwahati | 2010-12-13 | 841.01 | 593.64 | 593.64 | 593.64 | 0 | 0 | 84.1 | 66 |  | 90
2011-2012
7 | Construction of Govt college of Arts & Crafts in Kamrup District | 2011-06-27 | 500 | 178.61 | 26.05 | 0 | 0 | 152.56 | 50 | 0 |  | 10
2012-2013
8 | Mahapurush shri shri Madhav dev Kalakhetra at Dhekiakhowa ,at Jorhat Dist. | 2013-02-07 | 225.11 | 80.95 | 80.87 | 80.79 | 0.08 | 0 | 22.02 | 22.02 |  | 65
GRAND TOTAL |  |  | 4649.51 | 2529.47 | 2158.37 | 1972.53 | 159.79 | 371.02 | 463.96 | 286.765 | 0
0