## Education
NLCPR ongoing project- Education Deptt. as on June, 2019
Sl No. | NLCPR Project | Sanction Date | Approved Cost | Released by MDoNER | G/S recommended by T&D | U/C submitted to MDoNER G/S | U/C pending G/S | Fund yet to move by deptt G/S | Total S/S | S/S recommended by T&D | Physical Progress
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
2006-2007
1 | Modernisation & Augmentation of Infrastructure Development of Assam Textile Institute at Guwahati | 12.09.2006 | 741.49 | 233.57 | 233.57 | 200 | 33.57 | 0 | 74.14 | 0 | 51%
2007-2008
2 | Construction of Academic cum Administrative building of K.K.Handique Govt Sanskrit college | 21.06.2007 | 238.09 | 169.71 | 169.71 | 169.71 | 0 | 0 | 23.8 | 19 | 100%
3 | Dev. of Infrastructure facilities of Kharupetia college i.e. Const. of class rooms, computer laboratory with AC. Hostel for tennis etc. | 24.10.2007 | 175.68 | 112.27 | 112.27 | 55.33 | 56.94 | 168.589 | 17.56 | 17.56 | 80%
2010-2011
4 | Infrastructure Development of Assam SLET Commission | 15.11.2010 | 334.46 | 118.04 | 101.712 | 0 | 101.712 | 16.328 | 33.44 | 11.804 | 32.5%
5 | Infrastructure Development of Assam Institute of Management, Guwahati | 23.07.2010 | 1461.11 | 829.16 | 676.899 | 676.899 | 0 | 152.261 | 146.11 | 73 | 70%
| Grand Total |  | 2950.83 | 1462.75 | 1294.161 | 1101.939 | 192.222 | 337.178 | 295.05 | 121.364