## Power
NLCPR projects =POWER Department as on June, 2019
Rs. in lakh
Sl. No. | NLCPR Project | Sanction Date | Approved Cost | Release Break-up |  | Grant Share recommended by T&D | Dept.yet to move for fund (G/S) | Utilisation Break-up |  | UC pending (S/S) | Total State Share | State Share recommended by T&D | State Share yet to move by the Deptt. | %Physical Progress
|  |  |  | Date | Amount |  |  | Date | Amount
1 | Construction of 220/132 KV, 2x50 MVA and 220/33 KV, 2x40 MVA Azara Sub - Station with 220 Kv LILO line from one circuit of 220 KV DC Agia - Sarusajia line along with construction of 132 KV SC line to Boko with terminal bay at 132/33 Boko Sub-station | 2007-09-26 | 3252 | 2607.89 |  | 2607.89 | 0 | 2607.89 |  | 35.44 | 325.2 | 325.2 | 0 | 100
|  |  |  | 2007-09-26 | 1140.95 |  |  | 2012-07-04 | 1140.95
|  |  |  | 2012-07-19 | 1466.94 |  |  | 2014-01-03 | 1466.94
2 | Construction of 132 KV BTPS - Kokrajhar S/C line and 132 KV Kokrajhar S/C line 132 Kv/33Kv S/S at Kokrajhar | 2010-11-29 | 4333.19 | 3651.07 |  | 3651.07 | 0 | 3651.07 |  | 27.63 | 433.32 | 433.32 | 0 | 100
|  |  |  | 2010-11-29 | 1538.02 |  |  | 2013-08-29 | 1538.02
|  |  |  | 2013-10-22 | 1020.13 |  |  | 2018-05-14 | 1020.13
3 | Construction of new 33/11 kV, 2x5 MVA S/S at Thirubari with 45 Km 11 kV lines and 55 Km 33 kV lines from Dhiligaon to Thirubari | 2012-11-23 | 890.94 | 320.65 |  | 320.65 | 0 | 320.65 |  | 0 | 89 | 44.55 | 44.45 | 100
|  |  |  | 2012-11-23 | 320.65 |  |  | 2016-10-15 | 320.65
|  |  |  | 6579.61 |  |  | 0 | 6579.61
4 | Construction of 38 km 33 KV line from Balipara to Bhalukpung.,Sonitpur | 2005-06 | 133 |  | 133 | 133 | 0 |  | 133
Total of Power sector (4Projects) |  |  | 8609.13 | 6712.61 |  | 6712.61 | 0 | 6712.61 |  | 63.07 | 847.52 | 803.07 | 44.45
[15 empty] | 2012-11-23 | 320.65 | 2016-09-21 | 320.65