## Minister Final 12-12-2016
NLPCR-ASSAM
Status of Ongoing Projects
Public Works(Road & Bridges) (Rs. in lac)
Sl. No. |  | NLCPR Project | Sanction Date | Approved Cost | Release by MDoNER |  | G/S recommended by P&D | FOC received by Deptt (G/S) | State Share Recmnd by P&D | FOC received by Deptt (S/S) | Utilisation Certificate received | UC pending | Fund yet to be moved/ received by Deptt. | Physical Progress | Remarks
[5 empty] | Amount | [5 empty] | Amount
1 | Jorhat | Street Lighting in Jorhat City leading to Jorhat Airport | 2010-04-05 | 213.47 | 150.68 | 150.68 | 150.68 | 150.68 | 15.17 | 15.17 | 150.68 | 0 | 0 | 90 | Fund awaited from MDoNER.
2 | Dhemaji | Construction of RCC Bridge No. 1/1, 3/1 and 5/1 on Bahirjonai Berachapari Road in Dhemaji District (Assam) with approaches | 2006-02-21 | 552.17 | 396.03 | 396.03 | 229.44 | 229.44 | 22.68 | 22.68 | 229.44 | 0 | 166.59 | 68 | Department yet to move for balance fund for Rs. 166.59 lakh
3 | Dhemaji | Construction of RCC Bridge No. 1/1, 4/1 and 5/1 on Sripani Jengrai Road in Dhemaji District (Assam) with approaches | 2006-02-21 | 301.78 | 216.91 | 216.91 | 216.91 | 216.91 | 32.5656 | 12.68 | 216.91 | 0 | 0 | 100 | CC submitted on 14.10.2016. UC Rs. 7.61 lakh received & under process.
4 |  | Construction of RCC bridge No.26/3 on Samar Ali Das Road in Karbi Anglong District in Assam | 2004-07-28 | 167.54 | 152.97 | 152.97 | 100.84 | 100.84 | 7.459 | 7.459 | 100.84 | 0 | 52.13 | 55 | Suo moto FOC issued of Rs. 5.8654.
5 |  | Construction of RCC Bridge No.4/3, 10/2 and 14/1 on Pengeri Philobari Road in Tinsukia District with approaches | 2004-07-07 | 233.66 | 216.29 | 216.29 | 210.29 | 210.29 | 0 | 0 | 210.29 | 0 | 0 | 99 | Balance work is taken up under CMs special package.
6 | Kokrajhar | Construction of RCC Bridge No.27/2, 28/1,29/1,30/2,32/2,35/1 and 45/1 including approaches on Dhubri-Kachugaon Road in Kokrajhar | 2006-05-16 | 516.4 | 368.13 | 368.13 | 368.13 | 368.13 | 41.304 | 41.304 | 368.13 | 0 | 0 | 100 | Rs. 11.20 lakh (GS) forwarded to MDoNEr on 8.11.2016.3rd Instalment awaited.
7 |  | Construction of RCC Bridge No.38/1, 43/1,43/3 and 44/2 including approaches and subway on Silchar - Hailakandi Road in Hailakandi District | 2006-05-16 | 353.13 | 305.95 | 305.95 | 250.77 | 250.77 | 28.25 | 28.25 | 250.77 | 0 | 55.18 | 100 | Department yet to move for balance fund.
8 | Goalpara | Construction of RCC Bridge No.2/2 and 4/2 including approaches on Gurnagar Tikrikilla Road in Goalpara District | 2006-05-16 | 355.19 | 303.55 | 303.55 | 298.072 | 252.28 | 40.461 | 40.461 | 252.276 | 0.04 | 51.27 | 96 | MDoNER releases Rs 51.27L as 3rd instalment on 25/04/2016. balance amount under process for payment.
9 |  | Construction of RCC Bridge No. 2/3, 5/1, 9/1, 11/1, 15/3, 16/1, 18/1 and 19/4 on Itakhola Pavoi Road in Sonitpur District (Assam) with approaches | 2005-10-28 | 875.42 | 761.23 | 761.23 | 624.09 | 624.09 | 69.34 | 69.34 | 624.09 | 0 | 137.14 | 84 | MDoNER releases Rs. 137.14L as 3rd instalment on 09/08/2016.
10 | Nalbari | Construction of RCC Bridge No. 16/1, 19/1 and 19/3 on Bagals Road in Nalbari District with approaches | 2005-10-31 | 404.73 | 355.25 | 355.25 | 304.25 | 238.93 | 33.593 | 30.18 | 238.93 | 0 | 0 | 83 | UC Rs. 2.34 L.under process. 3rd Instalment Rs. 116.32 lakh received on 19.08.2016.
11 |  | Construction of RCC Bridge No. 6/1, 7/1, 8/1, 8/2, 9/1, 11/1 and 11/2 on Sepon Suffry Road in Sivasagar District (Assam) with approaches | 2005-12-27 | 411.17 | 360.86 | 360.86 | 342.62 | 342.62 | 29.2 | 29.2 | 342.55 | 0.07 | 18.24 | 96 | demand for balance fund awaited from PWD® .
12 |  | Construction of RCC Bridge No. 2/1 on Bamunbari to Jariguri Road in Dibrugarh District of Assam with approaches | 2005-12-21 | 108.05 | 94.21 | 94.21 | 93.16 | 93.16 | 8.64 | 8.64 | 93.16 | 0 | 1.05 | 100 | Suo moto FOC received Rs. 1.15L. UC Rs. 15.36 lakh (GS) forwarded to MDoNER on 29.11.2016.
13 |  | Construction of road and minor bridge from Motinagar to Buban hill Temple - Phase I | 2007-10-24 | 326.07 | 292.87 | 292.87 | 290.809 | 290.81 | 25.025 | 25.025 | 290.81 | 0 | 2.06 | 90 | UC for Rs. 58.63L (G/S) & Rs. 10.78L (S/S) received & is under process.
14 |  | Construction of Road from Bhangarpar to Chandranathppur via babur bazar (Length 5.5 KM) | 2007-12-20 | 249.05 | 219.06 | 219.06 | 179.73 | 178.73 | 13.6 | 13.6 | 178.73 | 0 | 40.33 | 56 | MDoNER releases Rs.39.33L as 3rd instalment on 15/09/2016.
15 |  | Construction of Dibrugarh Sapekhati road from km 12 to Km 18 along with 2 RCC bridges No. 18/1 and 19/1 with approches (Bridge over river Buridihing at Saraighat) | 2007-12-19 | 2116.45 | 1885.96 | 1885.96 | 1879.82 | 1879.82 | 211.65 | 211.65 | 1551.39 | 328.43 | 6.14 | 100 | Balance UC & C.C received but yet to send MDoNER due to non receipt of undertaking from PWD as sought by P&D Deptt.
16 | Hailakandi | Metalling and Black Topping of Swapanpur to Ramchandi Road of Hailakandi District. | 2008-03-27 | 379.75 | 273.12 | 273.12 | 273.12 | 273.12 | 0 | 0 | 273.12 | 0 | 0 | 92 | 3rd installment is awaited. Suo moto FOC issued.
17 | Lakhimpur | Construction of RCC bridge no. 18/2 over stream Bahanigaon & bridge no. 19/1 over river Kachikata on Laluk-Narayanpur via Bihpuria Road in Lakhimpur District | 2008-09-30 | 208.7 | 149.98 | 149.98 | 149.98 | 149.98 | 20.48 | 20.48 | 149.98 | 0 | 0 | 100 | 3rd instalment awaited.
18 | Dibrugarh | Construction of RCC bridge No. 57/1 on Gaurisagar Moran Road and construction of RCC bridge no. 15/2 over River Disam on Naharkatia - Tinkhong Road under Dibrugarh Rural Road Division | 2008-12-10 | 406.12 | 289.52 | 289.52 | 289.52 | 289.52 | 32.17 | 32.17 | 289.52 | 0 | 0 | 84 | CC forwarded to MDoNER on 22.07.2016.3rd installment awaited.
19 | Goalpara | Construction of RCC Br. No. 32/1 on AT road (old) including approaches with protection works in Goalpara | 2009-03-30 | 739.12 | 461.02 | 461.02 | 461.02 | 328.12 | 27.943 | 17.256 | 328.12 | 0 | 132.9 | 80 | Balance UC awaited from Deptt. Payment not received as informed by PWD.
20 |  | Rupshir Ali (Construction of Bridge Nos. 3/2,5/2 &5/4) | 2009-07-14 | 210 | 151.2 | 151.2 | 151.2 | 136.12 | 18.85 | 15.12 | 136.12 | 0 | 15.08 | 91 | 3rd installment awaited.Rs.3.73 lakh SS rcomen. by p&d on 8.11.16
21 |  | Construction of RCC Bridge No. 7/1,15/1 and 19/1 on Nagaon Barapujia Road(NH-38) Road division | 2009-08-18 | 465.83 | 403.67 | 403.67 | 335.38 | 287 | 37.22 | 37.22 | 287 | 0 | 68.29 | 95 | UC Rs. 4.38 L (GS) against 2nd installment forwarded to MDoNER on 15.10.16. 3rd inst. Received on 29.9.2016.Rs. 48.38322 lakh recom by P&D on 28.11.16.
22 | Udalguri | Improvement of Tangla Bhergaon Ramgaon Road from Ch.00 M to 9400 M including cross drainage works in Udalguri | 2010-02-05 | 1043.34 | 920.59 | 920.59 | 920.59 | 920.59 | 102.286 | 102.286 | 920.59 | 0 | 0 | 100 | C/C forwarded to M/DoNER on 08-10-2015.U/C of State Share is Awaited.Department requested to furnish U/C of S/S (on 08-10-2015)
23 | Nagaon | Upgradation of Nagaon - Bhuragaon Road via Dhing (SH-10) under Nagaon State Road Division (Nagaon District) | 2010-03-22 | 1151.91 | 1026.78 | 1026.78 | 1026.78 | 1026.78 | 110 | 110 | 1026.78 | 0 | 0 | 100 | CC awaited. Project completed.
24 | Dibrugarh | Improvement of Road Network leading towards Dibru- Chaikhowa National Park under Dibrugarh Rural Road division | 2010-03-22 | 747.42 | 619.73 | 619.73 | 602.578 | 537.58 | 33.7133 | 33.7133 | 537.58 | 0 | 17.15 | 70 | Rs.82.15 lakh released by MDoNER on 21.03.2016 as 3rd Instalment . Rs. 64.99821 lakh recommended by P&D on 21.10.2016.
25 | Nagaon | Construction of RCC Bridge No. 4/1 on Dimou-Raidongia Road over river Sonai under Nagaon Rural Road Division (Nagaon District) | 2010-04-05 | 270.98 | 188.4 | 188.4 | 96.5 | 96.5 | 10.19 | 10.19 | 96.5 | 0 | 91.9 | 65 | MDoNER releases Rs.91.90L as 2nd instalment on 19/08/2016.
26 |  | Metalling and Blacktopping of Road from Borhapjan samdang via Nahoroni road to Sukanguri L.P School in Tinsukia Rural Road Subdivision / Division | 2010-09-15 | 321.45 | 286.44 | 286.44 | 284.01 | 280.6 | 32 | 32 | 280.6 | 0 | 22.29 | 100 | C/C forwarded to MDoNER on 18.02.2016. Dept.yet to move for balance fund
27 | Nagaon | Construction of RCC Bridge No. 3/1 on Majgaon Shantipur Road over River Sonai under Nagaon rural road Division | 2010-06-17 | 333.19 | 237.55 | 237.55 | 217.32 | 217.32 | 13.2 | 13.2 | 217.32 | 0 | 20.55 | 92 | UC for Rs. 25.56499L forwarded to MDoNER on 15/10/2016.
28 | Tinsukia | Metalling & Black Topping of Road from Circuit House Tinsukia to NH-37 via Okanimuria Borguri Okanimuria Nakhrai and Lunpuria Kaibortogaon in Tinsukia Rural Road Subdivision/ Division | 2010-10-29 | 524.1 | 465.09 | 465.09 | 370.09 | 370.09 | 51.67 | 43.67 | 370.09 | 0 | 95 | 95 | 3rd installment of Rs. 95.00L released by MDoNER on 11.03.2016. Deptt. yet to move for fund.
29 | Dibrugarh | Construction of Moran Netai Road, Dibrugarh | 2010-11-10 | 303.42 | 214.39 | 214.39 | 214.39 | 214.39 | 0 | 0 | 213.82 | 0.57 | 0 | 78 | UC for Rs. 107.14L forwarded to MDoNER on 15/10/2016.
30 | Sibsagar | Construction of Tiphuk Jajolipukhuri Road with RCC Bridge No. 3/3 in Sibsagar District | 2010-11-10 | 559.91 | 494.23 | 494.23 | 396.23 | 396.23 | 25 | 25 | 396.23 | 0 | 98 | 70 | Deptt. yet to move for Rs.98.00L which is recently released.
31 | Sibsagar | Construction of Mohmora Ali with RCC Bridge No. 9/2 in Sibsagar District | 2010-11-12 | 771.96 | 271.8 | 271.8 | 40.24 | 40.24 | 0 | 0 | 40.18 | 0.06 | 231.56 | 25 | Deptt. yet to move for fund of Rs. 231.56L. UC for Rs. 40.08 lakh forwarded to MDoNER on 18.02.2016.
32 | Cachar | Construction of RCC Br. No. 2/2 and 2/3 (Renamed as Br. Nos. 3/1 and 4/6) on Shyamaprasadpur to Dossgram Road via Swapnargul over stream Singrai in Cachar District | 2010-11-29 | 257 | 183.22 | 183.22 | 183.22 | 183.22 | 25.52 | 25.52 | 183.22 | 0 | 0 | 79 | Funds awaited from MDoNER. .
33 | Bongaigaon | Const of RCC Br. No. ½ Over river Aie at Chillapara Kahibari villages on the road from Kokoijana 31-National High way to Nagaon.Manikpur 31 National Highway via Kirtanpara, Numbarpara villages under Bongaigaon rural road Divn. | 2010-11-29 | 4001.26 | 2851.2 | 2851.2 | 1425.63 | 1425.6 | 141.3374 | 141.3374 | 1425.6 | 0 | 1425.57 | 52 | 2nd instalment of Rs. 1425.60L received on 22-08-2016.
34 |  | Improvement of Road Network at Sonari Town under Charaideo Rural Road Division | 2010-12-13 | 723.74 | 521.1 | 521.1 | 521.1 | 521.1 | 57.32 | 57.32 | 520.08 | 1.02 | 0 | 93 | 3rd instalment awaited.
35 |  | Construction of RCC bridge no. 13/1, 13/2 and 30/2 on Mohbondha Road | 2011-01-25 | 614.33 | 438.3 | 438.3 | 299.81 | 299.81 | 24.35 | 24.35 | 299.81 | 0 | 138.49 | 76 | Deptt. yet to move for balance fund.
36 |  | Construction of Br. no 2/1&4/1 on Raha Barapujia road over river Botamari and Hatibandha with approaches in Nagoan District | 2011-02-22 | 369 | 317.52 | 317.52 | 309.51 | 309.51 | 35.6 | 35.6 | 309.51 | 0 | 8.01 | 85 | MDoNER releases Rs. 60.50L as 3rd instalment on 18/04/2016. UC for Rs. 52.49368L forwarded to MDONER on 15/10/2016.
37 | Jorhat | Improvement of JB Road | 2011-05-26 | 297.37 | 263.9 | 263.9 | 211.64 | 211.64 | 23.52 | 23.52 | 211.64 | 0 | 52.26 | 100 | MDoNER releases Rs.52.26L as 3rd instalment on 05/09/2016. UC for Rs.105.82 forwarded to MDoNER on 29-06-2015. CC submitted on 29.06.2015.
38 |  | Construction of road from Rangamati to kalaigaon road janaram chowka to aaola chowka | 2012-01-31 | 575.35 | 452.33 | 452.33 | 452.33 | 452.33 | 50.258 | 50.258 | 452.33 | 0 | 0 | 100% | UC of Rs. 58.35 lakh (GS) forwarded to MDoNER on 14.10.2016. Project completed.
39 |  | Construction of Maijan Thakurbari road to Malukbari road in Dibrugarh District | 2012-05-21 | 811 | 286.23 | 286.23 | 250.66 | 227.58 | 20 | 20 | 217.69 | 9.89 | 58.65 | 33 | UC Rs.73.45771 L(GS) & Rs. 20.00 lakh (SS) forwarded to MDoNER on 14.10.2016.
40 |  | Improvement of Road from 1st Km of Demow Dehing Road to Dhaoma Pukhuri (Length – 10.125 Km) with R.C.C. Bridge (Length – 18.75 m) in Demow Rural Road sub - Division | 2012-05-28 | 760 | 541.54 | 541.54 | 435.24 | 435.24 | 23 | 23 | 435.24 | 0 | 170.77 | 70 | UC Rs. 164.47 lakh (GS) forwarded to MDoNER on 29.11.16.
41 |  | Construction of RCC Bridges and Slab Culverts by Replacing Old Bridge and slab culverts on Kamarbondha Road upto 22nd Km | 2012-06-15 | 728.5 | 514.67 | 514.67 | 262.26 | 262.26 | 29.14 | 29.14 | 262.26 | 0 | 252.41 | 45 | MDoNER releases Rs.252.41L as 2nd instalment on 05/09/2016.
42 |  | Const. Of RCC Br.No.29/1 (at Brg.) at Kuhimari Bordowa road (SH-15) with RCC Bridge. | 2012-06-28 | 501.37 | 180.44 | 180.44 | 69.05 | 69.05 | 8.1929 | 8.19 | 69.05 | 0 | 111.39 | 20 | UC for Rs.42.12 lakh under process.
43 | Nalbari | Construction of RCC Bridge No. 3/1 over River Pagladia on U.C Baruah Road in Nalbari District including Approaches and Protection Work | 2012-08-21 | 730.15 | 522.5 | 522.5 | 262.8 | 262.8 | 29.2 | 29.2 | 262.8 | 0 | 259.7 | 45 | MDoNER releases Rs.259.70L as 2nd instalment on 05/09/2016. UC for Rs. 43.6507L forwarded to MDoNER on 16-08-2016.
44 |  | Improvement of Naginimora Jajoli Road from Ch. 8.346 Km to Ch. 13.650 Km including conversion of SPT bridge no. 14/1 to RCC Bridge | 2012-08-21 | 485.43 | 436.82 | 436.82 | 349.46 | 349.46 | 48.51 | 48.51 | 349.46 | 0 | 87.32 | 58 | MDoNER released Rs. 87.32L as 3rd instalment on 29/07/2016 & Deptt. yet to move for balance fund.
45 |  | Construction of Kaliapani RCC bridge No.21/1 over River Dibru on Domdoma Dighaltarang Natun Gaon road with approach Road in Tinsukia | 2012-08-22 | 1322.94 | 952.44 | 952.44 | 714.2052 | 620.88 | 69 | 52.91 | 620.88 | 0 | 331.56 | 35 | UC Rs. 144.88477 lakh forwarded to MDoNER on 8.11.2016. Rs. 69.00831 L recommended by P&D on 10.11.16.Rs. 93.11523 lakh (GS) reco by P&D on 3.12.2016.
46 |  | Construction of railway over Br. at Dhing gate on Nagaon Bhurgaon via Dhing at Nagaon under NLCPR | 2012-08-22 | 2105.46 | 1826.24 | 1826.24 | 1826.24 | 1826.24 | 202.91 | 184.22 | 1826.24 | 0 | 365.25 | 100 | 3rd installment Rs. 365.25 lakh released by MDoNER on 18.3.2016. UC Rs. 365.25 lakh forwarded to MDoNER on 29.11.2016.
47 |  | Construction of RCC Bridge No. 1/1 over River Doomdooma on old AT Road | 2012-09-26 | 421.87 | 151.8 | 151.8 | 53.09 | 0 | 0 | 0 | 0 | 0 | 98.709 | 15 | Rs. 53.09096 lakh recommended by P&D on 21.10.2016.
48 | Nalbari | Improvement of Kanimara Nannatary Road in Nalbari District | 2012-12-26 | 435 | 391.05 | 391.05 | 370.6754 | 312.84 | 34.75 | 34.75 | 312.84 | 0 | 78.21 | 82.16 | P&D recommended Rs.57.835376LLakh on 11.01.17 against the release of 3rd inst. of Rs.78.21L
49 | Barpeta | Construction of RCC Br.No.1/1 over river Kaldia on Sarumanikpur Maharani road. | 2013-02-22 | 461.56 | 332.32 | 332.32 | 316.05 | 316 | 42 | 18.45 | 316 | 0 | 38.19 | 80% | UC for Rs. 128.08L forwarded to MDoNER on 29.09.2016.3rd inst. awaited. S/S of Rs.23.55Lakh recommended by P&D on 26.12.2016
50 |  | Construction of RCC Br. No. 7/1 on Sissibargaon Amguri Road over Singimari steam in Dhemaji District | 2013-02-22 | 429.32 | 154.5 | 154.5 | 45.76 | 0 | 0 | 0 | 0 | 0 | 154.5 | 0 | Rs. 45.76689 lakh (GS) recommended by P&D on 23.11.16.
51 |  | Construction of road from Banamali Tiniali to Rongagorh Tiniali with RCC Br. No. 2/2 over river Desang and Br. No. 8/2 on Mohmora Ali | 2013-02-25 | 1422.31 | 1024 | 1024 | 512 | 512 | 56.79 | 56.79 | 512 | 0 | 0 | 65 | UC Rs. 21.81 lakh forwarded to MDoNER on 29.11.16.172.936 lakh (GS) forwarded to MDoNER on 15.10.2016.
52 |  | Const. of RCC. Br. No. 2/1 over river Belsiri on Dhekipelua to Belsiri T.E., Connecting NH-52, under Sonitpur Rural Road Division | 2013-02-25 | 552.5 | 198.75 | 198.75 | 198.754 | 198.75 | 38.41 | 22.08 | 198.75 | 0 | 0 | 50 | UC of Rs. 92.07 lakh forwarded to MDoNER on 29.09.2016.2nd install awaited. Rs. 16.32685 lakh (SS) recommen by P&D on 28.11.2016.
53 | Darrang | Construction of road from Ramhari to Bherbheri via Chamuakhat(Ch.8.00 Km to 11.50 KM) including cross drainage works (Darrang) | 2013-02-25 | 345.68 | 247.76 | 247.76 | 247.76 | 79.4 | 8.822 | 8.822 | 79.4 | 0 | 168.36 | 100% | MDoNER releases Rs.168.36L as 2nd instalment on 19/08/2016, P&D recommendede the 2nd ins. On 27.12.16
54 | Hailakandi | Construction of RCC Bridge No.6/1 over river Katakhal at Ratanpur Ferryghat on Hailakandi Ratanpur road(MDR) | 2013-03-25 | 2294.05 | 1651.64 |  | 1325.79 | 1240.8 | 153.17 | 153.17 | 1240.8 | 0 | 410.85 | 75% | UC Rs. 415.00 lakh (GS) & Rs. 140.857 lakh (SS) forwarded to MDoNER on 15.10.2016.UC Rs. 84.99 l under process.
55 |  | Improvement of Mridongpara Road under NLCPR in Sibsagar District | 2013-06-05 | 671.52 | 465.06 | 465.06 | 303.75 | 303.75 | 25.13 | 25.13 | 303.75 | 0 | 161.31 | 49 | Deptt. yet to move for balance fund.
56 |  | Construction of RCC Bridge No. 1/1 on Mohmoria to Kuruabahi via Bebejia Road over river Kalang under Nagaon Rural Road Division | 2013-06-05 | 274.08 | 220.73 | 220.73 | 220.73 | 220.73 | 24.52 | 24.52 | 220.73 | 0 | 0 | 90 | UC Rs. 4.15L under process.
57 | Bongaigaon | Construction of RCC Bridge no. 5/1 over river Manas connecting Goalpara and Numberpara village on the road from Tulungia at NH-31(B) to Manikpur at NH-31 via Borghola -Kirtanpara and Chakla | 2013-07-02 | 1794 | 1291.52 | 1291.52 | 645.75 | 645.75 | 71.75 | 0 | 645 | 0.75 | 645.77 | 55 | MDoNER releases Rs.645.77L as 2nd instalment on 24/11/2016. UC for Rs.645.00 L (GS) forwarded to MDoNER on 15.10.2016. Rs. 71.75 lakh recom. By P&D on 9.11.2016.
58 | Darrang | Improvement of Banglagarh Jaberikuchi Road including cross drainage works in Darrang District | 2013-07-02 | 2046.55 | 1473.51 | 1473.51 | 1345.28 | 1345.28 | 164.49 | 149.47 | 1345.29 | 0 | 128.23 | 78 | UC for Rs. 188.61L forwarded to MDoNER on 15/10/2016. Rs. 128.23L yet to move for fund by Deptt.Rs. 15.02 lakh recom by P&D on 10.11.16
59 | Goalpara | Construction of road from Rongjuli IB to Kherkuta via Bechimari road with RCC Bridge 1/1, 1/3 and 5/3 under Goalpara Rural Road Division | 2013-09-19 | 733.73 | 528.2 | 528.2 | 444.1445 | 444.14 | 29.29 | 29.29 | 444.14 | 0 | 84.06 | 67 | Rs. 84.06 L demand yet to move for fund by the Deptt.
60 |  | Construction of RCC Bridge No. 1/1 over river Barak at Sadarghat, Silchar on Silchar - Kumbhigram Road | 2013-11-07 | 5901.06 | 2124.38 | 2124.38 | 1291.288 | 1291.29 | 242.347 | 27.31 | 1291.29 | 0 | 1701.33 | 25% | UC for Rs. 176.36811L forwarded to MDoNER on 15/10/2016.UC Rs. 866.88 l (GS) sub to Mdoner on 3.12.16. P&D recommended Rs.107.517L (S/S) on 23/11/2016.
61 | Dhubri | Construction of road from Kanuri to Binnachora (Satgaharipara) via Nalia including protection works and 4 RCC bridges | 2013-12-09 | 3855.05 | 2774.3 | 2774.3 | 1933.75 | 1889.15 | 235.1581 | 235.1581 | 1887.15 | 2 | 885.15 | 75% | UC of Rs. 500.00L (GS) forwarded to MDoNER on 15.10.2016.
62 |  | Improvement of Morigaon – Pachatia-Damal-Dharamtul Road including construction of RCC bridge No. 5/1 over river Kolong | 2013-12-09 | 732.55 | 263.45 | 263.45 | 154.7507 | 154.75 | 0 | 0 | 154.75 | 0 | 108.7 | 20 | Deptt. yet to move for balance fund. UC for Rs. 154.75L forwarded to MDoNER on 14-09-2016.
63 | Cachar | Const. of road from Udharbond to Banaskandi Under Silchar Rural Road Division | 2013-12-09 | 312.19 | 112.05 | 112.05 | 22.786 | 22.79 | 0 | 0 | 22.786 | 0 | 89.264 | 8 | UC Rs. 22.78592 lakh received and under process.
64 | Nalbari | Construction of Khetri Dharmapur to Hajo Nalbari Road at Morowa via Piplibari, Kakaya,Jagara, Goalpara,Baguhati & Kalakuchi | 2013-12-09 | 1039.22 | 906.61 | 906.61 | 725.29 | 725.29 | 93.53 | 0 | 725.29 | 0 | 181.32 | 90 | MDoNER releases Rs.181.32L as 3rd instalment on 20/09/2016.
65 | Tinsukia | Widening & Strengthening of Lahowal- Bordubi-Tinsukia Road (L.B.T.Road) in Tinsukia District. | 2013-12-09 | 998.21 | 359.25 | 359.25 | 359.25 | 259.25 | 28.51 | 19.35 | 259.25 | 0 | 159.25 | 30 | UC Rs. 19.35 lakh (SS) forwarded to Mdoner on 29.09.16.Rs. 9.16713 l (SS) recom by P&D on 29.11.16.UC Rs. 100.00 lakh under process
66 |  | Construction and widening of road from Khowang Chariali to Chenimari | 2014-02-20 | 854.2 | 307.3 | 307.3 | 121.6 | 71.12 | 0 | 0 | 71.12 | 0 | 236.18 |  | Rs. 50.48 lakh payment under process .UC awaited.
67 |  | Widening and improvement of Barbora-Minirgon –Chapakhowa Road including conversion of SPT bridge No.7/1 in Tinsukia District | 2014-02-20 | 988.69 | 355.9 | 355.9 | 90.22 | 90.22 | 0 | 0 | 90.22 | 0 | 265.68 | 0 | Suo moto FOC received of Rs. 90.22L.
68 |  | Improvement of Namati to Sukani Road under PWD Dibrugarh Rural Road Division | 2014-02-20 | 631.58 | 227.25 | 227.25 | 227.25 | 227.25 | 0 | 0 | 227.25 | 0 | 0 | 0 | UC for RS. 227.25L forwarded to MDoNER on 14-09-2016. Fund awaited from MDoNER.
69 |  | Construction of RCC Bridge No. 2/1 on Nandini Karaimari Road in Assam | 14-07-2009 | 658.13 | 204.25 | 204.25 | 204.25 | 204.25 | 22.694 | 22.694 | 204.25 | 0 | 0 | 55 | 2nd instalment awaited.
70 |  | Construction of RCC Bridge No. 12/1 on Goroimari -Dewaguri Laharighat Road with approaches in Assam | 30-09-2009 | 317.34 | 225.62 | 225.62 | 176.25 | 113.11 | 7.0157 | 0 | 113.11 | 0 | 112.51 | 51 | MDoNER releases Rs.112.51L as 2nd instalment on 27/06/2016. Deptt. yet to move for fund.SS Rs. 7.01572 recomm by P&D on 9.11.16.
71 |  | Improvement and upgradation of Chencoories Elgin Road including construction of Major RCC bridge over river Ghagra | 15-10-2009 | 1180.91 | 818.02 | 818.02 | 818.02 | 811.98 | 92.8599 | 92.8599 | 811.9819 | 0 | 6.04 | 98 | 3rd instalment awaited.
72 | Kamrup(M) | Construction of Zoo Japorigog Road (CH.0.00 to 1865.00 m from R.G. Baruah Road near State Zoo to Junction Point of Dispur Narengi Road including electrical works | 13-12-2010 | 619.86 | 446.26 | 446.26 | 446.26 | 446.26 | 49.58 | 49.58 | 446.26 | 0 | 0 | 100 | 3rd instalment awaited.
73 |  | Construction of RCC Bridge No. 24/1 on Morigaon Moirabari Road in Morigaon District | 25-01-2011 | 315.54 | 223.84 | 223.84 | 223.84 | 223.84 | 24.87 | 24.87 | 223.84 | 0 | 0 | 85% | UC Rs. 15.05 lakh (GS) forwarded to MDoNER on 8.11.2016. Fund awaited.
74 |  | Construction of Bridge No. 1/1 including approaches and protection work over Jatinga at Borkhola on Mahasadak to Borkhola road | 22-02-2013 | 1432.23 | 1288.13 | 1288.13 | 1281.64 | 1159.5 | 142.4449 | 142.4449 | 1159.5 | 0 | 128.63 | 100% | UC for Rs. 129.00 lakh (GS) forwarded to MDoNER on 15.10.2016.
75 | Kamrup(M) | Improvement of Singimari –Sualkuchi Road including cross drainage works & road side drains in Kamrup district | 25-03-2013 | 1827.76 | 1315.6 | 1315.6 | 1315.6 | 657.8 | 73.09 | 73.09 | 657.8 | 0 | 506.13 | 55 | MDoNER releases Rs. 657.80L as 2nd instalment on 27-06-2016.Rs. 657.80 lakh recommended by P&D on 21.10.2016.
76 | Karimganj | Constn of road from 52.0 km point of NH 154 – Katlicherra Grant of District Hailakandi to Veterbond – Dullavcherra NEC road of Dist Karimganj | 27-06-2014 | 1616.58 | 1163.93 | 1163.93 | 1020.4393 | 872.47 | 102.959 | 102.959 | 872.47 | 0 | 291.46 | 64 | UC for Rs. 290.50 L (GS) forwarded to MDoNER on 15.10.2016.
77 | Darrang | Improvement of Kharupetia Udalguri Road from Ch.0.00 Km to 15.00 Km (EW, GSB, BM & SDBC, Pavement length=15.00 km, carriage way width=5.50 m) including RCC drains in the Bazar Portion under Darrang District” | 2015-03-25 | 2712.87 | 976.63 | 976.63 | 387.0936 | 387.09 | 43.0104 | 43.0104 | 387 | 0.09 | 589.63 | 31 | Deptt. yet to move for balance fund.
78 | Darrang | Construction of RCC Bridge.No.2/1 on the road from NH-52 to Kuwaripukhuri via Fakirapara and RCC Br.No 7/1 on Nimtoli kachomari Road including approach and protection works in Darrang District. | 2015-06-22 | 495.66 | 178.44 | 178.44 | 0 | 0 | 0 | 0 | 0 | 0 | 178.44 |  | AA not yet accorded.
79 |  | Construction of road side drain cum foothpath and provision for roadside streetlight illumination in Naharkotia Town in Dibrugarh Rural Road Division. | 2008-09 | 644.73 | 502.06 | 502.06 | 454.53 | 454.53 | 56 | 56 | 454.53 | 0 | 47.53 | 90 | MDoNER releases Rs.47.53 L as 3rd instalment on 05/09/2016.
12039.663
|  |  |  | 68920.91 | 45818.05 | 2025-06-10 01:12 | 36225.3556 | 34129.78 | 3744.7092 | 3212.818 | 33786.9039 | 342.92
|  |  |  | 68920.91 | 43443.47 |  | 34114.37 | 32805.51 | 3744.7092 | 3212.818 | 30984.23 | 1821.23 | 10636.8

## CompletedPWD Dec16
LIST OF COMPLETED PROJECTS UNDER THE NON-LAPSABLE CENTRAL POOL OF RESOURCES ( as on 08-07-2015 )
(Rs. in crore)
Sl. No. | Name of the Project | Year of sanction | Number of the Project | Approved cost | Total fund Released by MDONER | Total fund Utilised by GOA | Status
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
I | PWD(ROAD SCHEMES)
1 | Diguncherra to Airport | 1999-2000 | 1 | 0.25 | 0.25 | 0.25 | Completion Certificate submitted to DONER
2 | Jarighat to Lakhicherra Road | 1999-2000 | 1 | 0.92 | 0.92 | 0.92 | Completion Certificate submitted to DONER
3 | Haticherra - Dudpatil - Madurannamukh | 1999-2000 | 1 | 0.43 | 0.43 | 0.43 | Completion Certificate submitted to DONER
4 | Improvement of Kamakhya Temple Road | 2002-03 | 1 | 4.89 | 4.89 | 4.89 | Completion Certificate submitted to DONER
5 | Construction of RCC bridge No.40/1 on Bagals Road in Kamrup District In Assam. | 2004-05 | 1 | 1.29 | 1.17 | 1.17 | Completion Certificate submitted to DONER
6 | Construction of Road from Beltola Chariali to Sarusajai (Bisnu Rava Road) Guwahati, Assam. | 2005-06 | 1 | 7.77 | 7.77 | 7.77 | Completion Certificate submitted to DONER
7 | Construction of RCC bridge on 21/1 and 22/1 on North Guwahati - Mandakata Road. | 2003-04 | 1 | 2.4 | 1.89 | 1.89 | Completion Certificate submitted to DONER
8 | Construction of RCC Bridge No.1/1, 2/1 and 2/2 on Jonnai Silapathar Road in Dhemaji District in Assam. | 2004-05 | 1 | 1.9 | 1.85 | 1.85 | Completion Certificate submitted to DONER
9 | Bhangagarh - Bharalumukh VIP road for National Games - 2005. | 2004-05 | 1 | 9.82 | 9.54 | 9.54 | Completion Certificate submitted to DONER
10 | Hatigaon - Bhetapara Road in connection with National Games - 2005. | 2004-05 | 1 | 4.56 | 4.15 | 4.15 | Completion Certificate submitted to DONER
11 | Construction of RCC Bridge No.156/2, 159/1,163/2, 165/3, 172/2, 177/1 and 182/2 on Dhodar Ali Road in Sibsagar District. | 2004-05 | 1 | 3.53 | 3.44 | 3.22 | Completion Certificate submitted to DONER
12 | Construction of RCC Bridge No.1/3, 2/1 and 3/1 on Namti Ali Road in Sibsagar District. | 2004-05 | 1 | 0.9 | 0.82 | 0.82 | Completion Certificate submitted to DONER
13 | Construction of Additional two lane Rail over Bridge at A.T.Road at Maligaon, Guwahati. | 2005-06 | 1 | 13.56 | 13.27 | 12.02 | Completion Certificate submitted to DONER
14 | Construction of RCC Bridge No.3/2 over river Mansiri on Charduar Road in Sonitpur District with approaches. | 2005-06 | 1 | 1.66 | 1.64 | 1.48 | Completion Certificate submitted to DONER
15 | Construction of RCC bridge on 4/1 on Hatigaon - Bhetapara Road. | 2003-04 | 1 | 1.54 | 1.34 | 1.34 | Completion Certificate submitted to DONER
16 | Jagun Kharsang Road | 2004-05 | 1 | 3.04 | 2.57 | 2.57 | Completion Certificate submitted to DONER
17 | Construction of RCC Bridge No.6/1 on Udalguri Barbengera Road in Darrang District. | 2004-05 | 1 | 1.04 | 0.96 | 0.96 | Completion Certificate submitted to DONER
18 | Construction of RCC Bridge No.2/2 on Haripur Sansarghat Road in Nalbari District in Assam. | 2003-04 | 1 | 2.26 | 1.87 | 1.87 | Completion Certificate submitted to DONER
19 | Construction of RCC Bridge No.20/1 on Nalbari Palla Road in Nalbari District in Assam. | 2003-04 | 1 | 1.44 | 1.14 | 1.14 | Completion Certificate submitted to DONER
20 | Construction of RCC bridge No.8/2, 20/1, 21/1, 23/3, 29/2, 32/1, 36/1 and 40/1 on Mangaldoi Bhutiachang Road in Darrang District In Assam. | 2004-05 | 1 | 6.85 | 6.16 | 6.16 | Completion Certificate submitted to DONER
21 | Construction of RCC Bridge No.1/2 and 3/1 on Sarupeta-Bhuyan para Road in Barpeta District. | 2004-05 | 1 | 1.77 | 1.61 | 1.61 | Completion Certificate submitted to DONER
22 | Construction of RCC Bridge No.1/1, 4/1, 8/1 and 9/2 on Fakiragram-Sapatgram Road in Dhubri District with approaches. | 2005-06 | 1 | 5.15 | 5.02 | 5.02 | Completion Certificate submitted to DONER
23 | Construction of RCC Bridge No.5/1 on Sonakhira - Bubrighat Road in Karimganj Dist. With approaches. | 2005-06 | 1 | 0.97 | 0.93 | 0.93 | Completion Certificate submitted to DONER
24 | Construction of RCC Bridge No.3/1 on Pukia - Silapathar Road in Dhemaji Dist. | 2006-07 | 1 | 1.37 | 1.35 | 1.35 | Completion Certificate submitted to DONER
25 | Construction of RCC Bridge No.5/1,7/1,8/1,9/1 & 11/1 on Jogighopa-Chapar Road in Goalpara Dist. With approaches. | 2006-07 | 1 | 7.09 | 6.32 | 6.32 | Completion Certificate submitted to DONER
26 | Construction of 4 lane Tripura road including electrical works from NH-37 Bye Pass to GS road (Six Mile) via Jayanagar Chariali from ch. 0.00m 1650m.(Kamrup Dist.) | 2008-09 | 1 | 11.37 | 11.37 | 11.37 | Completion Certificate submitted to DONER
27 | Construction of RCC bridge No.3/1, 3/2, 6/3, 6/4, 6/6, 10/5,12/1,13/1,21/2 and 23/2 on Border Roads (Gar Ali) in Jorhat District In Assam. | 2004-05 | 1 | 3.98 | 3.87 | 3.87 | Completion Certificate submitted to DONER
28 | Construction of RCC Bridge No.1/1 and 2/3 on Additional Approach to Airport road. | 2003-04 | 1 | 1.73 | 1.64 | 1.64 | Completion Certificate submitted to DONER
29 | Construction of RCC Bridge No.42/5 & 74/1 on DLHS Road. | 2003-04 | 1 | 1.43 | 1.14 | 1.14 | Completion Certificate submitted to DONER
30 | Construction of RCC Bridge No.24/1 on Barpathar - Bokajan Deithor - Chowkihola (BBDC) Road in Karbi Anglong District in Assam. | 2004-05 | 1 | 0.54 | 0.49 | 0.49 | Completion Certificate submitted to DONER
31 | Construction of RCC Bridge No.40/2 on CPDMDK Road in Karbi Anglong District in Assam. | 2004-05 | 1 | 1.32 | 1.21 | 1.21 | Completion Certificate submitted to DONER
32 | STREET LIGHTS From Lokpriya Gopinath Bordoloi International Airport upto Jalukbari near Gauhati University for National Games 2005 in Assam. | 2004-05 | 1 | 2.39 | 2.16 | 2.15 | Completion Certificate submitted to DONER
33 | Construction of RCC bridge No.12/1 and 12/2 on Bangaon Jagara Road in Nalbari District In Assam. | 2004-05 | 1 | 1.75 | 1.7 | 1.7 | Completion Certificate submitted to DONER
34 | Construction of RCC Bridge No.17/4, 19/4, 20/2 and 26/1 on Mt. Sepon Sunpura Road in Sibsagar District with approaches. | 2005-06 | 1 | 3.78 | 3.37 | 3.37 | Completion Certificate submitted to DONER
35 | i) Construction of RCC Bridge No.6/1 on Chariali Pavoi Road in Sonitpur District with approaches. | 2005-06 | 1 | 0.89 | 0.85 | 0.85 | Completion Certificate submitted to DONER
36 | Construction of RCC Bridge No.2/3,7/2 & 3/2 on Bengbari-Ambangaon Road in Udalguri Dist. With approaches. | 2006-07 | 1 | 6.33 | 5.64 | 5.64 | Completion Certificate submitted to DONER
37 | Improvement of Roads of Sibsagar Town (MP) | 2007-08 | 1 | 2.42 | 2.38 | 2.38 | Completion Certificate submitted to DONER
38 | Upgradation of Nagaon Barapujia Rd. (MP) | 2007-08 | 1 | 2.98 | 1.8 | 1.8 | Completion Certificate submitted to DONER
39 | Improvement of Nagaon Marikolong Nonai Dakhinpat Rd. (MP) | 2007-08 | 1 | 1.99 | 1.95 | 1.95 | Completion Certificate submitted to DONER
40 | Widening & Raising of Nazirakhat Sonapur road.(MP) | 2007-08 | 1 | 2.65 | 2.08 | 2.08 | Completion Certificate submitted to DONER
41 | Improvement of Road from Kahilipara to Donbosco School at Dakhingaon.(MP) | 2007-08 | 1 | 2.52 | 2.51 | 2.51 | Completion Certificate submitted to DONER
42 | Improvement of Rampur Model Road (MP) | 2007-08 | 1 | 2.25 | 2 | 2 | Completion Certificate submitted to DONER
43 | Construction of RCC Bridge No.4/2, 9/2, 10/2 and 17/1 on Met-Na-Ali Road (Jorhat- Titabor) in Jorhat District. | 2004-05 | 1 | 1.43 | 1.3 | 1.3 | Completion Certificate submitted to DONER
44 | Construction of RCC Bridge No.24/2, 32/2 on Mt. Golaghat Merapani Road in Golaghat Dist. With approaches. | 2005-06 | 1 | 1.86 | 1.79 | 1.79 | Completion Certificate submitted to DONER
45 | Construction of RCC Bridge No.4/1 & 15/1 on Nagaon - Bhuragaon Road in Nagaon Dist. | 2006-07 | 1 | 4.34 | 4.05 | 4.05 | Completion Certificate submitted to DONER
46 | Construction of RCC Br. No.1/1 & 4/1 on Nilbagan -Hojai road in Nagaon District. | 2006-07 | 1 | 1.92 | 1.71 | 1.71 | Completion Certificate submitted to DONER
47 | Construction of RCC bridge No.1/1 over river Channel Gadadhar on Silairpar- Borshijhora Road in Dhubri Dist. | 2008-09 | 1 | 4.51 | 4.06 | 4.06 | Completion Certificate submitted to DONER
48 | Improvement of Badlapara to Dharamjuli Road under Udalguri R.R. Division | 2008-09 | 1 | 4.03 | 3.94 | 3.94 | Completion Certificate submitted to DONER
49 | Construction of RCC Br. No. 4/1on Belguri Satrsal Road in Dhubri District.Road | 2007-08 | 1 | 2.73 | 2.73 | 2.73 | Completion Certificate submitted to DONER
50 | Construction of RCC Bridge No.13/1, 14/1, 15/1, 20/3 and 22/1 on Silchar Kumbhirgram Road in Cachar District in Assam. | 2004-05 | 1 | 5.68 | 5.18 | 5.18 | Completion Certificate submitted to DONER
51 | v) Construction of RCC Bridge No.9/2 on Borbhogia-Mikirbheta Road in Marigaon District with approaches. | 2005-06 | 1 | 2.39 | 2.13 | 2.13 | Completion Certificate submitted to DONER
52 | Construction of RCC Bridge No.4/1, 6/1 and 14/1 on North Lakhimpur- Kamalabari Road with approaches. | 2005-06 | 1 | 4.55 | 4.06 | 4.06 | Completion Certificate submitted to DONER
53 | Construction of RCC Bridge No.2/1 on Kokrajhar-Monakucha Road in Kokrajhar District with approaches. | 2005-06 | 1 | 9.91 | 8.83 | 8.83 | Completion Certificate submitted to DONER
54 | Construction of RCC Bridge No.35/2 and 53/2 on Moran Naharkatia Road in Dibrugarh District in Assam. | 2004-05 | 1 | 1.14 | 1.04 | 1.04 | Completion Certificate submitted to DONER
55 | Construction of RCC Bridge No.5/1 on Buragohain - Tinthengia Road in Dibrugarh Dist. With approaches. | 2005-06 | 1 | 0.99 | 0.88 | 0.88 | Completion Certificate submitted to DONER
56 | Construction of RCC Br. No.1/1 over river Santijan on Srimanta Sankar Deva Goveshana Kendra in Nagaon District. | 2007-08 | 1 | 2.81 | 2.5 | 2.5 | Completion Certificate submitted to DONER
57 | Construction of RCC Br. No. 7/1 on Dharamtul dandua Road with approaches | 2008-09 | 1 | 2.48 | 2.21 | 2.21 | Completion Certificate submitted to DONER
58 | Improvement of Bezera Balikuchi roadin Kamrup (R) (1938) | 2010-11 | 1 | 3.71 | 2.61 | 2.61 | Completion Certificate submitted to DONER
59 | Construction of Rcc Br. No. 4/1 extn. On garmari Gaalmari Road | 2009-10 | 1 | 2.33 | 2.08 | 1.62 | Completion Certificate submitted to DONER
60 | Improvement of Road in Jorhat Town(MP) | 2007-08 | 1 | 2.5 | 2.24 | 1.74 | Completion Certificate submitted to DONER
61 | Improvement of Dolgaon Kapati Rd.(Orang Dolgaon Rd.) (MP) | 2007-08 | 1 | 2.36 | 1.7 | 1.7 | Completion Certificate submitted to DONER
62 | Construction of RCC Bridge No.11/1 on Teok - Boloma - Nakachari Road in Jorhat Dist. With approaches. | 2005-06 | 1 | 1.09 | 0.97 | 0.97 | Completion Certificate submitted to DONER
63 | Improvement of Charigaon road in Jorhat | 2010-11 | 1 | 5.57 | 4 | 4 | Completion Certificate submitted to DONER
64 | Construction of RCC Bridge No.4/1 over river Bhogdoi and 6/1 J.B.Road in Jorhat District. | 2007-08 | 1 | 3.24 | 2.89 | 2.89 | Completion Certificate submitted to DONER
65 | Improvement of Barpeta road Bashbari Road leading to Manas sanctuary from 1st km to 21st km in Barpeta District | 2006-07 | 1 | 12.36 | 10.99 | 10.85 | Completion Certificate submitted to DONER
66 | Replacement of existing of RCC Br. No. 1/1, 4/1, 7/1 & 8/1 on Abhyapuri-Tulungia Road via Barbhula in Bongaigaon District | 2008-09 | 1 | 3.38 | 2.42 | 2.37 | Completion Certificate submitted to DONER
67 | Construction of RCC Br. No.1/1 over river Kalang on Gahi- Borjoha Road. | 2011-12 | 1 | 2.81 | 2.5 | 2.5 | Completion Certificate submitted to DONER
68 | Metalling & Black topping of road from Dr. Fakaruuddin Ali Ahmed Path to Dolgobindapur via Nalbari Hindu samshan, Nalbari along with Pucca Drain and RCC Slab Culverts (MP) | 2009-10 | 1 | 2.28 | 1.62 | 1.62 | Completion Certificate submitted to DONER
69 | Construction of RCC Br. No. 5/3 on Borbhogia-Mikirbheta Road in Morigoan Dist. | 2008-09 | 1 | 2.41 | 2.41 | 2.41 | Completion Certificate submitted to DONER
70 | Construction of RCC Br. No. 8/1 on Bhalukmari -Mikirbheta-Bhurbandha road with approaches in Morigaon District. | 2009-10 | 1 | 2.55 | 2.27 | 2.27 | Completion Certificate submitted to DONER
71 | Construction of RCC Bridge No.1/1 on Hazua Pota in baska. | 2007-08 | 1 | 2.64 | 2.35 | 2.35 | Completion Certificate submitted to DONER
72 | Improvement of Batabari Kopti Rd. (MP) | 2007-08 | 1 | 2.14 | 1.89 | 1.52 | Completion Certificate submitted to DONER
73 | Construction of RCC Bridge No.1/1, 3/1, 3/2 & 4/1 on Bhoirapur - Kulibazar Road in Dhemaji Dist. With approaches. | 2005-06 | 1 | 4.66 | 4.16 | 4.16 | CC on 2-3-15
74 | Construction of RCC Bridge No.10/1 &, 18/1 on Bagals Road in Nalbari District with approaches. | 2008-09 | 1 | 3.08 | 2.2 | 2.1 | Completion Certificate submitted to DONER
75 | Construction of RCC Bridge No.2/4,6/1 & 8/1 on Dr. Jinaram Das Road in Barpeta Dist. | 2006-07 | 1 | 5.36 | 4.66 | 4.66 | Completion Certificate submitted to DONER
76 | Construction of RCC Br. (a) No.1/1 and 2/1 on Deroi Rongli road (b) No. 2/1 on Deopling Ramunagar road and No.3/1 Ghilaguri road in Sibsagar District. | 2010-11 | 1 | 3.91 | 3.32 | 3.32 | Completion Certificate submitted to DONER on 29-06-2015 via P&D file No. PDP/PP/PWD/26/2009/99.
77 | Construction of Rcc Br.over river Aie. | 2010-11 | 1 | 78.84 | 70.25 | 70.25 | Completion Certificate submitted to DONER 21-05-2014.
78 | Construction of RCC Br. No 6/1 , 9/1 & 10/1 on Ambagaon – Kathpara solmari Singrai Rd. ( NG-17) in Nagaon Dist | 2009-10 | 1 | 2.39 | 2.14 | 2.14 | Completion Certificate submitted to DONER
79 | Improvement of Tangla Bhergaon Ramgaon Road from ch.00 M to 9400 M including cross drainage works in Udalguri District. | 2009-10 | 1 | 10.43 | 9.21 | 9.21 | Completion Certificate submitted to DONER vide letter No.PDP(PP)PWD4/2008/182, dtd. 08/10/2015.
80 | Construction of Rangia Dhamdhama Road including RCC Br. No. 18/1, 18/2, 19/2, 20/1 and 20/3. Nalbari Dist. | 2012-13 | 1 | 10.55 | 9.45 | 7.56 | MDoNER releases Rs. 188.94L on 15-02-2016 as 3rd and final installment.CC & UC of (S/S)for Rs.100.77833L forwarded to MDoNER vide letter No. PDP(PP) PWD 155/2011/112 dtd. 06-10-2015.
81 | Construction of RCC Bridge No.12/3 on Bakulia Rajapathar Road in Karbi Anglong District in Assam. | 2004-05 | 1 | 1.74 | 1.58 | 1.57 | UC for Rs.69.611 L (G/S) and Rs. 10.90L (S/S) forwarded to MDoNER on 14-10-2015.CC & UC for Rs. 26.82L forwarded to MDoNER on 06-04-2015.
82 | Upgradation of Dolgaon Town to Sialmari via Dekerigaon Kharpunihabi road (MP), Darrang District | 2007-08 | 1 | 2.52 | 2.12 | 2.12 | CC & UC for Rs. 32.08L forwarded to MDoNER on 11-08-2016. Work physically completed. CCwill be submitted shortly. Physical inspection report sought from DC, Darrang.
83 | Construction of RCC Br.No.1/2 & 4/1 on old AT Road, Khowng, Dibrugarh | 2010-11 | 1 | 2.9 | 2.59 | 2.59 | CC & UC for Rs. 49.96L (G/S) and Rs. 25.7589L (S/S) forwarded to MDoNER vide No. PDP(PP) PWD42/2010/60, dtd.08-08-2016. 3rd installment of Rs. 50.00L released by MDoNER. Clarification on UC sought by MDoNER & PWD requested on 6-5-2014. 3rd instalment awaited
84 | Construction of RCC major bridge at 7th km. of Kathal Road over river Ghagra (MP), Cachar District. | 2007-08 | 1 | 2.5 | 2.25 | 2.25 | CC submitted to MDoNER vide No. PDP(PP) 54/2007/1.36, dtd 06/09/2016. UC for Rs.44.79L forwarded to MDoNER.
85 | Sessa T.E. to Timona Road in Dibrugarh | 2012-13 | 1 | 4.01 | 3.55 | 3.55 | CC of Rs. 353.95L & UC for Rs. 70.79 L (G/S) & Rs. 7.77422L (S/S) forwarded to MDoNER vide No. PDP(PP) PWD 134/2011/185 on 06.09.2016. DoNER releases 3rd & final instalment of Rs.70.79L on 27-08-2015.
86 | Construction of RCC Bridge No.10/1 on Gogamukh Ghillamara Road in Dhemaji Dist. | 2005-06 | 1 | 1.08 | 0.95 | 0.95 | CC, UC for Rs. 20.56L (G/S) out of 3rd instalment of Rs.20.56L forwarded to MDoNER on 04/09/2015.
87 | Construction of RCC Bridge No.1/2 on Manja to Hidim Teron Road in Karbi Anglong District in Assam. | 2004-05 | 1 | 1.78 | 1.62 | 1.62 | Completion Certificate for Rs. 178.12L submitted to MDoNER vide NO. PDP(PP) 38/2008/73 on 14-09-2016.
88 | Construction of RCC Br. No.1/11 over Tanghat Channel on NH-31(tanghat to Asharkandi Ghegraralga Road) Dhubri District | 2012-13 | 1 | 3.25 | 2.92 | 2.92 | CC& UC for Rs. 58.49L forwarded to MDoNER vide No. PDP(PP) PWD 53/2007/113 dtd. 14-09-2016.Completion Certificate along with UC for S/S of Rs. 9.68L forwarded to MDoNER vide letter No. PDP(PP)pWD 5/2010/99, dtd. 22-01-2016.
89 | Construction of Rcc Br. No.6/2, 7/3, 8/2, 10/1 and 11/1 over branches of river Kaloo on A.P.S. Road, Dhubri District. | 2012-13 | 1 | 13.91 | 12.53 | 12.53 | CC & UC for Rs. 250.00L forwarded to MDoNER vide No. PDP(PP) PWD 53/2007/113, dtd. 14-09-2016. Completion Certificate along with UC for S/S of Rs. 39.039L forwarded to MDoNER vide letter NO. PDP(PP) PWD 154/2011/134, dtd. 29/01/2016.
90 | Construction of road with RCC Bridge (2nos.) from Pazipur Dhurkuchi to Borbari Narapara Road. | 2013-14 | 1 | 5.86 | 5.23 | 5.23 | CC & UC for Rs. 154.29L forwarded to MDoNER vide No. PDP(PP) PWD 53/2007/113, dtd 14-09-2016. .
91 | Construction of Road from Rangamati to Kalaigaon Road (between) Janaram Chowka to Aaola Chowka in Darrang District. | 2011-12 | 1 | 5.75 | 4.52 | 4.52 | UC for Rs. 58.35L (G/S) & Rs. 6.578L (S/S) forwarded to MDoNER on 15/10/2016. Completion Certificate submitted to DoNER vide letter No. PDP(PP) PWD64/2010/147, dtd. 10-12-2015.
| Subtotal: |  | 91 | 403.38 | 362.06 | 356.9
II | POWER
92 | 220 KV/DC Kathalguri- Tinsukia Line. | 1998-99 | 1 | 6.4 | 6.4 | 6.4 | Completion Certificate submitted to DONER
93 | Tinsukia Sub-Station 2x50 MVA, 220/132 KV | 1998-99 | 1 | 19.64 | 19.1 | 19.1 | Completion Certificate submitted to DONER
94 | Augmentation of 220/132 KV 2x50 MVA S/S to 2x100 S/S at Mariani. | 2001-02 | 1 | 6.37 | 6.25 | 6.25 | Completion Certificate submitted to DONER
95 | Installation of 2x31.5 MVA 132/33 KV Transformers at Sarusajai Sub-Station. | 2002-03 | 1 | 5.26 | 4.81 | 4.81 | Completion Certificate submitted to DONER
96 | Augmentation of existing 1x63 & 1x50 MVA. 220x132 KV Transformers by 2x100 MVA, 220x132 KV Transformer at Sarusajai Sub-Station. | 2002-03 | 1 | 7.8 | 7.8 | 7.8 | Completion Certificate submitted to DONER
97 | Renovaton of BTPS-Agia-Sarusajai 220 KV D/C Transmission line (Circuit-I & II). | 2002-03 | 1 | 28.38 | 28.38 | 28.38 | Completion Certificate submitted to DONER
98 | 220x132 KV 2x50 MVA Balipara S/S and a 132 KV Lilo line at Balipara from Ckt of the existing 132 KV DC Gohpur-Depota line. | 2002-03 | 1 | 13.71 | 13.71 | 13.71 | Completion Certificate submitted to DONER
99 | Construction of 220/132 kv, 1x50 MVA, and 132/33 KV, 1x16 MVA Agia Sub-station in Assam | 2007-08 | 1 | 7.39 | 7.22 | 7.22 | Completion Certificate submitted to DONER
100 | Augmentation of Transformer Capacity of 132/33KV Panchgram Sub station from 2x16 MVA to 2x25 MVA in Cachar dist | 2007-08 | 1 | 4.4 | 3.96 | 3.96 | Completion Certificate submitted to DONER
101 | 1 No. of construction of 11/.4 KV S/S (500 KVA-10, 315KVA-10, 250KVA-100,100KVA-100 & 63KVA-50 Nos.) | 2000-01 | 1 | 6.88 | 6.88 | 6.88 | Completion Certificate submitted to DONER
102 | Construction of 33KV 30 Kms D/C line from Chandrapur to Narengi. | 2000-01 | 1 | 2 | 2 | 2 | Completion Certificate submitted to DONER
103 | Construction of 11/0.4 KV distribution S/S lines & LT Lines. | 2000-01 | 1 | 1 | 1 | 1 | Completion Certificate submitted to DONER
104 | LT lines 100 Kms. | 2000-01 | 1 | 1 | 1 | 1 | Completion Certificate submitted to DONER
105 | ST&D- Augmentation of Hailakandi 33 KV S/S from 2X2.5 MVA to 1X5 MVA. | 2002-03 | 1 | 1.2 | 0.8 | 0.8 | Completion Certificate submitted to DONER
106 | ST&D- Augmentation of Duliajan 33 KV S/S from 1X2.5 MVA to 1X5 MVA. | 2002-03 | 1 | 0.9 | 0.9 | 0.9 | Completion Certificate submitted to DONER
107 | ST&D- Augmentation of Hojai 33 KV S/S from 1X2.5 MVA to 2X2.5 MVA. | 2002-03 | 1 | 0.6 | 0.35 | 0.35 | Completion Certificate submitted to DONER
108 | ST&D- Augmentation of Tezpur 33 KV S/S from (1X2.5+5) MVA to 2X5 MVA. | 2002-03 | 1 | 0.9 | 0.5 | 0.5 | Completion Certificate submitted to DONER
109 | ST&D- Augmentation of 33/11 KV Garbhanga S/S from 2X5 MVA to 2X10 MVA. | 2002-03 | 1 | 0.96 | 0.96 | 0.96 | Completion Certificate submitted to DONER
110 | ST&D- Augmentation of Titabor 33/11KV S/S from 2X2.5 MVA to 2X5 MVA. | 2002-03 | 1 | 1.05 | 1.05 | 1.05 | Completion Certificate submitted to DONER
111 | ST&D- Installation of 11 KV Auto Recloser in S/S (40 Nos.) | 2002-03 | 1 | 3.17 | 3.17 | 3.17 | Completion Certificate submitted to DONER
112 | ST&D- Augmentation of Karimganj 33 KV S/S from 1X5 + 1X3.16 MVA to 2X5 MVA. | 2002-03 | 1 | 0.75 | 0.75 | 0.75 | Completion Certificate submitted to DONER
113 | ST&D- Construction of 14.5 km 33 KV Pathsala-Nathkuchi line with augmentation of Pathsala S/S from 2X2.5 MVA to 2X5 MVA. | 2002-03 | 1 | 1.81 | 1.81 | 1.81 | Completion Certificate submitted to DONER
114 | ST&D- Reconductoring of Kahilipara-Ulubari 33 KV feeder from raccoon to wolf conductor. | 2002-03 | 1 | 0.05 | 0.05 | 0.05 | Completion Certificate submitted to DONER
115 | ST&D- Construction of 20 km 33KV line from Garbhanga to Borjhar and interlink with the existing 33KV Mirza-Rani line alongwith augmentation of 33/11 KV Mirza S/S to 2X5 MVA. | 2002-03 | 1 | 2.14 | 2.14 | 2.14 | Completion Certificate submitted to DONER
116 | ST&D- Construction of 18 km long 33 KV line Latka tapping point to Agamoni alongwith installation of 2.5 MVA S/S at Agamoni. | 2002-03 | 1 | 0.77 | 0.77 | 0.77 | Completion Certificate submitted to DONER
117 | ST&D- Construction of 28 km line from Rowta to Dhekiajuli on double pole suspension with wolf conductor. | 2002-03 | 1 | 1.51 | 1.51 | 1.51 | Completion Certificate submitted to DONER
118 | ST&D- Construction of 12 km 33 KV Baitamari to Chapar line with construction of 2X2.5 MVA S/S at Chapar. | 2002-03 | 1 | 0.72 | 0.72 | 0.72 | Completion Certificate submitted to DONER
119 | ST&D- Construction of 5 MVA, 33 KV S/S at Biswanath Chariali. | 2002-03 | 1 | 0.98 | 0.73 | 0.73 | Completion Certificate submitted to DONER
120 | ST&D- Construction of 1X2.5 MVA, 33 KV S/S at Missamari. | 2002-03 | 1 | 0.85 | 0.55 | 0.55 | Completion Certificate submitted to DONER
121 | ST&D- Construction of 33/11 KV, 1X2.5 MVA S/S with Auto Reclosers at Manzai. | 2002-03 | 1 | 0.28 | 0.28 | 0.28 | Completion Certificate submitted to DONER
122 | ST&D- Construction of 23 km 33 KV line from Rangia to Tamulpur. | 2002-03 | 1 | 0.47 | 0.47 | 0.47 | Completion Certificate submitted to DONER
123 | ST&D - Construction of 18 km long 33 kV line from Garmur to Pulibor alongwith 2x2.5 MVA S/S at Publibor | 2002-03 | 1 | 1.24 | 1.24 | 1.24 | Completion Certificate submitted to DONER
124 | ST&D - Construction of 45 Km long 33 KV line from Rowta Grid S/s to Paneri and augmentation of Paneri S/S from 2x3.16 MVA to 2x5MVA23 km 33 kV line from Rangia to Tamulpur | 2002-03 | 1 | 3.62 | 3.62 | 3.62 | Completion Certificate submitted to DONER
125 | ST&D- Construction of 26 km 33 KV Agia-Mornoi with construction of 2X2.5 MVA S/S at Mornoi. | 2002-03 | 1 | 1.63 | 1.63 | 1.63 | Completion Certificate submitted to DONER
126 | ST&D- Construction of 30 km 33 KV line from Pailapool to Kabuganj. | 2002-03 | 1 | 0.97 | 0.97 | 0.97 | Completion Certificate submitted to DONER
127 | ST&D- Replacament of old 11 KV MCCB by VCG at Beheting, Hazalbank, Doomdooma, Duliajan, North Lakhimpur, Meherpur, Karimganj, Tanda, Amingaon, Narangi, Nagaon, Kaliabor, Kathiatoli, Rupohi, Samaguri, Bokajan, Jorhat, Balipara, Tezpur, Chapaguri & Diphu S/S. | 2002-03 | 1 | 5.1 | 5.1 | 5.1 | Completion Certificate submitted to DONER
128 | ST&D- Construction of 37 km 33 KV line from Patharkandi to Karimganj. | 2002-03 | 1 | 1.19 | 1.19 | 1.19 | Completion Certificate submitted to DONER
129 | Augmentation of Dibrugarh S/S from (2X5 +1X2.5) MVA to 2X10 MVA. | 2005-06 | 1 | 0.76 | 0.76 | 0.76 | Completion Certificate submitted to DONER
130 | Construction of 33 KV line from Jorhat to Kakojan alongwith installation of 2X2.5 MVA S/S at Kakojan | 2005-06 | 1 | 0.9 | 0.9 | 0.9 | Completion Certificate submitted to DONER
131 | Construction of 22 km 33 KV line from Bordubi to Tengakhat with construction of 1X2.5 MVA S/S at Tengakhat. | 2005-06 | 1 | 1.22 | 1.22 | 1.22 | Completion Certificate submitted to DONER
132 | ST&D- Construction of 1X2.5 MVA, 33 KV S/S at Gogamukh. | 2002-03 | 1 | 0.45 | 0.3 | 0.3 | Completion Certificate submitted to DONER
133 | Rural Electrification of 20 No. of Tribal Villages | 2000-01 | 1 | 1.35 | 1.36 | 1.36 | Completion Certificate submitted to DONER
| Subtotal: |  | 42 | 147.77 | 144.31 | 144.31
III | WATER RESOURCES
134 | Flood Control management schemes at different locations of Brahmaputra and Barak Valley. 25 No. of schemes. | 1998-99 | 25 | 62.36 | 60.66 | 60.66 | Completion Certificate submitted to DONER
135 | Strengthening of Kahai Spur (Stone spur no.2) to protect Dibrugarh town from the erosion of river Brahmaputra. | 2001-02 | 1 | 6.55 | 6.25 | 6.25 | Completion Certificate submitted to DONER
136 | Protection of Harinagar Pt-III area cum dyke along R/B of river Surma from Harinagar to Nathanpur. | 2001-02 | 1 | 3.65 | 3.65 | 3.65 | Completion Certificate submitted to DONER
137 | Protection of Guwahati Town from erosion of river Brahmaputra from Kachari Bazar to D.C. Court. | 2001-02 | 1 | 3.33 | 3.33 | 3.33 | Completion Certificate submitted to DONER
138 | A/E measures to protect Dehingpuria village near Margherita town erosion of Buridehing river. | 2012-13 | 1 | 5.4 | 4.85 | 3.88 | Completion Certificate submitted to DONER. MDoNEr releases Rs. 97.20L on 18.04.2016.
139 | A/E measures to protect Naharkotia town from the erosion of river Buridehing at Jagun Gaon area. | 2012-13 | 1 | 7.31 | 6.58 | 6.58 | Completion Certificate submitted to DONER on 16/08/2014. UC submitted for Rs. 344.99L forwarded to MDoNER on 29/07/2015.
140 | Raising & Strengthening of Brahmaputra Dyke from Dizmore to Sonarigaon from 14th to 23.15th km. including closing of Amguri & Arney Nalla. | 2003-04 | 1 | 11.51 | 9.83 | 9.83 | Completion Certificate submitted to DONER
| Sub total: |  | 31 | 88.6 | 95.15 | 94.18
IV | IRRIGATION (MINOR)
141 | 89 Minor Irrigation Schemes ( of which 114 MIS in the PLAINS DIST. ) | 1998-99 | 114 | 14.68 | 14.68 | 14.4 | Completion Certificate submitted to DONER
142 | Remodeling of LIS from river Buridihing in Sassoni Mauja in Dibrugarh Dist. (MP) | 2007-08 | 1 | 2.4 | 2.11 | 2.11 | Completion Certificate submitted to DONER
143 | LIS from river Buridihing in Tengakhat Kheremia Mauja in Dibrugarh Dist. (MP) | 2007-08 | 1 | 2.92 | 2.57 | 2.57 | Completion Certificate submitted to DONER
144 | Dokhindhol LIS (MP) | 2007-08 | 1 | 2.11 | 1.87 | 1.53 | Completion Certificate submitted to DONER
| Subtotal: |  | 117 | 22.11 | 21.23 | 20.61
V | HEALTH & F.W.
145 | Sankaradeva Nethralaya | 1999-2000 | 1 | 1 | 1 | 1 | Completion Certificate submitted to DONER
146 | Upgradation of Guwahati Medical College & Hospital | 1999-2000 | 1 | 8 | 8 | 8 | Completion Certificate submitted to DONER
147 | Sankaradeva Nethralaya for purchase of equipments. | 2002-03 | 1 | 0.82 | 0.82 | 0.82 | Completion Certificate submitted to DONER
148 | Sankardeva Nethralaya (One operation theatre) |  |  | 1.53 | 1.53 | 1.53 | Completion Certificate submitted to DONER
149 | Development of Assam Medical College HOPE. | 2002-03 | 1 | 20 | 18.4 | 18.4 | Completion Certificate submitted to DONER
| Subtotal: |  | 4 | 31.35 | 29.75 | 29.75
VI | CULTURAL AFFAIRS.
150 | Sankardeva Kalakshetra | 1998-99 | 1 | 4.85 | 4.85 | 4.85 | Completion Certificate submitted to DONER
151 | 1250 Capacity Auditorium and Convention Centre at SSK Guwahati. | 2001-02 | 1 | 20 | 19.92 | 19.92 | Completion Certificate submitted to DONER
| Subtotal: |  | 2 | 24.85 | 24.77 | 24.77
VII | AGRICULTURE
152 | Installation of one lakh Shallow Tube Wells | 1999-2000 | 1 | 70.47 | 68.95 | 68.95 | Completion Certificate submitted to DONER
VIII | EDUCATION
153 | Creation of new infrastructure at Cotton College. | 1999-2000 | 1 | 3 | 3 | 3 | Completion Certificate submitted to DONER
X | SCIENCE & TECHNOLOGY
154 | Centre of Plasma physics | 2000-01 | 1 | 4.5 | 4.5 | 4.5 | Completion Certificate submitted to DONER
IX | GUWAHATI DEVELOPMENT
155 | Construction of Multistoried Secretariate Building. | 2002-03 | 1 | 69 | 69 | 69 | Completion Certificate submitted to DONER.
| Sub Total: |  | 1 | 69 | 69 | 69
X | SPORTS & YOUTH WELFARE
156 | Creation of Main Athletic Stadium Complex alongwith Multi purpose Indoor Hall at Guwahati for National Games 2005. | 2003-04 | 1 | 75.1 | 75.1 | 75.1 | Completion Certificate submitted to DONER
157 | Construction of Indoor Stadium at Silchar (MP) | 2007-08 | 1 | 4.94 | 4.36 | 4.36 | Completion Certificate submitted to DONER
| Sub Total: |  | 2 | 80.04 | 79.46 | 79.46
XI | PUBLIC HEALTH ENGNEERING
158 | Stabilisation of Silchar Water Supply Scheme. | 2004-05 | 1 | 3.85 | 3.51 | 3.51 | Completion Certificate submitted to DONER
| Sub Total: |  | 1 | 3.85 | 3.51 | 3.51
XII | JUDICIAL
159 | Infrastructure Development of North Eastern Judicial Officers Trainning Institute. | 2005-06 | 1 | 3.54 | 3.53 | 3.53 | Completion Certificate submitted to DONER
XIII | URBAN DEVELOPMENT
160 | Project for Road Network of Jorhat Master Plan Area in Jorhat | 2006-07 | 1 | 4.61 | 4.03 | 4.03 | Completion Certificate submitted to DONER
161 | Greater Silchar Town Water Supply Scheme. | 2002-03 | 1 | 12.3 | 11.59 | 11.59 | Completion Certificate submitted to DONER
| Subtotal: |  | 2 | 16.91 | 15.62 | 15.62
Transport
162 | Construction of Multi Level Parking at Paltan Bazar, Guwahati | 2008-09 | 1 | 9.24 | 8.32 | 8.32 | Completion Certificate submitted to DONER
XIV | HILL AREAS
163 | Protection of different reaches from the erosion of river Dhansiri K.A. Dist. Ph-I. | 2001-02 | 1 | 2.1 | 2.1 | 2.1 | Completion Certificate submitted to DONER
164 | Protection of different reaches from the erosion of river Dhansiri K.A. Dist. Ph-II. | 2001-02 | 1 | 1.65 | 1.65 | 1.65 | Completion Certificate submitted to DONER
165 | 89 Minor Irrigation Schemes (of which 10 MIS in HILL DIST.) | 1999-2000 | 10 | 10.52 | 10.52 | 10.52 | Completion Certificate submitted to DONER
166 | Washillinghadi ELIS | 2000-01 | 1 | 2.7 | 2.7 | 2.7 | Completion Certificate submitted to DONER
167 | Amreng MIS | 2001-02 | 1 | 12 | 12 | 12 | Completion Certificate submitted to DONER
168 | HILL DISTRICT 6Nos. Of scheme | 1999-2000 | 6 | 5 | 5 | 5 | Completion Certificate submitted to DONER
169 | Construction of Joising Doloi Auditorium Complex at Diphu (MP) | 2006-07 | 1 | 3.79 | 3.32 | 3.32 | Completion Certificate submitted to DONER
170 | Borjan Composit Irrigation scheme. | 2005-06 | 1 | 22.29 | 20.06 | 20.06 | Completion Certificate submitted to DONER
171 | Phumen phangcho Minor Irrigation Scheme | 2011-12 | 1 | 6.09 | 6.57 | 6.57 | Completion Certificate submitted to DONER
172 | Farkongcho Irrigation Scheme | 2013-14 | 1 | 10.22 | 9.18 | 9.18 | CC for Rs. 919.76L & UC for Rs. 183.51L forwarded to MDoNER on 06.09.2016.
| Sub Total: |  | 24 | 76.36 | 73.1 | 73.1
XV | WPT & BC (PM's Package)
173 | Construction of 15 No.of Higher Secondary School Building | 2000-01 | 1 | 1.5 | 1.5 | 1.5 | Completion Certificate submitted to DONER
174 | 100 Bedded Hospital at Udalguri. | 2000-01 | 1 | 1.69 | 1.69 | 1.69 | Completion Certificate submitted to DONER
175 | Mini Stadium at Chapaguri, Bongaigaon. (BAC Area) | 2007-08 | 1 | 0.2 | 0.19 | 0.19 | Completion Certificate submitted to DONER
176 | Khowra Flow Irrigation Scheme | 2012-13 | 1 | 3.55 | 3.19 | 2.55 | MDoNER releases Rs. 63.74L as 3rd and final installment on 15-03-2016. CC forwarded to MDoNER vide letter No. PDP(PP) 15/2009/55, dtd. 31-10-2015.
177 | Flow Irrigation Scheme from River Kulsik at Palashgarh under tangla irrigation Division, Udalguri District | 2011-12 | 1 | 19.28 | 17.33 | 17.33 | CC for Rs. 1927.88L & UC for Rs. 394.12L forwarded to MDoNER on 15/10/2016.
178 | Improvement of Tangla Kachubill Road . (WPT&BC) | 2010-11 | 1 | 10.8 | 9.62 | 9.62 | Completion Certificate submitted to MDoNER vide No.PDP(PP)PWD.54/2010/67 on 02/11/2016. UC for Rs. 212.04L (Rs. 192.32 lakh(final instlmnt) & the balance amount of 2nd instalment of Rs. 19.72L) forwarded to MDoNER on 03/07/2015.
179 | Improvement of Moholiapara Dongapara Borongajuli PWD Road (WPT&BC) | 2010-11 | 1 | 8.35 | 7.45 | 7.45 | Completion Certificate submitted to MDoNER vide No. PDP(PP) PWD.55/2010/76 on 02/11/2016. Cumulative UC for Rs. 744.23L (G/S) & Rs. 82.68L (S/S) forwarded to MDoNER on March, 2016.
| Sub Total : |  | 7 | 45.37 | 40.97 | 40.33
INDUSTRIES
180 | Powerline to Balipara Industrial growth centre (Project Dropped) | 2004-05 | 1 | 13.73 | 6.27 | 6.27 | UC for Rs. 627.00L forwarded to MDoNER.
181 | Approach Road to Balipara Industrial Growth Centre | 2005-06 | 1 | 2.69 | 2.42 | 2.42 | Completion Certificate and UC for Rs.26.86Lakh the State Share awaited from Deptt. will be submitted soon.
| Sub Total : |  | 2 | 16.42 | 8.69 | 8.69
| Total : NLCPR (G) |  | 328 | 1073.86 | 1022.96 | 1015.57
BTC Package
182 | Improvement of Dhamdhama Tupalia Subanthaka (DTS) Road. | 2004-05 | 1 | 13.72 | 13.72 | 13.32 | Completion Certificate submitted to DONER.
183 | Metalling and black-topping of Narabari Dawkibari Road. | 2004-05 | 1 | 15.95 | 15.95 | 15.38 | Completion Certificate submitted to DONER.
184 | Improvement of North Kajalgaon Dangtol Road. | 2004-05 | 1 | 5.93 | 5.93 | 5.92 | Completion Certificate submitted to DONER.
185 | Improvement and Upgradation of Kashikotra to Basugaon Road. | 2004-05 | 1 | 5.51 | 5.51 | 5.34 | Completion Certificate submitted to DONER.
186 | Improvement of Sundari-Vidyapur via Kakragaon Road. | 2004-05 | 1 | 9.21 | 9.21 | 8.95 | Completion Certificate submitted to DONER.
187 | Widening and strengthening of Fakiragram-Serfanguri Road incuding conversion of SPT bridge to RCC bridge. | 2004-05 | 1 | 20.49 | 20.49 | 19.47 | Completion Certificate submitted to DONER.
188 | Impv. Of North Kajolgaon Bengtol shantipur road, Chirang. | 2004-05 | 1 | 8.1 | 8.1 | 7.86 | Completion Certificate submitted to DONER.
189 | Impv. Of Udalguri Bhakatpara road via Bhairguri, Udalguri | 2004-05 | 1 | 4.44 | 4.44 | 4.33 | Completion Certificate submitted to DONER.
190 | Impv. Of Barnagaon Pakribari road, Udalguri | 2004-05 | 1 | 1.5 | 1.5 | 1.46 | Completion Certificate submitted to DONER.
191 | Impv. Of Kalaigaon Kundarbil road, Udalguri. | 2004-05 | 1 | 1.32 | 1.32 | 1.29 | Completion Certificate submitted to DONER.
192 | Construction of 100 bedded hospital at Kajalgaon | 2004-05 | 1 | 38.52 | 38.52 | 38.52 | Completion Certificate submitted to DONER.
193 | Gorreswar to Khairabari Road | 2005-06 | 1 | 6.57 | 6.57 | 6.38 | Completion Certificate submitted to DONER.
194 | Lailongpara - Kopati road | 2005-06 | 1 | 1.31 | 1.31 | 1.31 | Completion Certificate submitted to DONER.
195 | Improvement of Tihu Doomni road leading to Indo-Bhutan foot hills (7th Km. To 25 Km.) | 2005-06 | 1 | 9.95 | 9.95 | 9.66 | Completion Certificate submitted to DONER.
196 | Bhergaon - Cheuni - Khagrabari - Dimakuchi Road | 2005-06 | 1 | 1.32 | 1.32 | 1.31 | Completion Certificate submitted to DONER.
197 | Khowrang Mohanpur road | 2005-06 | 1 | 2.5 | 2.5 | 2.46 | Completion Certificate submitted to DONER.
198 | Chapaguri - Khagrabari Road | 2005-06 | 1 | 6.3 | 6.3 | 6.25 | Completion Certificate submitted to DONER.
199 | Tulsijhyora Kailamaila road via Amguri | 2005-06 | 1 | 9 | 9 | 8.88 | Completion Certificate submitted to DONER.
200 | Champamati Irrigation Project | 2005-06 | 1 | 43.85 | 43.85 | 43.85 | Completion Certificate submitted to DONER.
201 | Sukla Irrigation Project | 2005-06 | 1 | 8.13 | 8.13 | 8.13 | Completion Certificate submitted to DONER.
202 | Construction of North East Gateway Bus Terminus at Srinwgai, Gossaigaon. | 2005-06 | 1 | 1.44 | 1.44 | 1.4 | Completion Certificate submitted to DONER.
203 | Bheragaon Piped Water Supply Scheme | 2006-07 | 1 | 2.47 | 2.47 | 2.41 | Completion Certificate submitted to DONER.
204 | Uttarpar Piped Water Supply Scheme | 2006-07 | 1 | 8.64 | 8.64 | 8.56 | Completion Certificate submitted to DONER.
205 | Improvement of Kaurbaha Nagrijuli. | 2004-05 | 1 | 14.5 | 14.45 | 14.08 | Completion Certificate submitted to DONER.
206 | Construction of cold storage at Udalguri district. | 2005-06 | 1 | 4.14 | 4.14 | 4.14 | Completion Certificate submitted to DONER.
207 | Construction of cold storage at Kokrajhar district. | 2005-06 | 1 | 4.14 | 4.14 | 4.14 | Completion Certificate submitted to DONER.
208 | Improvement of Bhowraguri Kachugaon Road in Kokrajhar. | 2004-05 | 1 | 23.73 | 23.73 | 22.46 | Completion Certificate submitted to DONER.
209 | Metalling & blacktopping of Gossaigaon to Saraibil Road and conversion of SPT bridge to RCC bridge. | 2004-05 | 1 | 19.39 | 19.39 | 17.92 | Completion Certificate submitted to DONER.
210 | Gossaigaon to Kajigaon via Bhumka Tipkai road | 2005-06 | 1 | 11 | 11 | 10.82 | Completion Certificate submitted to DONER.
211 | Renovation /reconstruction of RNB Civil Hospital at Kokrajhar | 2005-06 | 1 | 7.58 | 7.58 | 7.27 | Completion Certificate submitted to DONER.
212 | Udalguri Piped Water Supply Scheme | 2006-07 | 1 | 5.34 | 5.34 | 5.23 | Completion Certificate submitted to DONER.
213 | Improvement of Khairabari MPK road (Andherighat) to Harisinga via Bhergaon, Tangla and Purandia 42-25 Km. Length with conversion of 11 SPT bridges to RCC. | 2006-07 | 1 | 26.5 | 26.5 | 25.71 | Completion Certificate submitted to DONER.
214 | Subankhata Water Supply Scheme | 2005-06 | 1 | 3.28 | 3.28 | 2.55 | Completion Certificate submitted to DONER
215 | Constn. Of Road from NH-31 at Barama to Masalpur, Baska. | 2004-05 | 1 | 14.43 | 13.93 | 14.01 | Completion Certificate submitted to DONER
216 | Constn. Of Bodofa Cultural Complex at Kokrajhar. | 2004-05 | 1 | 18.44 | 18.44 | 18.26 | Completion Certificate submitted to DONER
217 | Construction of Kasikotra Bamungaon Bengtol road. | 2005-06 | 1 | 11.69 | 11.69 | 10.36 | Completion Certificate submitted to DONER
218 | Bijni - Panbari road | 2005-06 | 1 | 15.59 | 15.59 | 15.19 | Completion Certificate submitted to DONER
219 | Strengthening of 11KVHT & LT line with 12 meter steel tubular Pole including illumination of Kokrajhar town | 2008-09 | 1 | 5.2 | 2.6 | 3.62 | Completion Certificate submitted to DONER
220 | Conversion of SPT bridge 20/1 over River Gondia into RCC bridge on Gossaigaon Sapatgram road | 2008-09 | 1 | 10.83 | 5.41 | 10.83 | Completion Certificate submitted to DONER
221 | Impv. Of Jalah Rupahi Saudarbhitha Gobardhana road Baksa. | 2004-05 | 1 | 10 | 10 | 9.7 | Completion Certificate submitted to DONER
222 | Kokrajhar Water Supply Scheme, Kokrajhar. | 2004-05 | 1 | 23.12 | 23.12 | 22.99 | Completion Certificate submitted to DONER
223 | Improvement of Jalah to Kumarikata Road including two bridges over river Kaldia and Diring | 2010-11 | 1 | 21.21 | 10.61 | 12.1 | Completion Certificate submitted to DONER
| Total : BTC Package |  | 42 | 476.28 | 457.11 | 453.82
Addl. BTC Projects
224 | Upgradation of Sports Complex at Kajalgaon in Chirang district (Addl. BTC Package) | 2010-11 | 1 | 5 | 2.5 | 2.55 | Completion Certificate submitted to DONER
225 | Const. Of RCC bridge 8/1 over Gurufella river on Gossaigaon –Sapatgram road, Kokrajhar Dist.(Addl. BTC Package) | 2010-11 | 1 | 7.92 | 3.96 | 7.62 | Completion Certificate submitted to DONER
226 | Const. Of RCC bridge 6/3 over Gongia river on Dotma-Bhawraguri. Road, Kokrajhar Dist.(Addl. BTC Package) | 2010-11 | 1 | 8 | 4 | 5.69 | Completion Certificate submitted to DONER
227 | Bodoland Bhawan at Dwaraka, New Delhi.(Addl. BTC Package) | 2010-11 | 1 | 9.1 | 4.55 | 7.47 | Completion Certificate submitted to DONER
228 | Bodo Language Research and Development Centre for Gauhati University, Kokrajhar.(Addl. BTC Package) | 2010-11 | 1 | 2.95 | 1.48 | 2.22 | Completion Certificate submitted to DONER
229 | Improvement of Rowta Station Feeder Road in Udalguri District.(Addl. BTC Package) | 2012-13 | 1 | 1.52 | 0.61 | 1.09 | Completion Certificate submitted to DONER
| Sub Total : Additional BTC Package |  | 6 | 34.49 | 17.1 | 26.64
| Total : (BTC+Addl. BTC) Packages |  | 48 | 510.77 | 474.21 | 480.46
PM's Package (BRO)
230 | Udalguri Bhairabpurkund Road | 2001-02 | 1 | 5.86 | 5.86 | 5.86 | Completion Certificate submitted to DONER.
231 | Tamulpur Goreswar Road | 2001-02 | 1 | 4.73 | 4.73 | 4.73 | Completion Certificate submitted to DONER.
232 | Kumari kata Jalah Road | 2001-02 | 1 | 15.08 | 14.96 | 14.96 | Completion Certificate submitted to DONER.
233 | Kachubari Naokata patharighat | 2001-02 | 1 | 3.96 | 3.96 | 3.95 | Completion Certificate submitted to DONER.
234 | Rangia Goreswar road | 2002-03 | 1 | 1.52 | 1.52 | 1.52 | Completion Certificate submitted to DONER.
235 | Hardutta Birudutta Road | 2002-03 | 1 | 1.33 | 1.31 | 1.31 | Completion Certificate submitted to DONER.
236 | Charuali-Ramgaon Nagarijuli Road | 2002-03 | 1 | 5.38 | 4.92 | 5.63 | Completion Certificate submitted to DONER.
237 | Mangaldoi Bhutiachang Road | 2002-03 | 1 | 1.21 | 1.21 | 1.2 | Completion Certificate submitted to DONER.
238 | Tangala Dimakuchi Road | 2002-03 | 1 | 2.51 | 2.51 | 2.49 | Completion Certificate submitted to DONER.
239 | Recce of Roads in BAC Area | 2003-04 | 1 | 0.03 | 0.03 | 0.03 | Completion Certificate submitted to DONER.
240 | Rowta Udalguri Road | 2001-02 | 1 | 8.32 | 8.31 | 8.94 | Completion Certificate submitted to DONER
241 | Udalguri tamul pur Road including SPT bridges | 2002-03 | 1 | 37.32 | 34.45 | 34.45 | Completion Certificate submitted to DONER
242 | Udalguri Khaibari Road | 2001-02 | 1 | 3.66 | 3.66 | 4.2 | Completion Certificate submitted to DONER
243 | Barpeta Basbari Road (BRO) | 2002-03 | 1 | 0.9 | 0.87 | 0.11 | Completion Certificate submitted to DONER
244 | Ambagaon-Barigaon Road(BRO) | 2002-03 | 1 | 7.63 | 7.13 | 6.86 | Completion Certificate submitted to DONER
245 | Barangajuli-Khairabari Road(BRO) | 2002-03 | 1 | 2.1 | 0.59 | 0.02 | Completion Certificate submitted to DONER
246 | Chamupara- Purandia Road.(BRO) | 2003-04 | 1 | 4.85 | 2.81 | 2.65 | Completion Certificate submitted to DONER
247 | Namati-Mushalpur Road | 2004-05 | 1 | 0.31 | 0.31 | 0.31 | Completion Certificate submitted to DONER
248 | Tihu-Barama Road | 2004-05 | 1 | 0.64 | 0.64 | 0.64 | Completion Certificate submitted to DONER
249 | Kaithalkuchi-Barama- Subankhata Road | 2004-05 | 1 | 0.61 | 0.61 | 0.61 | Completion Certificate submitted to DONER
| Sub Total: BRO |  | 20 | 107.95 | 100.39 | 100.47
| Total:- |  | 399 | 1735.48 | 1630.52 | 1629.46

## PW(Roads)
Status of Ongoing projects : Public Works(Road & Bridges) as on June, 2019
Sl. No. | District | Name of projects |  | Sanction Date | Approved Cost | Release by MDoNER |  | Grant Share recommended by P&D | Utilisation Certificate submitted (grant share) | UC pending (grant share) | Fund yet to be moved/ received by Deptt.(grant share) | Total state share | State Share Recmnd by P&D | Physical Progress
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 10 | 11 | 12 | 13 | 14 | 17
2004-05
1 | Karbi Anglong | Construction of RCC bridge No.26/3 on Samar Ali Das Road in Karbi Anglong District in Assam |  | 2004-07-28 | 167.54 | 147.11 | 147.11 | 107.78 | 107.78 | 0 | 39.33 | 10.48 | 7.459 | 70
2 | Tinsukia | Construction of RCC Bridge No.4/3, 10/2 and 14/1 on Pengeri Philobari Road in Tinsukia District with approaches |  | 2004-07-07 | 233.66 | 216.29 | 216.29 | 210.29 | 210.29 | 0 | 0 | 0 | 0 | 100
|  | Total |  |  | 401.2 | 363.4 | 363.4 | 318.07 | 318.07 | 0 | 39.33 | 10.48 | 7.459
2005-06
3 | Dhemaji | Construction of RCC Bridge No. 1/1, 3/1 and 5/1 on Bahirjonai Berachapari Road in Dhemaji District (Assam) with approaches |  | 2006-02-21 | 552.17 | 396.03 | 396.03 | 362.83 | 267.15 | 95.67 | 33.2 | 53.37 | 0 | 91 | 396.02
4 | Dhemaji | Construction of RCC Bridge No. 1/1, 4/1 and 5/1 on Sripani Jengrai Road in Dhemaji District (Assam) with approaches |  | 2006-02-21 | 301.78 | 216.91 | 216.91 | 216.91 | 216.91 | 0 | 0 | 30.17 | 12.68 | 100
5 | Nalbari | Construction of RCC Bridge No. 16/1, 19/1 and 19/3 on Bagals Road in Nalbari District with approaches |  | 2005-10-31 | 404.73 | 355.25 | 355.25 | 355.25 | 238.93 | 116.32 | 0 | 39.47 | 39.47 | 100
6 | Sibsagar | Construction of RCC Bridge No. 6/1, 7/1, 8/1, 8/2, 9/1, 11/1 and 11/2 on Sepon Suffry Road in Sivasagar District (Assam) with approaches |  | 2005-12-27 | 411.17 | 360.86 | 360.86 | 360.16 | 360.16 | 0 | 0.7 | 40.09 | 40.09 | 100
|  | Total |  |  | 1669.85 | 1329.05 | 1329.05 | 1295.15 | 1083.15 | 211.99 | 33.9 | 163.1 | 92.24
2006-07
7 | Kokrajhar | Construction of RCC Bridge No.27/2, 28/1,29/1,30/2,32/2,35/1 and 45/1 including approaches on Dhubri-Kachugaon Road in Kokrajhar |  | 2006-05-16 | 516.4 | 465.15 | 465.15 | 465.15 | 368.13 | 97.02 | 0 | 51.63 | 41.304 | 100
8 | Hailakandi | Construction of RCC Bridge No.38/1, 43/1,43/3 and 44/2 including approaches and subway on Silchar - Hailakandi Road in Hailakandi District |  | 2006-05-16 | 353.13 | 305.95 | 305.95 | 298.67 | 250.77 | 47.9 | 19.14 | 35.313 | 28.25 | 100
9 | Goalpara | Construction of RCC Bridge No.2/2 and 4/2 including approaches on Gurnagar Tikrikilla Road in Goalpara District |  | 2006-05-16 | 355.19 | 303.55 | 303.55 | 298.072 | 252.276 | 45.792 | 5.478 | 33.78 | 40.461 | 100
|  | Total |  |  | 1224.72 | 1074.65 | 1074.65 | 1061.892 | 871.176 | 190.712 | 24.618 | 120.723 | 110.015
2007-08
10 | Dibrugarh | Construction of Dibrugarh Sapekhati road from km 12 to Km 18 along with 2 RCC bridges No. 18/1 and 19/1 with approches (Bridge over river Buridihing at Saraighat) |  | 2007-12-19 | 2116.45 | 1885.96 | 1885.96 | 1879.82 | 1879.82 | 0 | 6.15 | 211.65 | 211.65 | 100
11 | Cachar | Construction of road and minor bridge from Motinagar to Buban hill Temple - Phase I |  | 2007-10-24 | 326.07 | 292.87 | 292.87 | 290.809 | 290.81 | 0 | 2.06 | 32.6 | 25.025 | 98
12 | Hailakandi | Metalling and Black Topping of Swapanpur to Ramchandi Road of Hailakandi District. |  | 2008-03-27 | 379.75 | 273.12 | 273.12 | 273.12 | 273.12 | 0 | 0 | 37.97 | 0 | 92
|  | Total |  |  | 2822.27 | 2451.95 | 2451.95 | 2443.749 | 2443.75 | 0 | 8.21 | 282.22 | 236.675
2008-09
13 | Lakhimpur | Construction of RCC bridge no. 18/2 over stream Bahanigaon & bridge no. 19/1 over river Kachikata on Laluk-Narayanpur via Bihpuria Road in Lakhimpur District |  | 2008-09-30 | 208.7 | 149.98 | 149.98 | 149.98 | 149.98 | 0 | 0 | 20.48 | 20.48 | 100
14 | Dibrugarh | Construction of RCC bridge No. 57/1 on Gaurisagar Moran Road and construction of RCC bridge no. 15/2 over River Disam on Naharkatia - Tinkhong Road under Dibrugarh Rural Road Division |  | 2008-12-10 | 406.12 | 347.23 | 347.23 | 347.23 | 289.52 | 57.71 | 0 | 32.17 | 32.17 | 100
15 | Goalpara | Construction of RCC Br. No. 32/1 on AT road (old) including approaches with protection works in Goalpara |  | 2009-03-30 | 739.12 | 461.02 | 461.02 | 461.01 | 305.79 | 155.23 | 0 | 73.19 | 29.72 | 100
16 | Dibrugarh | Construction of road side drain cum foothpath and provision for roadside streetlight illumination in Naharkotia Town in Dibrugarh Rural Road Division. |  | 2008-09 | 644.73 | 502.06 | 502.06 | 494.53 | 494.53 | 0 | 7.53 | 56 | 56 | 96
|  | Total |  |  | 1998.67 | 1460.29 | 1460.29 | 1452.75 | 1239.82 | 212.94 | 7.53 | 181.84 | 138.37
2009-10
17 | Sibsagar | Rupshir Ali (Construction of Bridge Nos. 3/2,5/2 &5/4) |  | 2009-07-14 | 210 | 188.39 | 188.39 | 180.15 | 180.15 | 0 | 8.24 | 18.85 | 18.85 | 100
18 | Morigaon | Construction of RCC Bridge No. 2/1 on Nandini Karaimari Road in Assam |  | 14-07-2009 | 658.13 | 466.75 | 466.75 | 332.64 | 204.25 | 0 | 262.5 | 65.81 | 22.694 | 77
19 | Morigaon | Construction of RCC Bridge No.12/1 on Goroimari-Dewaguri lahorighat road with approaches in Assam |  | 2009-09-30 | 317.34 | 225.62 | 225.62 | 225.62 | 225.62 | 0 | 0 | 31.33 | 31.17 | 87
20 | Dibrugarh | Improvement of Road Network leading towards Dibru- Chaikhowa National Park under Dibrugarh Rural Road division |  | 2010-03-22 | 747.42 | 659.27 | 659.27 | 638.95 | 638.95 | 0 | 20.32 | 73.26 | 73.26 | 100
21 | Cachar | Improvement and upgradation of Chencoories Elgin Road including construction of Major RCC bridge over river Ghagra |  | 15-10-2009 | 1180.91 | 818.02 | 818.02 | 818.02 | 818.02 | 0 | 0 | 118.01 | 92.8599 | 98
|  | Total |  |  | 3113.8 | 2358.05 | 2358.05 | 2195.38 | 2066.99 | 0 | 291.06 | 307.26 | 238.8339
2010-11
22 | Nagaon | Construction of RCC Bridge No. 4/1 on Dimou-Raidongia Road over river Sonai under Nagaon Rural Road Division (Nagaon District) |  | 2010-04-05 | 270.98 | 188.4 | 188.4 | 188.4 | 188.4 | 0 | 0 | 26.17 | 10.2 | 98
23 | Jorhat | Street Lighting in Jorhat City leading to Jorhat Airport |  | 2010-04-05 | 213.47 | 188.35 | 188.35 | 188.35 | 150.68 | 37.67 | 0 | 20.92 | 20.92 | 100
24 | Tinsukia | Metalling and Blacktopping of Road from Borhapjan samdang via Nahoroni road to Sukanguri L.P School in Tinsukia Rural Road Subdivision / Division |  | 2010-09-15 | 321.45 | 286.44 | 286.44 | 284.01 | 280.6 | 0 | 5.84 | 32 | 32 | 100
25 | Nagaon | Construction of RCC Bridge No. 3/1 on Majgaon Shantipur Road over River Sonai under Nagaon rural road Division |  | 2010-06-17 | 333.19 | 237.55 | 237.55 | 237.55 | 237.55 | 0 | 0 | 32.99 | 13.2 | 97
26 | Tinsukia | Metalling & Black Topping of Road from Circuit House Tinsukia to NH-37 via Okanimuria Borguri Okanimuria Nakhrai and Lunpuria Kaibortogaon in Tinsukia Rural Road Subdivision/ Division |  | 2010-10-29 | 524.1 | 465.09 | 465.09 | 449.3 | 449.3 | 0 | 15.79 | 51.67 | 51.67 | 100
27 | Dibrugarh | Construction of Moran Netai Road, Dibrugarh |  | 2010-11-10 | 303.42 | 214.39 | 214.39 | 214.39 | 213.82 | 0 | 0.57 | 29.74 | 24.317 | 93
28 | Sibsagar | Construction of Tiphuk Jajolipukhuri Road with RCC Bridge No. 3/3 in Sibsagar District |  | 2010-11-10 | 559.91 | 494.23 | 494.23 | 490.19 | 480.71 | 9.41 | 4.04 | 54.91 | 54.91 | 100
29 | Sibsagar | Construction of Mohmora Ali with RCC Bridge No. 9/2 in Sibsagar District |  | 2010-11-12 | 771.96 | 271.8 | 271.8 | 120.4 | 120.4 | 0 | 151.45 | 77.19 | 7.74 | 27
30 | Cachar | Construction of RCC Br. No. 2/2 and 2/3 (Renamed as Br. Nos. 3/1 and 4/6) on Shyamaprasadpur to Dossgram Road via Swapnargul over stream Singrai in Cachar district. |  | 2010-11-29 | 257 | 229.01 | 229.01 | 229.01 | 183.22 | 45.79 | 0 | 25.69 | 25.52 | 100
31 | Bongaigaon | Const of RCC Br. No. ½ Over river Aie at Chillapara Kahibari villages on the road from Kokoijana 31-National High way to Nagaon.Manikpur 31 National Highway via Kirtanpara, Numbarpara villages under Bongaigaon RR Divn. |  | 2010-11-29 | 4001.26 | 2851.2 | 2851.2 | 2658.84 | 2658.84 | 191 | 192.37 | 396.14 | 141.3374 | 80
32 | Sibsagar | Improvement of Road Network at Sonari Town under Charaideo Rural Road Division |  | 2010-12-13 | 723.74 | 636.21 | 636.21 | 636.21 | 635.21 | 1 | 0 | 70.68 | 70.68 | 100
33 | Jorhat | Construction of RCC bridge no. 13/1, 13/2 and 30/2 on Mohbondha Road |  | 2011-01-25 | 614.33 | 437.14 | 437.14 | 437.14 | 353.15 | 83.99 | 0 | 60.71 | 52.3471 | 86
34 | Nagaon | Construction of 2/1& 4/1 on Raha Barapujia road in Nagaon district. |  | 22.02.2011 | 369 | 317.52 | 317.52 | 317.52 | 309.51 | 8.01 | 0 | 35.6 | 35.6 | 100
35 | Kamrup(M) | Construction of Zoo Japorigog Road (CH.0.00 to 1865.00 m from R.G. Baruah Road near State Zoo to Junction Point of Dispur Narengi Road including electricalwork |  | 13-12-2010 | 619.86 | 469.66 | 469.66 | 469.66 | 446.26 | 23.4 | 0 | 61.98 | 61.98 | 100
36 | Morigaon | Construction of RCC Bridge No. 24/1 on Morigaon Moirabari Road in Morigaon District |  | 25-01-2011 | 315.54 | 223.84 | 223.84 | 223.84 | 223.84 | 0 | 0 | 31.08 | 30.92 | 100%
|  | Total |  |  | 10199.21 | 7510.83 | 7510.83 | 7144.81 | 6931.49 | 400.27 | 370.06 | 1007.47 | 633.3415
2012-13
37 | Dibrugarh | Construction of Maijan Thakurbari road to Malukbari road in Dibrugarh District |  | 2012-05-21 | 811 | 286.23 | 286.23 | 250.66 | 250.66 | #REF! | 35.57 | 81.1 | 20 | 40
38 | Sibsagar | Improvement of Road from 1st Km of Demow Dehing Road to Dhaoma Pukhuri (Length – 10.125 Km) with R.C.C. Bridge (Length – 18.75 m) in Demow Rural Road sub - Div. |  | 2012-05-28 | 760 | 541.65 | 541.65 | 500.2 | 435.24 | 0 | 106.41 | 76 | 55.52 | 70
39 | Jorhat | Construction of RCC Bridges and Slab Culverts by Replacing Old Bridge and slab culverts on Kamarbondha Road upto 22nd Km |  | 2012-06-15 | 728.5 | 514.67 | 514.67 | 512.7 | 512.7 | 0 | 1.97 | 70.11 | 70.11 | 100
40 | Morigaon | Const. Of RCC Br.No.29/1 (at Brg.) at Kuhimari Bordowa road (SH-15) with RCC Bridge. |  | 2012-06-28 | 501.37 | 180.44 | 180.44 | 142.38 | 87.23 | 55.15 | 38.06 | 38.33 | 8.1929 | 25
41 | Nalbari | Construction of RCC Bridge No. 3/1 over River Pagladia on U.C Baruah Road in Nalbari District including Approaches and Protection Work |  | 2012-08-21 | 730.15 | 653.13 | 653.13 | 653.13 | 0 | 0 | 0 | 72.57 | 72.57 | 100
42 | Sibsagar | Improvement of Naginimora Jajoli Road from Ch. 8.346 Km to Ch. 13.650 Km including conversion of SPT bridge no. 14/1 to RCC Bridge |  | 2012-08-21 | 485.43 | 436.79 | 436.79 | 417.04 | 417.04 | 0 | 19.75 | 48.5 | 48.5 | 100
43 | Tinsukia | Construction of Kaliapani RCC bridge No.21/1 over River Dibru on Domdoma Dighaltarang Natun Gaon road with approach Road in Tinsukia |  | 2012-08-22 | 1322.94 | 952.44 | 952.44 | 952.42 | 907.156 | 0 | 45.28 | 132.29 | 100.79 | 90
44 | Kamrup | Const. of Rangia Dhamdhama Road including RCC Br. No 18/1.18/2,19/2,20/1 & 20/3. |  | 2012-08-22 | 1054.77 | 944.77 | 944.77 | 942.52 | 942.52 | 0 | 0 | 104.97 | 104.97 | 100
45 | Tinsukia | Construction of RCC Bridge No. 1/1 over River Doomdooma on old AT Road |  | 2012-09-26 | 421.87 | 151.8 | 151.8 | 136.55 | 53.09 | 0 | 98.709 | 42.18 | 15.17 | 50
46 | Nalbari | Improvement of Kanimara Nannatary Road in Nalbari District |  | 2012-12-26 | 435 | 391.05 | 391.05 | 391.05 | 370.23 | 20.824 | 0 | 43.45 | 42.02 | 100
47 | Barpeta | Construction of RCC Br.No.1/1 over river Kaldia on Sarumanikpur Maharani road. |  | 2013-02-22 | 461.56 | 415.4 | 415.4 | 415.4 | 332.32 | 83.08 | 0 | 46.15 | 42 | 100%
48 | Dhemaji | Construction of RCC Br. No. 7/1 on Sissibargaon Amguri Road over Singimari steam in Dhemaji District |  | 2013-02-22 | 429.32 | 154.5 | 154.5 | 154.5 | 154.5 | 0 | 0 | 42.489 | 42.489 | 60
49 | Sibsagar | Construction of road from Banamali Tiniali to Rongagorh Tiniali with RCC Br. No. 2/2 over river Desang and Br. No. 8/2 on Mohmora Ali |  | 2013-02-25 | 1422.31 | 1024.03 | 1024.03 | 1024 | 941.57 | 0 | 0 | 142.23 | 114.2 | 80
50 | Sonitpur | Const. of RCC. Br. No. 2/1 over river Belsiri on Dhekipelua to Belsiri T.E., Connecting NH-52, under Sonitpur Rural Road Division |  | 2013-02-25 | 552.5 | 397.5 | 397.5 | 397.5 | 397.5 | 0 | 0 | 55.25 | 55.25 | 100
51 | Cachar | Construction of Bridge No. 1/1 including approaches and protection work over Jatinga at Borkhola on Mahasadak to Borkhola road |  | 22-02-2013 | 1432.23 | 1288.13 | 1288.13 | 1281.64 | 1281.64 | 0 | 6.49 | 142.44 | 142.4449 | 100%
52 | Darrang | Construction of road from Rangamati to Kalaigaonbetween Janaram Chawka to Aulachawka |  | 2012-08-21 | 575.35 | 492.47 | 492.47 | 490.98 | 452.33 | 38.65 | 1.49 | 49.57 | 49.57 | 100%
53 | Hailakandi | Construction of RCC Bridge No.6/1 over river Katakhal at Ratanpur Ferryghat on Hailakandi Ratanpur road(MDR) |  | 2013-03-25 | 2294.05 | 2064.54 |  | 2064.54 | 2063.59 | 74.52 | 25 | 229.4 | 226.47 | 100%
|  | Total |  |  | 14418.35 | 10889.54 | 8825 | 10727.21 | 9599.316 | #REF! | 378.729 | 1417.029 | 1210.2668
2013-14
54 | Sibsagar | Improvement of Mridongpara Road under NLCPR in Sibsagar District |  | 2013-06-05 | 671.52 | 465.06 | 465.06 | 465.06 | 465.06 | 0 | 0 | 67.15 | 33.75 | 81
55 | Bongaigaon | Construction of RCC Bridge no. 5/1 over river Manas connecting Goalpara and Numberpara village on the road from Tulungia at NH-31(B) to Manikpur at NH-31 via Borghola -Kirtanpara and Chakla |  | 2013-07-02 | 1794 | 1291.52 | 1291.52 | 1291.52 | 1291.52 | 0 | 0 | 179.4 | 71.75 | 91
56 | Darrang | Improvement of Banglagarh Jaberikuchi Road including cross drainage works in Darrang District |  | 2013-07-02 | 2046.55 | 1841.89 | 1841.89 | 1753.428 | 1681.66 | 71.77 | 88.46 | 204.65 | 164.49 | 94
57 | Goalpara | Construction of road from Rongjuli IB to Kherkuta via Bechimari road with RCC Bridge 1/1, 1/3 and 5/3 under Goalpara Rural Road Division |  | 2013-09-19 | 733.73 | 528.26 | 528.26 | 517.23 | 444.14 | 73.09 | 11.03 | 73.37 | 29.29 | 81
58 | Cachar | Construction of RCC Bridge No. 1/1 over river Barak at Sadarghat, Silchar on Silchar - Kumbhigram Road |  | 2013-11-07 | 5901.06 | 4248.04 | 4248.04 | 4248.04 | 4248.04 | 0 | 0 | 590.01 | 538.05 | 100%
59 | Dhubri | Construction of road from Kanuri to Binnachora (Satgaharipara) via Nalia including protection works and 4 RCC bridges |  | 2013-12-09 | 3855.05 | 2774.3 | 2774.3 | 2774.3 | 2774.3 | 0 | 0 | 385.5 | 385.5 | 100%
60 | Cachar | Const. of road from Udharbond to Banaskandi Under Silchar Rural Road Division |  | 2013-12-09 | 312.19 | 296.19 | 296.19 | 296.19 | 251.62 | 44.57 | 0 | 31.21 | 27.84 | 100%
61 | Nalbari | Construction of Khetri Dharmapur to Hajo Nalbari Road at Morowa via Piplibari, Kakaya,Jagara, Goalpara,Baguhati & Kalakuchi |  | 2013-12-09 | 1039.22 | 906.61 | 906.61 | 906.61 | 725.29 | 181.32 | 0 | 102.98 | 93.53 | 100
62 | Morigaon | Impr. Of Morigaon Pachatia Dhamal-dharamtul road including cons. Of RCC br. No.5/1 over river Kollong. |  | 09.12.2013 | 732.55 | 263.45 | 263.45 | 263.45 | 263.45 | 0 | 0 | 73.25 | 61.35 | 46
63 | Tinsukia | Widening & Strengthening of Lahowal- Bordubi-Tinsukia Road (L.B.T.Road) in Tinsukia District. |  | 2013-12-09 | 998.21 | 898.38 | 898.38 | 865..63795 | 718.5 | 147.1379 | 32.74 | 99.82 | 99.82 | 96
64 | Dibrugarh | Construction and widening of road from Khowang Chariali to Chenimari |  | 2014-02-20 | 854.2 | 307.3 | 307.3 | 307.3 | 307.3 | 0 | 0 | 85.37 | 85.37 | 43
65 | Tinsukia | Widening and improvement of Barbora-Minirgon –Chapakhowa Road including conversion of SPT bridge No.7/1 in Tinsukia dt |  | 2014-02-20 | 988.69 | 355.9 | 355.9 | 353.04 | 260.03 | 95.87 | 2.8559 | 98.86 | 39.54 | 41
66 | Dibrugarh | Improvement of Namati to Sukani Road under PWD Dibrugarh Rural Road Division |  | 2014-02-20 | 631.58 | 227.25 | 227.25 | 202.41 | 202.41 | 0 | 24.84 | 63.15 | 7.43 | 46
|  | Total |  |  | 20558.55 | 14404.15 | 14404.15 | 13378.578 | 13633.32 | 613.758 | 159.9259 | 2054.72 | 1637.71
2014-15
67 | Karimganj | Constn of road from 52.0 km point of NH 154 – Katlicherra Grant of District Hailakandi to Veterbond – Dullavcherra NEC road of Dist Karimganj |  | 27-06-2014 | 1616.58 | 1454.91 | 1454.91 | 1454.91 | 1163.93 | 290.98 | 37.17 | 161.65 | 155.07 | 100
68 | Darrang | Improvement of Kharupetia Udalguri Road from Ch.0.00 Km to 15.00 Km (EW, GSB, BM & SDBC, Pavement length=15.00 km, carriage way width=5.50 m) including RCC drains in the Bazar Portion under Darrang District” |  | 2015-03-25 | 2712.87 | 1947.71 | 1947.71 | 1947.71 | 1947.71 | 0 | 0 | 270.05 | 270.05 | 82.42%
|  | Total |  |  | 4329.45 | 3402.62 | 3402.62 | 3402.62 | 3111.64 | 290.98 | 37.17 | 431.7 | 425.12
2015-16
69 | Darrang | Construction of RCC Bridge.No.2/1 on the road from NH-52 to Kuwaripukhuri via Fakirapara and RCC Br.No 7/1 on Nimtoli kachomari Road including approach and protection works in Darrang District. |  | 2015-06-22 | 495.66 | 348.91 | 348.91 | 343.6633 | 189.94 | 65.136 | 5.2467 | 48.46 | 25.507 | 60
2017-18
70 | Kamrup(M) | Construction of alternative road to Kamakhya Temple at Guwahati in Kamrup(Metro) district(Phase-I restricted to hill cutting and retaining wall) under NLCPR in Assam |  | 2017-18 | 1385.39 | 498.6 | 498.6 | 273.2918 | 176.78 | 96.53 | 225.3082 | 138.53 | 30.365 | 25
71 | Dibrugarh | Construction of RCC Br. No 9/1 on Mancotta- Khamtighat Road along with approaches and protection works and strengthening of damaged road pavement from ch.8308.00m to ch.32600.00m via saraighat bridge up to Bamunbari Tiniali connecting MoranNaharkatiaRoadDibrugarh |  | 2017-18 | 1387 | 499.32 | 499.32 | 499.32 | 489.32 | 0 | 10 | 138.7 | 138.7 | 85
72 | Nalbari | Construction of road from kashimpur to Suplekuchi via Purbabharatii |  | 4: 2017-18; 5: 559.57; 6: 175.15; 7: 175.15; 12: 175.15; 13: 55.95
73 | Barpeta | Construction of two lane ROB in between Barpeta Railway Station and Surupeta Railway station replacing L.CGate No.SK-37 at Barpeta District. |  | 4: 2017-18; 5: 3416.27; 6: 1229.86; 7: 1229.86; 12: 1229.86; 13: 341.62
74 | Darrang | Construction of Digheripar Bordoulguri Borachuba road from ch-`10.10km to ch-4.12km and from ch4.560km to ch10.100km(Length=9.660km) including cross drainage works in darrang district |  | 4: 2017-18; 5: 1142.12; 6: 10; 7: 10; 12: 10
|  | Total |  |  | 7890.35 | 2412.93 | 2412.93 | 772.6118 | 666.1 | 96.53 | 1650.3182 | 674.8 | 169.065
|  | Grand Total:- |  |  | 69122.08 | 48006.37 | 45941.83 | 44536.484 | 42154.762 | #REF! | 3006.0979 | 6699.802 | 4924.6032