## Sports & YW
NLPCR-ASSAM
List of ongoing NLCPR projects as on June, 2019
(Rs. in lac)
Sports & Youth Welfare
Sl. No. | NLCPR Project | Sanction Date | Approved Cost | Release by MDoNER | Fund recommended by T&D (G/S) | UC received | Total S/S | Fund recommended by T&D (S/S) | Physical Progress | Deptt. yet to move/receive fund
1 | Development of Jorhat stadium at Jorhat | 2007-07-30 | 268.93 | 235.03 | 235.03 | 193.1 | 26.91 | 26.91 | 100% | 0
2 | Construction of District Sports Complex at Jhagrapara in Dhubri District | 2008-12-10 | 377.77 | 116.66 | 116.66 | 116.66 | 37.77 | 11.33 | 45% | 0
3 | Construction of Chandi Baruah Stadium at Barpeta | 2009-02-10 | 290.36 | 152.24 | 118.95 | 89.67 | 29.03 | 8.96 | 70% | 33.29
4 | Construction of Multi Disciplinary Sports Complex at Khanikar, Dibrugarh District | 2017-05-12 | 13982.23 | 10 |  |  | 1398.22 |  |  | 10
5 | Construction of RCC Gallery of District Sports Association( Stadium Complex , Hailakandi) | 2010-05-17 | 177.13 | 95.64 | 95.64 | 63.76 | 17.71 | 6.37 | 45%
|  |  | 15096.42 | 609.57 | 566.28 | 463.19 | 1509.64 | 53.57 |  | 43.29