## Urban Development
NLPCR-ASSAM
Status of the ongoing Project:- Urban Development as on June, 2019
Sl. No. | NLCPR Project | Sanction Date | Approved Cost | Release by MDoNER | Fund recommended by T& D | UC received | UC pending | Deptt. yet to move/receive fund | Total State Share ( in lakh) | State share recommended by T&D | Physical Progress
Amount
2006-2007
1 | Dhubri Town Water Supply Scheme | 2006-09-12 | 1026.53 | 923.88 | 923.88 | 923.88 | 0 | 0 | 102.65 | 102.65 | 90%
2 | Improvement of Roads and Natural Drainage System within Greater Tezpur Town | 2007-03-28 | 2551.78 | 348.13 | 348.13 | 348.13 | 0 | 0 | 0 | 34.81 | 74% of Drainage Work
| Sub Total:-2006-2007 |  | 3578.31 | 1272.01 | 1272.01 | 1272.01 | 0 | 0 | 102.65 | 137.46
2007-2008
3 | Golaghat Town Water Supply Scheme | 2007-05-28 | 504.61 | 440.93 | 440.93 | 440.93 | 0 | 0 | 50.46 | 50.46 | 100%
4 | Sibsagar Town Water Supply Scheme | 2007-05-28 | 1639.35 | 1179.43 | 1179.43 | 1179.43 | 0 | 0 | 163.93 | 163.93 | 70%
| Sub Total:-2007-2008 |  | 2143.96 | 1620.36 | 1620.36 | 1620.36 | 0 | 0 | 214.39 | 214.39
2009-2010
5 | Margherita Water Supply Scheme in Tinsukia District | 2010-03-22 | 933.66 | 328.73 | 328.73 | 263.91 | 64.82 |  | 93.36 | 37.35 | 65%
6 | Mangaldoi Water Supply Scheme | 2010-03-22 | 1261.05 | 445.06 | 445.06 | 445.06 | 0 | 0 | 126.1 | 50.44 | 47%
7 | Improvement of Municipal Roads in Narayanpur Town in Assam | 2010-01-20 | 400 | 352.94 | 352.94 | 352.94 | 0 |  | 40 | 40 | 100%
| Sub Total:-2009-2010 |  | 2594.71 | 1126.73 | 1126.73 | 1061.91 | 64.82 | 0 | 259.46 | 127.79
2010-2011
8 | Construction of Bus Terminals at Barpeta town | 2010-10-11 | 185.96 | 129.97 | 129.97 | 129.97 | 9.3 |  | 18.6 | 18.6 | 95%
9 | Bongaigaon Town Water Supply scheme (Bongaigaon District) | 2011-01-21 | 3202.24 | 1129.46 | 338.84 | 58.32 | 280.52 | 790.62 | 320.22 | - | 30%
10 | Kharupetia Water Supply Scheme | 2011-01-21 | 1981.15 | 699.23 | 699.23 | 248.24 | 450.99 | 0 | 198.11 | 198.24 | 50%
11 | Sarupathar Piped water Supply scheme | 2011-01-25 | 1029.35 | 363.30. | 363 | 179.53 | 183.77 | 0 | 102.93 | 41.18 | 60%
12 | Improvement of Roads in Biswanath Chariali Town | 2011-02-22 | 1174.43 | 812.83 | 414.35 | 414.35 | 0 | 398.48 | 117.44 | 41.44 | 65%
13 | Construction of Multistoried Car Parking cum City Hall at Jorhat | 2010-12-13 | 1051.33 | 734.48 | 505.66 | 371 |  | 228.82 | 105.13 | 41 | 52%
| Sub Total:-2010-2011 |  | 8624.46 | 3505.97 | 2451.05 | 1401.41 | 924.58 | 1417.92 | 862.43 | 340.46
2011-2012
14 | Construction of 4 Nos. road including box culverts and pucca drainage in Lakhipur Town | 2011-12-29 | 1424.77 | 1018.76 | 799.58 | 509.58 | 290 | 219.18 | 142.47 | 56 | 60%
2012-2013
15 | Construction of road side drainage system including improvement of town roads in Nagaon town. | 2012-09-25 | 1924.5 | 692.82 | 692.82 | 692.82 | 0 |  | 192.45 | 192.45 | 47%
2013-2014
16 | Improvement and Development of Goalpara Town Road Network in Goalpara District | 2013-05-17 | 1723.85 | 1241.18 | 1241.18 | 1241.18 | 0 |  | 172.38 | 172.38 | 94%
17 | Improvement of Road Bye Lanes of Chabua Town | 2013-09-23 | 906.03 | 617.51 | 617.51 | 617.51 | 0 |  | 90.6 | 35.17 | 76%
18 | Development of Roads for Dhemaji Town | 2013-12-09 | 1198.11 | 816.22 | 816.22 | 816.22 | 0 |  | 119.81 | 0 | 80%
19 | Improvement of Drainage system of Dibrugarh Town in Assam | 2014-02-28 | 2381.48 | 857.33 | 857.33 | 857.33 | 0 |  | 238.14 | 120 | 53%
20 | Construction of Roads at Tinsukia Town | 2014-02-20 | 1460.65 | 1051.67 | 1051.67 | 1051.67 | 0 |  | 146.06 | 98 | 90%
21 | Improvement of Roads of Tinsukia Master Plan Area,Tinsukia | 2014-03-03 | 1545.74 | 556.45 | 556.45 | 556.45 | 0 |  | 154.57 | 61 | 62%
22 | Tinsukia Town Water Supply Scheme (Phase-I) | 2013-12-20 | 3582.96 | 1289.65 | 1289.65 | 1135 | 154.65 | 0 | 358.29 | 40 | 62%
23 | Tinsukia Town Water supply Scheme (Phase –II) | 2013-12-20 | 3581.25 | 1275.15 | 1275.15 | 859.5 | 415.65 |  | 358.12 | 0 | 36%
24
25
24 | Proposed Town Hall at Dibrugarh. | 2013-12-09 | 1408.17 | 506.65 | 506.65 | 506.65 | 0 |  | 140.81 | 0 | 37%
| Sub Total:-2013-2014 |  | 17788.24 | 8211.81 | 8211.81 | 7641.51 | 570.3 | 0 | 1778.78 | 526.55
2014-2015
25 | Storm Water Drainage System for Margherita Town | 2015-04-07 | 2158.48 | 777.05 | 537 | 237 | 240.05 | 0 | 215.84 | 0 | 13%
| Grand Total:- |  | 40237.43 | 18225.51 | 16711.36 | 14436.6 | 2089.75 | 1637.1 | 3768.47 | 1595.1