## WPT&BC Deptt.
NLCPR -ongoing projects : WPT&BC Department as on June, 2019
Rs. in Lakh
Sl. No. | Name of the projects | Sanction Date | Approved Cost | Release Break-up |  | Grant share recommended by T&D | Department yet to move for fund | Utilisation Break-up |  | UC submtd | UC pending | Total State share | State share recommended | Physical Progress
|  |  |  | Date | Amount |  |  | Date | Amount
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
2011-12
1 | Construction of Road with MTBT from UT Road at Dimakuchi Donbosco School to Badlapara via Kalikhola Road, Udalguri in Assam | 2011-12-14 | 620.91 | 557.91 |  | 557.91 | 0 | 446.34 |  | 446.34 | 111.57 | 62.09 | 62.09 | 83.9%
|  |  |  | 2011-12-15 | 223.17 |  |  | 2015-02-05 | 223.17
|  |  |  | 2014-02-24 | 223.17 |  |  | 2016-10-15 | 223.17
|  |  |  | 2016-12-21 | 111.57
2 | upgradation of NT road through Ramphalbil Bazar to all weather road with conversion of SPT bridges into RCC bridge(International Border Areas) in Kokrajhar District. | 2011-06-27 | 764.18 | 538.28 |  | 538.28 |  | 432.83 |  | 432.83 | 105.45 | 74.6 | 74.6 | 60%
|  |  |  | 2011-06-29 | 269.71 |  |  | 2016-07-20 | 269.71
|  |  |  | 2016-09-19 | 268.57 |  |  | 2017-08-19 | 268.57
3 | Upgradation of Road from NH-31 (C) via Serfanguri, Nepalpara, Athiabari, Ebargaon, Thaigiriguri and No. 2 Hazarikapara to Kapuragaon in Kokrajhar | 2011-12-14 | 759.7 | 540.56 |  | 540.56 | 0 | 269.79 |  | 269.79 | 270.77 | 75.21 | 61.67 | 95%
|  |  |  | 2011-12-15 | 269.79 |  |  | 2016-09-14 | 269.79
|  |  |  | 2016-11-24 | 270.77
4 | Construction of RCC Br. No. 8/1 over Saral Bhanga on Dotma Balajan Road in Kokrajhar District | 2011-12-19 | 1202.31 | 857.1 |  | 857.1 | 0 | 857.1 |  | 857.1 | 0 | 119.04 | 95.24 | 80%
|  |  |  | 2011-12-19 | 428.55 |  |  | 2017-01-12 | 428.55
|  |  |  | 2016-01-05 | 428.55 |  |  | 2017-09-12 | 428.55
5 | Construction of RCC bridge No 15/2 over river Burisuti on Patdadaha Panbari Road in Chirang District | 2012-02-21 | 719.17 | 517.8 |  | 517.8 | 0 | 517.8 |  | 517.8 | 0 | 71.91 | 28.77 | 48.5%
|  |  |  | 2014-02-21 | 258.9 |  |  | 2017-03-16 | 258.9
|  |  |  | 2017-05-04 | 258.9 |  |  | 2019-05-28 | 258.9
6 | Tamulpur Piped Water Supply Scheme in Baksa District | 2011-12-15 | 293.7 | 261.71 |  | 209.37 | 52.34 | 209.37 |  | 209.37 | 52.34 | 29.08 | 29.08 | 100%
|  |  |  | 2011-12-15 | 103.41 |  |  | 2014-05-29 | 103.41
|  |  |  | 2014-12-19 | 105.96 |  |  | 2016-10-15 | 105.96
|  |  |  | 2017-06-27 | 52.34
| Total 2011-12 |  |  |  | 3273.36 | 3221.02 | 52.34 |  |  | 2733.23 | 540.13 |  | 351.45
2012-2013
7 | Construction of Road from Rongaichara to Bhola Bazar in Baksa District. | 2012-12-26 | 365.59 | 131.55 |  | 131.55 | 0 | 131.55 |  | 131.55 | 0 | 35.49 | 35.49 | 40%
|  |  |  | 2012-12-27 | 131.55 |  |  | 2018-07-12 | 131.55
8 | Conversion of washed out STP Bridge No. 2/1 over river Hell into RCC Bridge on Shialmari Moinaguri Road in Kokrajhar District | 2012-12-28 | 1967.53 | 1416.62 |  | 1416.62 | 0 | 1416.62 |  | 1416.62 | 0 | 196.75 | 126.38 | 86%
|  |  |  | 2012-12-28 | 708.15 |  |  | 2015-06-19 | 708.15
|  |  |  | 2015-09-14 | 708.47 |  |  | 2017-11-02 | 708.47
| Total 2012-13 |  | 2333.12 |  | 1548.17 | 1548.17 |  |  |  | 1548.17 | 0 |  | 161.87
2013-2014
9 | Construction of Road from Paoriputa to Natun Panbari with black topping and construction of RCC Bridge over river Pasnai in Udalguri Rural Road Division (Length - 2.30 Km) in Udalguri District of Assam | 2013-05-17 | 767.94 | 552.65 |  | 552.65 | 0 | 276.45 |  | 276.45 | 276.2 | 76.37 | 49.9 | 67%
|  |  |  | 2013-05-23 | 276.45 |  |  | 2016-09-07 | 276.45
|  |  |  | 2016-09-19 | 276.2
10 | Improvement/Upgradation of Mangaldoi Bhutiachang Samrang road from CH-47722M to CH-48292 and fromCH-50000 to CH-62500M including cross drainage works in Udalguri District | 2013-06-11 | 2991.66 | 2691.92 |  | 2691.92 | 0 | 2615.02 |  | 2615.02 | 76.9 | 299.1 | 257.228 | 100%
|  |  |  | 2013-06-24 | 1076.9 |  |  | 2017-07-05 | 1076.9
|  |  |  | 2015-12-18 | 1076.64 |  |  | 2016-10-15 | 1076.64
|  |  |  | 2016-11-10 | 461.48 |  |  | 2018-10-05 | 461.48
|  |  |  | 2017-10-13 | 76.9
11 | Improvement of road from Budura to Parbhuchuba Dimakuchi PWD Road at Batabari via Khasiachuba, Barangabari in Udalguri District | 2013-07-02 | 1109 | 798.47 |  | 798.47 | 0 | 798.43 |  | 798.43 | 0.04 | 110.9 | 110.899 | 76%
|  |  |  | 2013-07-04 | 398.85 |  |  | 2015-04-10 | 398.85
|  |  |  | 2015-09-16 | 399.62 |  |  | 2017-09-18 | 399.58
12 | Const of RCC Br. No.9/8 over Laska on Dauluguri Dotma road in Kokrajhar District | 2013-07-02 | 175.03 | 126.01 |  | 126.01 | 0 | 126.01 |  | 126.01 | 0 | 17.5 | 17.5 | 52
|  |  |  | 2013-07-05 | 62.9 |  |  | 2015-04-07 | 62.9
|  |  |  | 2017-03-14 | 63.11 |  |  | 2018-05-07 | 63.11
13 | Improvement of Kadamtal Nikashi Road from Kuchighar to Bhaluk donga in Baksa Diastrict | 2013-10-21 | 415.75 | 299.33 |  | 299.33 | 0 | 299.33 |  | 299.33 | 0 | 41.57 | 20.8 | 70%
|  |  |  | 2013-10-22 | 149.67 |  |  | 2016-09-07 | 149.67
|  |  |  | 2016-09-19 | 149.66 |  |  | 2019-03-01 | 149.66
14 | Improvement of Road from Khairabari to Jamuguri in Udalguri District | 2013-10-28 | 1329.18 | 478.3 |  | 478.3 |  | 478.3 |  | 478.3 | 0 | 132.91 | 53
|  |  |  | 2013-10-31 | 478.3 |  |  | 2018-07-18 | 478.3
15 | Improvement of Road from Barama-Dhamdhama-Tamulpur under Non Lapsable Central pool of Resources in Baksa District | 2014-03-03 | 846.55 | 603.43 |  | 603.43 | 0 | 603.43 |  | 603.43 | 0 | 83.81 | 83.81 | 97
|  |  |  | 2014-06-11 | 304.76 |  |  | 2016-07-01 | 304.76
|  |  |  | 2016-08-02 | 298.67 |  |  | 2017-03-07 | 298.67
16 | College of Nursing at Kokrajhar in Kokrjhar District | 2013-05-17 | 1427.21 | 1027.43 |  | 735.02 | 292.41 | 517.79 |  | 517.79 | 509.64 | 142.69 | 78.486 | 55%
|  |  |  | 2013-05-23 | 517.79 |  |  | 2017-06-15 | 517.79
|  |  |  | 2017-07-10 | 509.64
17 | Conversion of SPT Bridge No. 10/1, 12/3, 14/2 and 16/1 into RCC Bridge on metd. Kokrajhar Bahalpur road in Kokrajhar District | 2013-09-23 | 698.94 | 622.82 |  | 622.82 | 0 | 622.82 |  | 622.82 | 0 | 69.2 | 55.36 | 98%
|  |  |  | 2013-09-24 | 251.35 |  |  | 2015-05-14 | 251.35
|  |  |  | 2016-02-25 | 246.91 |  |  | 2017-01-12 | 246.91
|  |  |  | 2017-06-20 | 124.56 |  |  | 2018-08-29 | 124.56
| Total 2013-2014 |  |  |  | 7200.36 | 6907.95 | 292.4 |  |  | 6337.58 | 862.78 |  | 726.983
2014-2015
18 | Improvement of Sujit Narzary road from Tihu Chowk to Barimakha via Belguri Pathar in Baksa District | 2015-02-24 | 3135.82 | 2257.78 |  | 2257.78 | 0 | 2257.78 |  | 2257.78 | 0 | 313.58 | 313.582 | 77%
|  |  |  | 2015-02-24 | 1128.89 |  |  | 2016-09-14 | 1128.89
|  |  |  | 2016-09-21 | 1128.89 |  |  | 2017-07-28 | 1128.89
19 | Construction of Road from Borobazar to Gumergaon via Chawdhuripara in Chirang District | 2014-12-29 | 1668.39 | 1201.2 |  | 1201.2 | 0 | 1201.2 |  | 1201.2 | 0 | 166.83 | 166.839 | 56%
|  |  |  | 2014-12-19 | 600.62 |  |  | 2016-11-29 | 600.62
|  |  |  | 2016-12-21 | 600.58 |  |  | 2018-03-12 | 600.58
20 | Met & Bt road from Jaipur NH-31C to Amguri JD Road (Dumbruguri to Amguri) including construction of RCC Bridges & Culvertsin in Kokrajhar District | 2014-12-24 | 1471.47 | 1057.4 |  | 1057.4 | 0 | 1057.2 |  | 1057.2 | 0.2 | 146.57 | 146.578 | 74%
|  |  |  | 2014-12-29 | 529.72 |  |  | 2016-06-07 | 529.72
|  |  |  | 2016-09-19 | 527.68 |  |  | 2018-08-09 | 527.48
| Total 2014-2015 |  |  |  | 4516.38 | 4516.38 |  |  |  | 4516.18 | 0.2 |  | 626.999
2015-2016
21 | Construction of road from Bijni Subhaijhar road at village Nayapara No.2 to Kathalguri via Sanyasiguri including construction of RCC bridge No.1/2 over river Chara in Chirang District, in Assam. | 2015-06-22 | 395.84 | 284.7 |  | 284.7 | 0 | 142.3 |  | 142.3 | 142.4 | 39.59 | 39.59 | 65.71
|  |  |  | 2015-06-22 | 142.3 |  |  | 2017-08-19 | 142.3
|  |  |  | 2017-09-20 | 142.4
2016-2017
22 | Construction of road from Subhaijhar to Uttar Ballamnguri via Kumarshali at Bijni in Chirang District under NLCPR in Assam | 2017-02-22 | 1434.88 | 2017-06-20 | 516.54 | 516 | 0.54 | 2018-06-12 | 450 | 450 | 66.54 | 143.488 | 143.488 | 40
2017-2018
23 | Impovement of Udalguri Sapekhaity Bhakatpara Road in Udalguri Rural Road Division” in Udalguri District of Assam under NLCPR. | 2017-05-11 | 3103.05 | 2017-08-17 | 1117.09 | 1117.09 | 0 | 2018-10-29 | 1117.09 | 1117.09 | 0 | 310.38 | 310.3 | 40
| GRAND TOTAL : (WPT&BC) |  | 27663.8 |  | 18456.6 | 18111.31 | 345.28 |  |  | 16844.55 | 1612.05 |  | 2360.68