## Sheet1
ANNEXURE-I
Proposals submitted under Rs. 250.00 crore Additonal BTC Package
Rs. In lakh.
Sl. No. | Name of project | Estimated cost | Date of retention by DoNER
1 | 2 | 3 | 4
1 | Setting up of IT Park-Kokrajhar | 2594.21 | 23-11-09
2 | Establishment of Sports Complex at Mushalpur in the Baska district | 500 | 23-11-09
3 | Upgradation of Sports Complex at Kajalgaon in Chirang district | 500 | 23-11-09
4 | Setting up of Food Processing Plant at Karigaon,Kokrajhar district under Agriculture sector | 996 | 23-11-09
5 | Construction of Cold Storage at Barama, Baksa Dist. | 890 | 23-11-09
6 | Setting up of Integrated Agro-Processing park at Lalpool, Udalguri Dist. | 907 | 23-11-09
7 | Setting up pf Model Dairy, Fishery, Horticulture,Poultry Farm Training center at Kokilabari, Baksa Dist | 1146 | 23-11-09
8 | To enhance the existing facilities in Veterinary Hospital, Titaguri, Samthaibari & Udalguri. | 900 | 23-11-09
9 | Const. Of RCC bridge over Gurufella river on Gossaigaon –Sapatgram road, Kokrajhar Dist. | 792 | 23-11-09
10 | Const. Of RCC bridge over Gongia river on Dotma-Bhawraguri. Road, Kokrajhar Dist. | 800 | 23-11-09
11 | Const. Of RCC bridge over Puthimari river at Dolongghat(Dhulabari, Baksa Dist. | 800 | 23-11-09
12 | Bodoland Bhawan at Dwaraka, New Delhi | 915 | 23-03-10
13 | Integrated Textile Park at Mashalpur, Baksa. | 4100 | 23-03-10
14 | Construction of RCC 4 storied Provision Building for Research and Development of Bodo language at Kokrajhar University campus, Balagaon. | 295.81 | 23-03-10
15 | Improvement of Udalguri Tamulpur road ( up to Panery) | 3000 | Retention awaited
16 | Impt. Of road from Bashbari to Gossaigaon via Dingdingna,Kokrajhar Dist. | 2500 | Retention awaited
17 | Impt. Of widening of Bishmuri,Saralpara Sarbhog road, Kokrajhar Dist. | 2679 | Retention awaited
18 | Const. Of road from Bhergaon to Barnadi Wild Life Sanctuary via Pachimpatala Baragajuli PWD road, Udalguri Dist. | 954 | Retention awaited
19 | Impt. Of Rowta Station Feder road, Udalguri Dist. | 133 | Retention awaited
20 | Const. Of road from Sapkhaity to Bhakatpara road, Udalguri | 933 | Retention awaited
21 | Const. Of road from Mashalpur Lama Mandir to Nikashi including two numbers bridge,Baksa Dist. | 420 | Retention awaited
22 | Const. Of Khanda road from Dawdhara to Doomni via Nawputa, Baksa Dist. | 1075 | Retention awaited
23 | Const. Of Keshab Nagar to Doomni via Golagaon PHC road Baksa Dist. | 1250 | Retention awaited
24 | Impt. Of Tangala Deor road, Udalguri Dist. | 1953 | Retention awaited
25 | Border trade Centre at Dadgiri, Chirang | 600 | Retention awaited
26 | Boder trade Centre at NK Daranga, Baksa | 600 | Retention awaited
27 | Construction of 100 Bedded Civil Hospital at Salbari | 3000 | Retention awaited
28 | Contn. Of Gurudev Kalicharan Brahma 100 Bedded Civil Hospital at Parbatjhora, Kazigaon in Kokrajhar District | 3000 | Retention awaited
29 | Establishment of District Library at Musalpur in Baksa District | 500 | Retention awaited
30 | Establishment of Sub-Divisional Library at Parbatjhora, Kazigaon | 500 | Retention awaited
31 | Establishment of Sub-Divisional Library at Bhergaon in Udalguri | 500 | Retention awaited
32 | Constn. Of Inter-State Inter State bus terminus at Khargoan in Kokrajhar | 3000 | Retention awaited
33 | Const. Of Driving Training Institute at Khargaon in Kokrajhar | 467 | Retention awaited
34 | Constn. Of Inter-State Inter State bus terminus at Musalpur in Baksa District. | 1000 | Retention awaited
35 | Labour Welfare Training Institute cum Reserch Centre at Chandrapara in Kokrajhar District. | 700 | Retention awaited
36 | Const. Of Industrial Estate under Kokrajhar District | 500 | Retention awaited
37 | Const. Of District Museum at Musalpur in Baksa District | 125 | Retention awaited
38 | Const. Of District Museum at Kajolgaon in Chirang District | 125 | Retention awaited
39 | Const. Of Auditorium with Recording Studio at Kokrajhar | 1100 | Retention awaited
40 | Integrated Cluster Development project on Sericulture at Kokrajhar | 510 | Retention awaited
41 | Improvement of road from Kumarikata to Siddhinathpur via Kauli in Baksa District | 1997.02 | Retention awaited
42 | Const. Of RCC bridge over river Agrang on Hazua Bhuyapara road near Borobazar | 325 | Retention awaited
43 | Const. Of major RCC bridge over river Anglisinga on KK Boro road near Vehguri . | 415 | Retention awaited
44 | Const. Of RCC brige over river Balti near Baghmara chowk on Kumarikata Kauli to Guwabari Bazar. | 1088 | Retention awaited
45 | Const. Of road from Tangabari via Hulma gaon to Domgaon Bazar | 720 | Retention awaited
46 | Const. Of road from Bhodiaguri Pub Domgaon via Rani Sundri to Bengtul road | 881.75 | Retention awaited
47 | Const. Of NH-31 ( C) at Bamungaon via Jaoliabari road | 326 | Retention awaited
48 | Improvement of roadfrom NH-31 ( C) at UN Brahma Academy to Monglagaon via Saljhora Muslim Basti | 240 | Retention awaited
49 | Const. Of RCC bridge No 1/1 over river Duloni & RCC bridge No 11/1, 11/3 & 16/1 & const. Of road portion from Chowdhuripara to Dagarpara including widening & strengthening of road near Bijni Town on Bini Subhaijhar road | 1377.53 | Retention awaited
50 | Const. Of road from Boro Bazar to Ulubari via Bagargaon including RCC bridge & cross drainage in Chirang District | 1700 | Retention awaited
51 | Const. Of road from Palengbari to Bijni via Alukhanda including RCC bridge in Chirang district. | 2199.5 | Retention awaited
52 | Met.& Bt. Of road from Lalmati to Monglajhora | 600 | Retention awaited
53 | Met.& Bt. Of road from Rupshi to Ponorgaon | 725 | Retention awaited
54 | Met. & Bt. Of road from Dingdanga to Anandapur | 440 | Retention awaited
55 | Widening & strengthening of Kokrajhar Ramfalbil road | 280 | Retention awaited
56 | Widening & strengthening of Saraikhosra to Basugaon Road | 457 | Retention awaited
57 | Const. Of road from Nepali Basti Chowk to Dhopguri via No1Nasansali road | 771.28 | Retention awaited
58 | Widening & stregthening of Charaikhola Basugaon rod | 350 | Retention awaited
59 | Upgradation & Modernization of Liquid Nitrojen plant ( LN2) at ICDP, Kokrajhar with the procurement of new plant machineries for Liquid Nitrojen production for boosting up of artificial imsemination activities | 248.13 | Retention awaited
60 | Repairing/Renovation/Reconstruction of dilapidate veterinari institutions in the field of A.H. & Vety. Deptt. under BTC. | 250 | Retention awaited
| Total | 62651.23

## Status of project
Status of retained project under Additional BTC package ( Rs. 250.00 crore)
Rs. In lakh
Sl No. | Name of project | Sanctioned Amount | Fund released by DoNER | Remarks
1 | 2 | 3 | 4 | 9
1 | Setting up of IT Park-Kokrajhar | 2594.21 |  | Awaited approval of SLSC, DPR, T.E.E.R.and recommendation of SLSCetc from WPT&BC Dept.
2 | Establishment of Sports Complex at Mushalpur in the Baska district | 500 |  | Dropped, awaited retention of alternative proposal from M/DoNER.
3 | Upgradation of Sports Complex at Kajalgaon in Chirang district | 500 | 250 | Requested WPT&BC to submit proposal for recommendation for release of fund on 02-02-11.Proposal awaited.
4 | Setting up of Food Processing Plant at Karigaon,Kokrajhar district under Agriculture sector | 996 |  | Awaited approval of SLSC, DPR, T.E.E.R.and recommendation of SLSCetc from WPT&BC Deppt.
5 | Construction of Cold Storage at Barama, Baksa Dist. | 890 | 445 | Requested WPT&BC to submit proposal for recommendation for release of fund on 02-02-2011. Proposal awaited.
6 | Setting up of Integrated Agro-Processing park at Lalpool, Udalguri Dist. | 907 | 453.5 | Requested WPT&BC to submit proposal for recommendation for release of fund on 02-02-2011. Proposal awaited.
7 | Setting up pf Model Dairy, Fishery, Horticulture,Poultry Farm Training center at Kokilabari, Baksa Dist | 1146 |  | Awaited approval of SLSC, DPR, T.E.E.R.and recommendation of SLSCetc from WPT&BC Department.
8 | Enhancement of existing facility in Veterinary Hospital at Titaguri (Kokrajhr), Samthaibari (Chirang) and Bomagaon in Udalguri District. | 901.9 | 450.9 | WPT&BC Department to submit proposal for release of fund.
9 | Const. Of RCC bridge over Gurufella river on Gossaigaon –Sapatgram road, Kokrajhar Dist. | 792 | 396 | Requested WPT&BC to submit proposal for recommendation for release of fund on 02-02-2011. Proposal awaited.
10 | Const. Of RCC bridge over Gongia river on Dotma-Bhawraguri. Road, Kokrajhar Dist. | 800 | 400 | Requested WPT&BC to submit proposal for recommendation for release of fund on 02-02-2011. Proposal awaited.
11 | Const. Of RCC bridge over Puthimari river at Dolongghat(Dhulabari, Baksa Dist. | 800 | 400 | Requested WPT&BC to submit proposal for retention on 02-02-2011. Proposal awaited.
12 | Bodoland Bhawan at Dwaraka, New Delhi | 909.83 | 454.92 | Requested WPT&BC to submit proposal for recommendation for release of fund on 02-02-2011. Proposal awaited.
13 | Proposed Integrated Textile Park at Kharuajan, Mashalpur, Baksa. | 4100 | 2050 | WPT&BC Department to submit proposal for release of fund to P&D Department.
14 | Bodo Language Research and Development Centre for Gauhati University, Kokrajhar. | 295.81 | 147.9 | WPT&BC Department to submit proposal for release of fund to P&D Department.
15 | Improvement of road road from Bashbari to Gossaigaon via Dingdinga, Kokrajhar District (D.K. Road) | 2500 |  | WPT&BC/BTC was requested on 10-08-2011 to prepare DPR and get approval of SLSC.
16 | Improvement and widening of Bishmuri Saralpara Sarbhog Road | 2679 |  | WPT&BC/BTC was requested on 10-08-2011 to prepare DPR and get approval of SLSC.
17 | Met. And Blacktopping road from Lalmati to Manglajhora | 600 |  | WPT&BC/BTC was requested on 10-08-2011 to prepare DPR and get approval of SLSC.
18 | Improvement of Rowta Station Feeder Road | 133 |  | WPT&BC/BTC was requested on 10-08-2011 to prepare DPR and get approval of SLSC.
19 | Construction of road from Borobazar to Ulubari via Bagargaon including RCC Bridge & Cross Drainage in Chirang District. | 1700 |  | WPT&BC/BTC was requested on 10-08-2011 to prepare DPR and get approval of SLSC.
20 | Construction of Khanda Road from Dawdhara to Domni via Nawputa. | 1075 |  | WPT&BC/BTC was requested on 10-08-2011 to prepare DPR and get approval of SLSC.
| total | 24819.75 | 5448.22

## addi. BTC
Status of projects under Rs 250 Crore Additional BTC Package as on March/15
| Name of sanctioned project | Approved cost ( Rs in crore) | Fund released by DoNER ( Rs in crore) | Utilization Certificate submitted to DoNER | Physical progress in %
1 | Upgradation of Sports Complex at Kajalgaon in Chirang district | 5 | 2.5 | 2.55 | 100%
2 | Construction of Cold Storage at Barama, Baksa Dist. | 8.9 | 4.45 | 3.68 | 55%
3 | Setting up of Integrated Agro-Processing park at Lalpool, Udalguri Dist. | 9.07 | 8.46 | 4.53 | 65%
4 | Enhancement of existing facility in Veterinary Hospital at Titaguri (Kokrajhr), Samthaibari (Chirang) and Bomagaon in Udalguri District. | 9.02 | 4.51 | 4.87 | 64%
5 | Const. Of RCC bridge over Gurufella river on Gossaigaon –Sapatgram road, Kokrajhar Dist. | 7.92 | 3.96 | 7.62 | 100%
6 | Const. Of RCC bridge over Gongia river on Dotma-Bhawraguri. Road, Kokrajhar Dist. | 8 | 4 | 5.69 | 100%
7 | Const. Of RCC bridge over Puthimari river at Dolongghat(Dhulabari, Baksa Dist. | 8 | 4 | 2.6 | 38%
8 | Bodoland Bhawan at Dwaraka, New Delhi | 9.1 | 4.55 | 7.47 | 100%
9 | Proposed Integrated Textile Park at Kharuajan, Mashalpur, Baksa. | 41 | 20.5 | 16.39 | 38%
10 | Bodo Language Research and Development Centre for Gauhati University, Kokrajhar. | 2.95 | 1.48 | 2.22 | 100%
11 | Setting up of Model Dairy, Fishery,Horticulture and Poultry Farm training Centre | 11.46 | 5 | 2.31
12 | Construction of Khanda Road from Dadhara to Doomni via Nawputa | 10.75 | 10.75 | 10.3 | 82%
13 | Improvement of Road from Bashbari to Gossaigaon via Ding Dinga | 25 | 10.91 | 6.82 | 45%
14 | Improvement of Bishmuri Saralpara Sorbhog Road | 26.79 | 11.69 | 11.07 | 69%
15 | Metalling and Blacktopping of Road from Lalmati to Mangaljhora | 6 | 2.62 | 0.06
16 | Construction of Borobazar Ulubari Road via Bagargaon including RCC bridge & cross drainage in Chirang | 18.69 | 18.29 | 12.5 | 68%
17 | Improvement of Rowta Station Feeder Road in Udalguri District | 1.52 | 0.62 | 1.09 | 100%
18 | Setting up of Information Technology Park at Kokrajhar | 25.84 | 12.97
19 | Setting up of Food Processing Plant at Karigaon | 9.96
20 | Construction of Sports Complex at salbari | 5 | 2.5
21 | Construction of Road from Ambagaon to Kundarbil, Udalguri | 12.75 | 6.38
22 | Construction of Road from Kumarikata to nayabasti, Baksa | 12.79 | 6.4
|  | 275.61 | 146.54 | 101.77
Note on C22: wipro:

## BTC pack
Status of projects under BTC package (Rs. 500 crore)as on Feb/15
Sl No | Name of Projects | Approved cost ( Rs in crore) | Fund released by GoI ( Rs in crore) | Utilization Certificate submitted to M/DoNER | Physical Progress in %
1 | Improvement of Dhamdhama Tupalia Subanthaka(DTS) Road for 2004-05 | 13.72 | 13.72 | 13.32 | 100%
2 | Improvement of Kaurbaha Nagrijuli Road for 2004-05 | 14.5 | 14.45 | 14.08 | 100%
3 | Construction of Road from NH-31 at Barama to Masalpur for 2004-05 | 14.43 | 13.93 | 14.01 | 100%
4 | Improvement of Jalah Rupahi Saudarbhitha Gobardhan Road, Baksa for 2004-05 | 10 | 10 | 9.7 | 100%
5 | Improvement of North Kajalgaon Bengtol Shantipur Road for 2004-05 | 8.1 | 8.1 | 7.86 | 100%
6 | Improvement & upgradation of Kashikotra to Basugaon Road for 2004-05 | 5.51 | 5.51 | 5.34 | 100%
7 | Improvement of Sundari- Vidyapur via Kakragaon Road for 2004-05 | 9.21 | 9.21 | 8.95 | 100%
8 | Improvement of North Kajalgaon Dangtol Road for 2004-05 | 5.93 | 5.93 | 5.92 | 100%
9 | Construction of 100 bedded hospital at Kajalgaon for 2004-05 | 38.52 | 38.52 | 38.52 | 100%
10 | Widening & strengthening of Fakiragram Serfanguri Road for 2004-05 | 20.49 | 20.49 | 19.47 | 100%
11 | Metalling and Blacktopping of Narabari Dawkibari Road for 2004-05 | 15.95 | 15.95 | 15.38 | 100%
12 | Improvement of Bhowraguri Kachugaon Road, Kokrajhar for 2004-05 | 23.73 | 23.73 | 22.46 | 100%
13 | Metalling & Blacktopping of Gossaigaon to Saraibil Road and conversion of SPT bridge to RCC for 2004-05 | 19.39 | 19.39 | 17.92 | 100%
14 | Kokrajhar Water Supply Scheme for 2004-05 | 23.12 | 23.12 | 22.99 | 100%
15 | Construction of Bodofa Cultural Complex at Kokrajhar for 2004-05 | 18.44 | 18.44 | 18.26 | 100%
16 | Improvement of Udalguri Bhakatpara Road Bhairguri, Udalguri for 2004-05 | 4.44 | 4.44 | 4.33 | 100%
17 | Improvement of Barnagaon Pakribari Road , Udalguri for 2004-05 | 1.5 | 1.5 | 1.46 | 100%
18 | Improvement of Kalaigaon Kundarbil Road, Udalguri for 2004-05 | 1.32 | 1.32 | 1.29 | 100%
19 | Champamati Irrigation Project for 2005-06 | 43.85 | 43.85 | 43.85 | 100%
20 | Renovation/ Reconstruction of RNB Civil Hospital at Kokrajhar for 2005-06 | 7.58 | 7.58 | 7.27 | 100%
21 | Subankhata Water Supply Scheme for 2005-06 | 3.28 | 3.28 | 2.55 | 100%
22 | Sukla Irrigation Project for 2005-06 | 8.13 | 8.13 | 8.13 | 100%
23 | Goreswar to Khairabari Road for 2005-06 | 6.57 | 6.57 | 6.38 | 100%
24 | Bhergaon-Cheuni-Khagrabari- Dimakuchi Road for 2005-06 | 1.32 | 1.32 | 1.31 | 100%
25 | Lailongpara- Kopati Road for 2005-06 | 1.31 | 1.31 | 1.31 | 100%
26 | Khowrang Mohanpur Road for 2005-06 | 2.5 | 2.5 | 2.46 | 100%
27 | Chapaguri- Khagrabari Road for 2005-06 | 6.3 | 6.3 | 6.25 | 100%
28 | Tulsijhyora Kailamaila Road for 2005-06 | 9 | 9 | 8.88 | 100%
29 | Bijni – Panbari Road for 2005-06 | 15.59 | 15.59 | 15.19 | 100%
30 | Gossaigaon to Kajigaon via Bhumka Tipkai Road for 2005-06 | 11 | 11 | 10.82 | 100%
31 | Construction of Cold Storage at Udalguri District for 2005-06 | 4.14 | 4.14 | 4.14 | 100%
32 | Construction of Cold Storage at Kokrajhar District for 2005-06 | 4.14 | 4.14 | 4.14 | 100%
33 | Construction of North East Gateway Bus Terminus at Srinwgai, Gossaigaon | 1.44 | 1.44 | 1.4 | 100%
34 | Improvement of Tihu Doomni Road leading to Indo-Bhutan foot hill for 2005-06 | 9.95 | 9.95 | 9.66 | 100%
35 | Improvement of Khairabari MPK Road Andherighat to Harisinga via Bhergaon for 2005-06 | 26.5 | 26.5 | 25.71 | 100%
36 | Construction of Kasikotra Bamungaon Bengtol Road for 2005-06 | 11.69 | 11.69 | 10.36 | 100%
37 | Bheragaon Piped Water Supply scheme for 2006-07 | 2.47 | 2.46 | 2.41 | 100%
38 | Udalguri Piped Water Supply Scheme for 2006-07 | 5.34 | 5.33 | 5.23 | 100%
39 | Uttarpar Piped water Supply Scheme for 2006-07 | 8.64 | 8.64 | 8.56 | 100%
40 | Conservation of SPT bridge 20/1 over river Gongia into RCC bridge on Gossaigaon Sapatgram Road for 2008-09 | 10.83 | 5.41 | 10.83 | 100%
41 | Strengthening of 11 KVHT & LT Line with 12 meter Steel Tubular Pole including illuminisation of Kokrajhar Town. For 2008-09 | 5.2 | 2.5 | 3.62 | 100%
42 | Improvement of Jalah to Kumarikata Road including 2 bridges over river Kaldia & Diring for 2008-09 | 21.21 | 10.61 | 12.1 | 75%
|  | 476.28 | 456.99 | 453.82

## Sheet3
Note on C19: wipro: