## Sheet1
DPRs/MDPRs etc. submitted and pending MDPRs etc. of the retained projects (as on 31.3..2015)
| Name of the District | Name of the Deptt | Year of retention | Name of the project | Estt. Cost (in cr.) | Original DPRsubmitted /notsubmitted to DONER | RDPR submitted/ not submitted to DONER | Remark
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
1 | Karbi Anglong | Hill Areas | 2007-08 | Kaziranga from Sky, Kohora Assam (Karbi Anglong) | 3.52 | submitted | not submitted | HAD requested for copy of concept paper alongwith clarification vide PDP(PP64/08/24) on 18.06.2010.reply awaited
2 | Karbi Anglong | Hill Areas | 2007-08 | Development of Water body at Kohora (Kaziranga) Karbi Anglong | 2.93 | submitted | not submitted | clarification sought by DoNER forwarded to Deptt. vide PDP(PP) 8/2008/40 dtd. 21.10.2011.Reply awaited
3 | Udalguri | WPT&BC | 2007-08 | Bodoland Institute of Information technology at Udalguri | 10 | submitted | submitted | MDPR sent to MDONER on005.02.2014
4 | Kamrup(M) | Cultural Affairs | 2007-08 | Construction of 800 capacity Auditorium of Srimanta Sankaradeva Kalakshetra.(Kamrup Dist.) | 15.18 | submitted | not submitted | MDPR submitted by CA Deptt. returned on 02.02.09 for correction.MDPR resubmitted returned forcertain correction on 16.06.2010. information awaited from Cultural Affairs Dept.
5 | cachar | NERAMAC | 2007-08 | Setting up of Multi-Fruit processing Plant at Silchar (Cachar Dist.) | 18.1 | submitted | not submitted | . a Committee hasapproved of rate for procurement of machines as advised by DoNER . NERAMAC yet to submit reply to M/DONER
6 | Kamrup(M) | Education(H) | 2007-08 | Infrastructure for Krishna Kanta Handique Open University | 12.35 | submitted | not submitted | clarification saught by DoNER forwarded to M/DoNEr vide letter No.PDP(PP)58/2009/30 dtd. 4.08.2012.M/DONEr requested to depute an engineer to meet the observations on 25.01.2013. | Deptt.
7 | Kamrup(M) | Education(H) | 2007-08 | Infrastructure Development of Girls Polytecnic Guwahati | 2.12 | Submitted | not submitted | clarification saught by DoNER sent to Deptt. vide letter No.PDP(PP)36/2008/36 24.4.2013. Reply awaited from Deptt | Deptt.
8 | Jorhat | UDD | 2008-09 | Improvement of Drainage System in Titabar Town | 2.08 | Submitted | not submitted | clarification saught by DoNER on DPR. Dept. was requested on 23.08.12.Awaited from Dept.Awaited from UDD | R.DAS
9 | Jorhat | Education(H) | 2008-09 | Modernisation and Augmentation of Infrastructure of H.R.H. Prince of Wales Institute of Engineering & Technology, Jorhat | 2.75 | Submitted | not submitted | MDPR forwarded toM/DONER on 09.10.2012 M/DONEr sought clarification again on 15.01.2013. Dept. was requested vide PDP(PP)66 2008 /9.dtd.28.01.2013.MDPR awaited
10 | Karimganj | PWD | 2008-09 | Construction of Road from NH-44 to Kotamoni via Korikhai (Karimganj Rural Road Division) | 20.54 | Submitted | Submitted | MDPR Sent to DONER vide PDP(PP)8/2008/9 dtd. 29.03.2010
11 | Kamrup | Education(H) | 2008-09 | Improvement of Infrastructure of Assam Engineering College at Jalukbari | 12 | submitted | not submitted | Deptt. requested to comply with the observation on MDPR as sought by DONER vide PDP(PP)67/2008/20 datd 07.05.2013
12 | Udalguri | WPT&BC | 2008-09 | Construction of proposed Stadium at Udalguri in Udalguri District | 5 | Submitted | Submitted | MDPR sent to M/DONER vide PDP(PP)10/2009/27 dated 05.2.2014 |  | Deptt
13 | Lakhimpur | PWD | 2008-09 | Construction of RCC Bridge No. 4/1, 6/1,10/1 & 14/1 on Dhakuakhana to Dhemaji Road via Machkhuwa under Lakhimpur State Road Division | 6.98 | Submitted | submitted | MDPR forwarded to DONER vide PDP (PP) PWD 21/2009/7 Dtd. 06.07.2013 | PATHAK
14 | Kamrup | Power | 2008-09 | Construction of new 33/11 KV S/S at Chirakhundi, Rangia | 2.22 | Submitted | not submitted | Deptt .was requested to furnish a certificate regarding provision of enhanced cost from own resources or to limit the cost to the tune of DONER retained cost
15 | Karimganj | PWD | 2008-09 | Construction of RCC Bridge No. 1/1 over River Longa with approaches at Balipipla (Karimganj Rural Road Division) | 4.2 | Submitted | submitted | carification forwarded to DONER videPDP(PP)PWD90/2008/12 dtd. 23.02.2010 . | Updated on 12.08.14
16 | Golaghat | PWD | 2008-09 | Construction of RCC Bridge No.5/1 on chabukdhara Ali over River Kakodonga (Golaghat Rural Road Division) | 3.38 | Submitted | not submitted | PWD has requested to drop the project | NOT INCLUDED IN I.18.2015 status
17 | Golaghat | PWD | 2008-09 | Construction of RCC Bridge No. 3/6 over river kakodonga on U/M Bahikhowa Ghat Ali (Golaghat Rural Road Division | 3.42 | Submitted | submitted | DoNER sought clarification on MDPR ,forwarded to DONER vide PDP(PP)PWD8/2009/20 dtd 28.07..2013.
18 | Lakhimpur | PWD | 2008-09 | Construction of RCC Bridge No.1/1, 3/1, 5/1 on Dhemaji (Bordoloni) to Sibsagar Road under Lakhimpur State Road Division | 8.99 | submitted | submitted | MDPR forwarded to DONER vide PDP (PP)PWD 22/2009/9 dated 11.01.2012 |  | DONER
19 | Nagaon | PWD | 2008-09 | Construction of RCC Bridge No. 8/1 on Rupahi Puranigudam Chapanalla Road (Ng – 8) under Nagaon State Road Division Chapanalla Road (Ng – 8) | 3.09 | Submitted | not submitted | Clarification sought by M/DONEr. forwarded to PWD on 12/2/14. reply awaited . |  | DONER
20 | NC Hills | Hill Areas | 2008-09 | Improvement of Nayapur Dayangmukh Road from Km 0/0 with Granular Sub-base, W.B.M.S., S.D.B.C. etc. and Reconstruction of weak and narrow culverts including bridging the missing link of SPT Bridge No. 7/1 with new RCC Bridge (PWD Road Haflong Road Division) | 4.97 | Submitted | submitted | MDPR sent to DONER vide PDP(PP)62/2008/27 dtd. 5.6.2013 |  | DONER
21 | Karbi Anglong | Hill Areas | 2008-09 | Construction of RCC Bridge No. 67/1 on Kherani Rongpongbong Road (KR Road) over River Amreng | 5 | Submitted | submitted | MDPR sent to M/DONERron 14.08.2014 |  | HAD
22 | Kokrajhar | WPT&BC | 2008-09 | Construction of RCC Bridge No. Dotoma Patgaon Road over Longa River | 6.66 | Submitted | Submitted | clarification on MDPR ,forwarded to DONER vide PDP(PP)24/2009/29 dated 10.03.2014 | udt
23 | Dibrugarh | Tourism | 2008-09 | Development of Eco Tourism at Jeypore | 3.59 | Submitted | not submitted | DoNER saught Land avl. Certificate & forest Clearance certificate. Dept was requested vide PDP(PP)/9/2009/21 dtd.24.10.2013. Er |  | Dept
24 | Dibrugarh | Sports & YW | 2008-09 | Improvement & Modernisation of Dibrugarh Indoor Stadium | 3.5 | Submitted | Not submitted | As per request of M/DoNER, PW Deptt. has been asked to submit details of drawings on 01.08.2012 | SPORTS &YW
25 | Dibrugarh | Sports & YW | 2008-09 | Development of Khanikar Sports Complex, Dibrugarh | 15 | Submitted | Not submitted | DONER sought clarification on DPR , forwarded to Deptt. vide PDP(PP)89/2010/8 dated 21.08.2012 | SPORTS &YW
26 | Nalbari | Sports & YW | 2008-09 | District Sports Complex at Nalbari | 8 | Submitted | Not submitted | DONER requested to prepare DPR in latest SOR. MDPR awaited from SPORTS &YW Dept.sought clarification o/ MDPR .
27 | Lakhimpur | Cultural Affairs | 2008-09 | Harumati Public Auditorium | 2 | Submitted | Submitted | clarification sought byDONER forwarded to DONER ovide PDP(PP)31/2009/39 dtd.23.07..2013 |  | DONER
28 | Sonitpur | UDD | 2008-09 | Improvement of Roads and Drainage infrastructure at Gohpur Town | 11.47 | Submitted | Not submitted | clarification sought byDONER forwarded to Dept. vide PDP(PP)166/2011/4 dtd.18.09-2012 |  | UDD
29 | Karimganj | Sports & YW | 2008-09 | Construction of Nilam Bazar Mini Stadium | 5.02 | Submitted | Not submitted | DPR Forwarded to M/Doner vide PDP(PP)15/2010/12 dtd. 09-08-2012.Dept. was reqstd on 28.1.2014 to submit MDPR as desired by M/DONER. Awaited from Deptt. | DONER
30 | Cachar | Irrigation | 2008-09 | Extension & Improvement Kulicherra FIS (Silchar Division) | 2.1 | Submitted | not submitted | DoNER forwarded observation on DPR . Deptt was requested to clarify/meet the observation vide letter No. PDP(PP)14/2009/12 dtd.28.09.2012 |  | IRRIGATIOn
31 | Dibrugarh | Education(H) | 2008-09 | Infrastracture Development of Dibrugarh Polytechnic, Lahoal | 7.22 | Submitted | Not submitted | DoNER sought MDPR . PWD was intimated for MDPR on 15.02.2013 |  | EDUCATION(PWD(B)
32 | Karbi Anglong | Hill Areas | 2008-09 | Longnit Stadium | 4.65 | Submitted | not submitted | DoNER sought Clafcn.HAD reqstd vide letter No. PDP(PP)41/2010/10 dtd.08.11..2012 |  | HAD
33 | Dibrugarh | Health & FW Dept. | 2008-09 | Development of Assam Medical College & Hospital, HOPE, Dibrugarh (Phase-II) | 20 | Submitted | Submitted | DONER sought clarification on DPR .clarification sent to M/DONER vide PDP(PP)68/2009/49 dated 20.01.2014 |  | DONER
34 | Cachar | Education(H) | 2008-09 | Modernisation and Augmentation of Infrastructure of Silchar Polytechnic | 4.5 | Submitted | Not submitted | DoNER requested to prepare revised DPR, Dept. was reqstd.vide letter No. PDP(PP)53/2010/13 dtd.02.09.2013,Deptt. Was reqstd to suibmit one more copy of MDPR on 20.1.2014 |  | EDUCATION(PWD(B)
35 | Kokrajhar | WPT&BC | 2009--10 | Construction of Mwnsiu sibri English School Building at Bathow Mission, Bengtol. | 12.85 | Submitted | not submitted | DONER saught information vide letter dated 12.07.2011. Deptt. is requested to submit the same vide letter No. PDP(PP) 35/2010/17 dtd.25.07.2011. on 20.01.2013reminded on 29.06.2012 |  | WPT&BC
36 | Jorhat | UDD | 2009--10 | Augmentation of distribution network of Jorhat Town Water supply Scheme. | 3.56 | Submitted | not submitted | DPR sent to DONER vide PDP(PP)90/2010/4 dtd.08.12..2010.Clarification sought by M/DONER on 2/2014. awaited from UDD |  | UDD
37 | Cachar | PHE | 2009--10 | Augmentation of Udarbond PWSS. | 4.6 | Submitted | not submitted | MDPR/clarification forwarded to Deptt. vide PDP(PP)11/2010/26 dtd.3.01.2014. Reply awaited.
38 | Kamrup® | PWD | 2009--10 | Conversion of SPT Br. No.1/1,2/1,3/2,7/1,11/1, 11/2&14/1 to RCC bridge on Kamalpur-Marrowa road | 14.06 | Submitted | submitted | MDPR Forwarded to M/Doner vide PDP(PP)PWD 16/2010/15 dtd. 13.08.2014 |  | DONER
39 | Barpeta | WPT&BC | 2009--10 | Construction of Si-Bwrai Bathou Ashram School Buyilding Auditorium, Customary Law, Yoga Centre, Music School etc. Sarupeta Geruapara, Barpeta district | 12.36 | Submitted | not submitted | DONER saught information vide letter dated 14.07.2011. Deptt. is requested to submit the same vide letter No. PDP(PP)21/2010/17 dtd.25.07.2011.reminded on 26.06.2012 & on 20.01.2013 |  | WPT&BC
40 | Dhubri | PWD | 2009--10 | Construction of RCC Br. No. 2/1 on Uttar Kachokhana School road over river Gangadhar Channel under Dhubri rural road Divn. | 5.55 | Submitted | not submitted | clarification awaited from deptt. since1.10.2013 | pathak | DONER
41 | Dhemaji | PWD | 2009--10 | Conctruction of RCC bridge no.8/1 over river Bogipung on road from Kawpatani to Nalbari & Bridge no.9/2 over river Betoniholla and Br. no.14/1 over river Ratna on road from Chowldhuce Bali to Chutiakari via Deodubi Kaibarta. | 8.86 | Submitted | not submitted | DPR Forwarded to M/Doner vide PDP(PP)PWD 75/2010/6 dtd. 26.08.2010M/DONER sought clarification on DPR .Dept was requested on19.02.2013 to furnish clarification.reply awaited | pathak | PWD
42 | Golaghat | PHE | 2009--10 | Ponka Water Supply scheme Golaghat | 9.94 | Submitted | not submitted | DPR sent to DoNER vide PDP(PP)52/2010/3 dated 04.09.2010 DONER requested to furnishMDPR/clarification. Awaited from PHED | RDAS | PHE
43 | Sibsagar | UDD | 2009--10 | Simaluguri Town Water Supply Scheme, Sibsagar | 8.68 | Submitted | submitted | DONER sought clarification on MDPR,MDPR sent to DONER on Feb/2014. | RDAS | UDD
44 | Goalpara | Sports & YW | 2009--10 | Construction of D.N.Singh Stadium/Sports Complex at Goalpara. | 5.93 | Submitted | Not submitted | MDPR sought by DoNER Dept. intimated on 08.10.2012 | SPORTS&YW
45 | Darrang | PWD | 2009--10 | Construction of RCC Br. No. 2/1 on the road from NH-52 to Kuwaripukhuri via Farirpara and RCC Br. No. 7/1 on Nimtoll Kachomari road including approach and protection work | 5.24 | Submitted | Submitted | clarification sought by M/Doner sent to doner vide.PDP(PP)PWD60/2010/23 dtd. 26.02.2015 |  | PWD
46 | Lakhimpur | UDD | 2009--10 | Silapathar Water Supply scheme | 27.27 | Submitted | submitted | Clarification sought by M/DONER. forwarded to DONER . vide PDP(PP)110/2011/26 dtd.19.10.2013 | RDAS | DONER
47 | Cachar | PHE | 2009--10 | Augmentation of Meherpur PWSS | 7.13 | submitted | not submitted | MDPR sought by DONER.forwarded to Deptt vide PDP(PP)100/2011/36 dtd.03.01.2014. Reply awaited. | RDAS | DONER
48 | Jorhat | UDD | 2009--10 | Water Supply Scheme for Jorhat Town by drawing water from river Brahmaputra | 52.04 | submitted | not submitted | clarification sought by DoNER. Deptt was requested for the same vide PDP(PP)90/2010/241 dated 29.04.2014 . | RDAS | UDD
49 | NC Hills | Hill Areas | 2009--10 | Impvt. Of S.S. Road (Mahur to Cho to Wapu) L=25 km providing Earth Work,GSB, WBN, PCSC Retaining Wall & Cross drainage works etc. | 4.14 | Submitted | not submitted | DONER sought clarification/MDPR. sent to HAD vide PDP(PP)73/2010/32 dated 13.09.2012.reply awaited |  | HAD
50 | NC Hills | Hill Areas | 2009--10 | Impvt. Of Maibang-Semkhor Road (Length-10 Km ) Widening, R/Wall, Jungle clearance, Conversion of Wooden Br. To RCC Br. Side Drain, WBM, M&B etc. | 4.2 | Submitted | not submitted | DONER sought MDPR/clarification .awaited from Dept. |  | HAD
51 | NC Hills | Hill Areas | 2009--10 | Construction of Girls’ Hostel with 100 capacity accommodation Facility at Maibong Higher Secondary School | 1 | Submitted | Submitted | Clarification forwarded to MDONER vide letter No.PDP(PP)34/2010/16 dtd.13.3-2014. |  | HAD
52 | Kokrajhar | WPT&BC | 2009--10 | Renovation of 33 kv line S/S to 33/11 kv Kokrajhar S/S via Fakiragram | 3.06 | Submitted | not submitted | clarification sought by M/Doner . forwarded to Power dept. vide PDP(PP)47/2010/45 dtd.19.04.2013 |  | POWER
53 | Karbi Anglong | Hill Areas | 2009--10 | Development of Karbi Anglong Sports Association (KASA) Stadium at Diphu Karbi Anglong dist. Assam. | 3 | Submitted | submitted | DPR sent to M/DONER vide PDP(PP)9/2013/4 dtd. 4.03..2013.Original NDC forwarded on 1.04.2013
54 | NC Hills | Hill Areas | 2009--10 | Construction of North Cachar Hills Autonomous Council Secretariat Building along with Council Court Building | 10 | Submitted | not submitted | DPR sent to M/DONER vide PDP(PP)30/2010/4 dtd. 5.5.2013.clarification sought byDONER . Sent to HAD on 28.01.2012. reply awaited
55 | NC Hills | Hill Areas | 2009--10 | Extension of Haflong Govt. College Building which will Include construction of another new building to meet the growing crisis of day by day because of singular existence Of such premier Institution of education in the locality | 1.1 | Submitted | not submitted | clarification sought byDONER forwarded to Deptt. vide PDP(PP)31/201/11 dtd. 31.12.2013.Reply awaited
56 | Karimganj | UDD | 2009--10 | Construction of Nilam Bazar Hut(Market Complex) | 4 | submitted | not submitted | clarification sought by DoNER forwarded to Deptt. vide PDP(PP)6/2012 dtd.18.1.2014. Awaited from PWD (BLDG).
57 | Kokrajhar | WPT&BC | 2009--10 | Tourist resort cum Amusement Park at Manas Wild Life Sanctuary. | 34.78 | submitted |  | DONER recommended to drop the project. DPR sent to M/DONER vide PDP(PP)7/2012 dtd.07.09.2013
58 | Jorhat | Power | 2010-11 | Dedicated power supply scheme to integrated infrastructure development (IID) centre,Titabor. | 3.68 | Submitted | not submitted | . DoNER advised IND & COMDept. To move through Power( UAEDCL) Deptt. Project transferred to Power Deptt.M DPR awaited. DpR submitted by power dept. returned for correction vide PDP(PP)101/2011/18 dated 23.08.2013
59 | Barpeta | UDD | 2010-11 | Barpeta Town Water supply scheme | 28.01 | Submitted | submitted | MDPR sent to M/DONER. vide PDP(PP)91/2010/40 dtd. 21.02.2014 | RDAS | UDD
60 | Sibsagar | UDD | 2010-11 | Nazira Town Water supply scheme,Sibsagar district. | 13.82 | Submitted | submitted | clarification/ MDPR sought by M/DONER sent to DONER vide PDP(PP)95/2011/23 dtd.18.06.2014 | RDAS | UDD
61 | Sibsagar | Cultural Affairs | 2010-11 | Construction of mohioshi Joymoti Kalakshetra, at the historic Zerenga pathar in Sibsagar. | 42.03 | submitted | not submitted | Clarification sought by M/DONER. Awaited from deptt. |  | DONER
62 | Sonitpur | PWD | 2010-11 | Improvement of Halem-Kawaripathar Kuwari road connecting Arunachal Pradesh . 13 km with 2nos RCC bridges. | 6 | submitted | Submitted | NLCPR Committee meeting held on 21.12.12 dropped the project . | Pathak
63 | Golaghat | Education(H) | 2010-11 | Proposal of Infrastructure Development of JDSG college,Bokhat. | 3.45 | submitted | not submitted | DoNER sought clarification on MDPR ,forwarded to deptt. vide letter No.PDP(PP)102/20011/17 dtd. 14.08.2012. |  | EDN(PWD(B)
65 | Kamrup | NERAMAC | 2010-11 | Central Packaging Centre. | 15.87 | submitted |  | DPR Forwarded to M/Doner vide PDP(PP)81/2010/5 dtd. 21.07..2012 |  | DONER
66 | Karbi Anglong | Hill Areas | 2010-11 | Imp. Of Road from NH-36 at Phuloni Bazar to Borpadum via Sarthe Rongphar, Sar Rongpi, Men Rongpi, Hanboka Chariali up to Amphukhuri (L=15.00km) | 3.1 | Submitted | not submitted | clarification sought byDONER forwarded to Deptt. vide PDP(PP)44/2012/9 dtd. 22.03.13.Reply awaited |  | HAD
67 | Karbi Anglong | Hill Areas | 2010-11 | Construction of Road from NH-39 to Dilaojan (Ph-1) L=8.00km | 3 | Submitted | not submitted | HAD is requestedto furnish clarification as sought by DONER vide PDP(PP)40/2012/24 dtd 7.8.2013 |  | HAD
68 | Chirrang | WPT&BC | 2011-12 | Construction of road from Bijni Subhaijhar road at village Nayapara No.2 to Kathalguri via Sanyasiguri including constrcution of RCC bridge No.1/2 over river Chara in Chirang district. | 3.66 | submitted | not submitted | sought clarification on MDPR forwarded to M/Doner vide PDP(PP) 10/2012/17 dtd 02.04.2013. M/DONER sought an ink signed copy of NDC . Dept.was reqstd for on 08.04.2014 |  | DONER
69 | Sonitpur | PWD | 2011-12 | Const. of RCC Br. No. 4/1 over river Belsiri including approaches and river training & protection works on Kalakuchi Garjuli road under Sonitpur Rural Road Divn. | 7 | submitted | Submitted | MDPR Forwarded to M/Doner vide PDP(PP)PWD153/2011/42 dtd. 22.09.2013 |  | DONER
70 | Morigaon | PWD | 2011-12 | Improvement of road from 40th km of Nagaon Bhuragaon Road (SH-10) to Singaheruah road by M&BT including const of RCC Br.No.1/1 with approaches and protection works. | 6.4 | submitted | submitted | Clarification Forwarded to M/Doner vide PDP(PP)PWD160/2011/28 dtd. 07.12..2012 |  | DONER
71 | Barpeta | PWD | 2011-12 | Construction of RCC Bridge No.1/1 over river Pahumara at Madhapur Ghat on Madhapur Bhawanipur road (PMGSY road) under NLCPR 2011-12. | 10.5 | submitted | submitted | MDPR Forwarded to M/Doner vide PDP(PP)156/2011/14 dtd. 12.2.13 |  | DONER
72 | Jorhat | Health & FW Dept. | 2011-12 | Medical Gas pipe line system, Modular Ot's,ICU,NICU,RICU for Jorhat Medicalcollege and Hospital,Assam. | 17.86 | submitted | not submitted | DONER reqtsd. To reframe the DPR. Dept.was requested for the same vide PDP (PP)22/2012/pt/19 dtd.02.08.2013 |  | H&FW
73 | Kokrajhar | WPT&BC | 2011-12 | Met. & Bt. Of road from No.2 Goladangi to No.1 Goladangi with 1(one) no.RCC Bridge including Cross drainageworks with protection work in Kokrajhar district. | 7.4 | submitted | not submitted | MDPR/clarification sought by M/Doner. Dept. was reqstd for the same vide PDP(PP)11/2012/16 dtd.04.07..2013.
74 | Tinsukia | UDD | 2011-12 | Water supply project of Digboi Town. | 32.65 | Submitted | submitted | DoNER sought clarification on MDPR. forwarded to DONER PDP(PP)138/2011/11 dtd. 02.09.2013 |  | UDD
76 | Dhemaji | PWD | 2011-12 | Improvement of road from Pukia Tinali to Jonai Tinali including construction work of CD works | 21.91 | submitted | submitted | Clarification sought byM/Doner on MDPR forwarded to DONEr on 2.02.2015 vide PDP(PP)PWD29/2012/27
77 | Kokrajhar | WPT&BC | 2011-12 | Raising & strengthening of existing embankment with A/E measures on L/B of river Sarabhanga from Patgaon to Khalashi under NLCPR for 2011-12 | 35.14 | submitted |  | DPR Forwarded to M/Doner vide PDP(PP) 26/2012/6 dtd. 12.7..2012 |  | DONER
78 | Nagaon | UDD | 2011-12 | Nagaon Town Water supply Scheme | 44.53 | submitted | not submitted | DPR Forwarded to M/Doner vide PDP(PP) 34/2012/3 dtd. 28.08..2012..DONER sought MDPR. Dept. was requested on 21.10.2013.Awaited from Dept. |  | UDD
79 | Kamrup(M) | Education(H) | 2011-12 | Construction of G+2-storied RCC Building for class Room and Digital library providing ground floor parking provision at college campus of Gauhati Commerce College. | 10 | submitted | not submitted | clarification onM DPR saught by DONER on 3.1.2014.vide PDP(PP) 49/2012/25 dtd. 16.1.2014. reply awaited from PWD(B). |  | DONER
80 | Sibsagar | UDD | 2011-12 | Preservation , protection, , Improvement & Cleaning of historical Yamuna around Sivsagar Tank and Siv-Doul of Sivsagar Town | 11.45 | submitted | not submitted | DPR Forwarded to M/Doner vide PDP(PP) 17/2012/12 dtd. 1.08..2013. M/DONER sought clarification . UDD was requested for the same on 19.10.2013
81 | Barpeta | PWD | 2011-12 | Construction of RCC Br. No.1/1 over Pahumara at Bhoukamari Ghat on Barkur Hathinapur road (PMGSY road) under NLCPR 2011-12. | 10.19 | submitted | submitted | M/Doner sought clarification on DPR. Reply sent to m/DONER on 11.02.2015
82 | Dhemaji | PWD | 2011-12 | Const. of RCC Br. No. 2/1,2/2,2/3,3/1,4/1,5/1&6/1 on Old NT Road. | 11.61 | submitted | not submitted | M/Doner sought clarification on DPR. PWD was requesred for the same on 05.02.2014. reply awaited. Dept submitted MDPR with 17.52% increased estd cost on 04.12.2014.PWD was asked to furnish reasons for enhancement on 17.02.2015
83 | Morigaon | PWD | 2012-13 | Improvement of Basnaghat -Bhuragaon Road(S.H.-47) from 14th to 23rd km under Morigaon Rural Road Division. | 7.46 | submitted | not submitted | DPR Forwarded to M/Doner vide PDP(PP)PWD 52/2012/4 dtd. 20.11.2012.M/DONER sought clarification on DPR.Dept was requested on july/2013. Awaited from Deptt. |  | DONER
84 | Kokrajhar | WPT&BC | 2012-13 | Improvement of Road from Kajigaon to Bashbari via Barshijhora (Kokrajhar Rural Road Division) | 17.85 | submitted | Submitted | MDPR Forwarded to M/Doner vide PDP(PP) 55/2012/24 dtd. 09.09.2014 |  | DONER
85 | Lakhimpur | PWD | 2012-13 | Const. of Road from NH-52 (Harmoutty to Bangalmora via Merbil Lakhanabari Manaha & Meraghuli) | 5.81 | Submitted | Submitted | clarification sought byDONER forwarded to DONER ovide PDP(PP)PWD 3/2013/10 dtd.13.03.13.
86 | Golaghat | Border Roads | 2012-13 | Impovement of and upgradation of single lane pavement to intermediate lane of Merapani Uriamghat Road. | 5.05 | Submitted | not submitted | Clarification sought by M/DONER. Dept. was requested to furnish the same on 04.07.2013
87 | Jorhat | PWD | 2012-13 | Const. of Road from Mellang grant to Kaliapani Bagisha including construction of Br. No.1/1 over river Bhogdoi with approaches. | 8.11 | Submitted | submitted | MDPR forwarded to M/DoNER . vide PDP(PP)PWD65/2012/10 dtd.11.09.2013. |  | DONER
88 | Kamrup® | Water Resourses | 2012-13 | Protection of Sonapur and its adjoining areasd from the severe bank erosion of river Puthimari. | 5.5 | Submitted |  | DPR Forwarded to M/Doner vide PDP(PP)18/2013/3 dtd. 30.05..2013
89 | Baska | WPT&BC | 2012-13 | Closing avulsion of river Chamrang at Chamrang village | 4.06 | Submitted | Submitted | DoNER sought clarification on DPR . Sent to M/DONER on.09.09.2013.
90 | Karimganj | Border Roads | 2012-13 | Imp./Constn.of Fakirabazar-Nilambazar road | 17 | Submitted | not submitted | clarification sought byDONER forwarded to Deptt. vide PDP(PP)64/2012 29 dtd. 01,04.2014
91 | Udalguri | WPT&BC | 2012-13 | Improvement of road from Kabir Ali to Chaibari Mekenji road in Udalguri Rural Road Division. | 8 | Submitted | Submitted | clarification/MDPR sent to M/DONER vide PDP(PP)41/2013/11 dtd. 26.03..2014 |  | DONER
92 | Lakhimpur | PWD | 2012-13 | Construction of Road from Phulbari G.P. Office to Nizarapara via Rajghar 750.00 | 7 | Submitted |  | DPR sent to M/DONER vide PDP(PP)PWD37/2013/3 dtd. 13.08..2013
93 | Karbi Anglong | Hill Areas | 2012-13 | Construction of Commercial cum Recreation centre at Diphu Town inKarbi-Anglong District. | 4.32 | Submitted | Submitted | clarification sought byDONER sent on vide PDP(PP)8/2013/12 dtd. 7.12.2013
94 | Karbi Anglong | Hill Areas | 2012-13 | Construction of Indoor Stadium at Dongkamakam under Hamren Sub-Division | 6 | Submitted | Submitted | clarification sought byDONER forwarded to Deptt. vide PDP(PP)7/2013/55 dtd. 21.03.13. MDPR/clarification sent to M/DONER on 14-08-2014
95 | Dima Hasao | Hill Areas | 2012-13 | Impvt.& Strengthening of road from Moulien to Tattephai (L=14.00km) and construction of R.C.C. Bridge under NLCPR. | 11.32 | Submitted |  | DPR sent to M/DONER vide PDP(PP)12/2013/65 dtd. 19.07..2013
96 | sonitpur | Sports &YW | 2012-13 | Development of proposed sports complex at Konibari, Gohpur. | 5.78 | Submitted | Not submitted | DPR forwarded to M/DONER vide PDP(PP)21/2013/7 dtd.24.06.14.2013. Clarifi saught by DONER sent to Deptt. on 24.06.14.reply awaited | M/DONEr
97 | darrang | Sports &YW | 2012-13 | Construction of Mini stadium at Sipajhar. | 10.27 | Submitted | Not submitted | DONER sought Clarification/MDPR Dept. was requested for the same on 27.03.2014 | SPORTS&YW
98 | Dima Hasao | Hill Areas | 2012-13 | Conversion of Asam type to RCC Building of existing 100 bedded Civil Hospital with constn. Of staff quarters and improvement & renovation of existing building at Haflong (Ph-II). | 17 | Submitted | Submitted | clarification on DPR sent to M/DONER vide PDP(PP)20/2014/5 dtd. 18.07.2014
99 | Karbi Anglong | Hill Areas | 2012-13 | Impvt. & M7BT of Tumpreng Hongkram Road from 1st km to 23rd km including construction of RCC Bridge No.9/4&10/3 in Hamren Sub Division. | 10 | Submitted |  | DPR sent to M/DONER vide PDP(PP)20/2014/5 dtd. 27.05.2014
100 | Karimganj | PWD | 2012-13 | Construction of Road from NH44 to Bakarsal village & Construction of Road from Puamara Kaliganj PWD Road to Chandpar village link upto Kawartoli. | 11.5 | Submitted | Not submitted | DPR sent to M/DONER vide PDP(PP)17/2014/5 dtd.15.03.2014. M/DONER sought clarification on DPR . PWD was reqstd for the same on 27.04.2014.reply awaited |  | PWD
101 | Lakhimpur | UDD | 2012-13 | Storm Water drainage under Narayanpur Town Committee. | 12.14 | Submitted | not submitted | clarification sought by M/DONER. forwarded to DONER.. . AA awaited. |  | Deptt
102 | Darrang | PWD | 2012-13 | Improvement of Road Network at Mangaldoi Urban Area | 10 | Submitted |  | DPR sent to M/DONER vide PDP(PP)PWD36/2014/5 dtd. 10.09.2014
103 | Barpeta | PWD | 2012-13 | Construction of Drain cum Footpath within Sarupeta Bazar Committee area | 5.07 | Submitted | not submitted | M/DONER sought clarification on MDPR.Dept.was requstd for the samedtd.29.05.2014.Reply awaited
104 | Nagaon | UDD | 2012-13 | Improvement of Footpath cum drainage network at Raha Urban Area,Assam. | 7 | Submitted | not submitted | M/DONER sought clarification on DPR.Dept.was requstd for the same on 30.1.2014 reply awaited.
105 | Dibrugarh | Water Resourses | 2013-14 | Anti erosion measures to extention of Sassoni Tingkhong bund Ph-I on the left bank of river Buridehing (protection work at Bamunibeel and Uriamguri area) | 12.3 | Submitted | Submitted | clarification sought by M/DONER forwarded to M/DONER vide PDP(PP)31/2013/31 dtd. 9.10..2013
106 | Sonitpur | Water Resourses | 2013-14 | Protection of L/B of river Borgang from erosion at d/s of NH-52 to its outfall at river Brahmaputra . | 14.78 | Submitted | Submitted | Reply on clarification sought byDONER forwarded to M?DONER vide PDP(PP)PWD36/2013/7 dtd. 28.11.2013 |  | Deptt
107 | Nalbari | PWD | 2013-14 | Construction of Road from NH-31 to Kashimpur Suplekuchi via Purbabharati | 4.91 | Submitted |  | DPR sent to M/DONER vide PDP(PP)PWD46/2013/4 dtd. 18.09..2013 |  | DONER
108 | Bongaigaon | Irrigation | 2013-14 | Lower Dulani Irrigation Scheme | 12.05 | Submitted |  | DPR sent to M/DONER vide PDP(PP)44/2013/3 dtd. 26.09.2013 |  | DONER
109 | Udalguri | WPT&BC | 2013-14 | Construction of Road from Khokabasti to Deolguri (U.T. road) | 9.25 | Submitted | Submitted | MDPR sent to M/DONER vide PDP(PP)43/2013/10 dated 24.2.2014 | udt
110 | Cachar | Water Resourses | 2013-14 | Anti-Erosion measures to protect Singerbond area from erosion of river Barak on its L/B | 11 | Submitted |  | DPR forwarded to M/DONER vide PDP(PP)35/2013/3 dtd.19.9.2013
111 | Sibsagar | CAD | 2013-14 | Constn of Ethnic Culture Preservation and Development Centre ,Sibsagar | 4.83 | Submitted | Submitted | clarification saught by DoNER sent to DONER vide letter No.PDP(PP)48/2013/14 15.03.2014.
112 | Nagaon | PWD | 2013-14 | Imt. by widening & strengthening of Kathaltoli Amlakhi Road (from 1km to 25 km ) including constn. Of RCC Br. No. 10/1, 18/1,19/1 & 22/1. | 24.31 | Submitted | Submitted | clarification forwarded to M/DONER vide PDP(PP)PWD60/2013/10 dtd.28.02.2014
113 | Kokrajhar | WPT&BC | 2013-14 | Bodoland Cultural Centre at Ramphalbil | 6.64 | Submitted | not submitted | M/DONER sought clarification/MDPR. Dept. was reqstd vide PDP(PP)54/2013/10 dtd.18.12.2013 |  | DEPTT
114 | Dima Hasao | Hill Areas | 2013-14 | Newzoar Flow Irrigation scheme | 2.92 | Submitted |  | DPR forwarded to M/DONER vide PDP(PP)52/2013/5 dtd.07.10.2013
115 | Kamrup(M) | PWD(BLDG) | 2013-14 | Karmachari Bhavan at Panjabari, Guwahati | 7.77 | Submitted | not submitted | DONER sought clarification
116 | Chirang | WPT&BC | 2013-14 | Construction of road from Subhaijhar to Uttar Ballamguri via Kumarshali at Bijni | 14.7 | Submitted | Submitted | DPR forwarded to M/DONER vide PDP (PP)65/2013/4 dtd.27.12.2013.M/DONER sought CP of the project. Sent on 10.03.2014
117 | Chirang | WPT&BC | 2013-14 | Construction of Kishan Bazar to Bhiranggaon Rowmari, Polashguri, Amguri Road | 11 | Submitted |  | DPR forwarded to M/DONER vide PDP(PP)58/2013/5 dtd.3.2.2014
118 | Dima Hasao | Hill Areas | 2013-14 | Improvement of Jongrorhadi & Daudungkhor village approach Road via Mojowari village with M&B topping,hume pipe culvert and retaining wall,6.00km | 3.13 | Submitted | Submitted | clarification sought by forwarded to M/DONER vide PDP(PP)50/2013/7 dtd.19.09.2014.2014
119 | Dima Hasao | Hill Areas | 2013-14 | Improvement of Killumki approach Road at Lodi village with M&B topping,Hume pipe culvert and retaining wall.L=5.200km | 2,75 | Submitted | Submitted | clarification sought forwarded to M/DONER vide PDP(PP)49/2013/5 dtd.10.09.2014
120 | Sonitpur | Irrigation | 2013-14 | D.T.W Irrigation Scheme at 20 points under Bihaguri Development Block, Sonitpur,Assam phase I | 13 | Submitted |  | DPR sent to M/DONER on 04.06.2014.LC forwarded to M/DONER on16.08.2014.M/DONEr was requested on 29.08.2014 for approval of the project.
121 | Dhemaji | P&RD | 2013-14 | Construction of Road from Matikhula Siva Mandir to Dakhin Dhemaji GP Office under Dhemaji Dev. Block, Dhemaji | 5 | Submitted |  | DPR forwarded to M/DONER vide PDP(PP)75/2013/5 dtd.20.12.2013
122 | Lakhimpur | P&RD | 2013-14 | Construction of Road from Dhalpur NH-52 to Rangati Maghnowa via Jorhatia under Ganak Doloni G.P. of Narayanpur Dev. Block | 5.76 | Submitted |  | DPR forwarded to M/DONER vide PDP(PP)54/2013/5 dtd.10.12.2013
123 | Kampur(M) | CAD | 2012-13 | Construcion of proposed cultural complex (Natsala) of Harisabha at Panbazar, Guwahati | 2.5 | Submitted | not submitted | DPR forwarded to M/DONER vide PDP(PP)51/2013/5 dtd.21.12.2013. DoNER sought original Concept Paper. Dept. was requested for the same on 27.02.2014
124 | Kampur(M) | Social Welfare Deptt. | 2013-14 | Construction of composite Regional centre (North East) for Disability study and action. | 5 | Submitted | Submitted | DONER sought clarification/MDPR. Sent to M/DONER on 13.1.2015
125 | Udalguri | WPT&BC | 2013-14 | Construction of Road from Tangla Chariali to Deor Path via Chaibari Chowk | 8 | Submitted | not submitted | DPR forwarded to M/DONER vide PDP(PP)10/2014/5 dtd.15.2.2014. M/DONER sought some documents . Dept. was reqstd. For the same on 22.04.2014 |  | WPT& BC
127 | Sibsagar | PWD | 2013-14 | Constn of RCC Bridge No 3/1, 1/1 and 5/1 on Amguri to Bangalmari road | 10.5 | Submitted |  | DPR forwarded to M/DONER vide PDP(PP )PWD3/2014/5 dtd.27.2.2014
128 | Golaghat | PWD | 2013-14 | Construction of Road from Dessoi Dhansiri Gelabil to Majchapori Ali | 12.88 | Submitted | Submitted | MDPR forwarded to M/DONER vide PDP(PP )5/2014/22 dtd.18.03.2015. | PWD
129 | Nagaon | PWRD | 2013-14 | Construction of proposed Railway Overbridge at Natun Bazar (Replacing Railway Level Crossing Gate No.JGJN-HJI ST-40) Nilbagan Hojai Tumpreng Road at Hojai, Nagaon. | 3289.7 | Submitted | Submitted | As sought by DONER latest SOR sent toi M/DONETR on 12.3.2014
130 | jorhat | PWD | 2013-14 | Construction of Road from Bongaon to Takarchuk Road cum Bund by Mt & Bt in Jorhat Rural Road Division | 30.75 | Submitted | not submitted | MDPR sent to M/DONER .DONER sought clarification onMDPR.PWD was reqstd for reply on observations on 26.05.2014
131 | Karimganj | Border Areas | 2013-14 | Construction of road from Chatal to east Khagail via South Bajarbond, East Bajarbond, Nakirkuna and Belala, Length - 10 km, with 6 numbers of RCC bridges 25 mts each & 25 numbers of Box culvert | 24.4 | Submitted |  | DPR sent to M/DONER vide PDP(PP)18/2014/5 dtd.11.03.2014
132 | Barpeta | Cultural Affairs | 2013-14 | Guru Milan Kshetra, Barpeta | 5 | Submitted |  | DPR sent to M/DONER on 25.02.2014
133 | Dimahasao | Hill Areas | 2013-14 | New Construction and improvement of Ethnic village at Haflong( Near Jatinga) Dima Hasao | 4.5 | Submitted |  | DPR sent to M/DONERvide PDP(PP)16/2014/8 dtd.02.04.2014
134 | Tinsukia | UDD | 2013-14 | Water supply project in Tinsukia Town (PhaseIII) | 24 | Submitted |  | DPR sent to M/DONERvide PDP(PP)26/2014/29 dtd.28.08.2014
135 | Karbi Anglong | Hill Areas | 2013-14 | Widening with Geometrical improvement of Diphu Dellai Saruhajan Road (Birola to Rongplimplam) l=17.00 km. | 17.35 | Submitted |  | DPR sent to M/DONERvide PDP(PP)23/2014/5 dtd.14.08.2014
136 | Sonitpur | Irrigation | 2013-14 | D.T.W Irrigation Scheme at 20 points under Bihaguri Development Block, Sonitpur,Assam phase-II | 13 | Submitted |  | DPR sent to M/DONER on 19.11.2014
137 | Kamrup® | PWD | 2013-14 | Constn of road from Demu to Baharghat | 5 | Submitted |  | DPR sent tp M/DONER on 13.08.2014
138 | Goalpara | PWD | 2013-14 | Improvement of Road from Simlabari to Khalisarbhita including CD works . | 7.84 | Submitted |  | DPR submitted to M/DONER on 07.05.2014
139 | Kamrup(M) | PWD | 2013-14 | Construction of alternative road to Kamakhya Temple at Guwahati from Pandu in Kamrup (Metro) District | 12.16 | Submitted | Submitted | clarification sent to M/DONER on 02.04.2014
140 | Darrang | PWD | 2013-14 | Improvement and upgradation of Sipajhar Borichowka Mahaliapara road including crossed drainage works under Mangaldoi Rural Road Division. | 10 | Submitted |  | DPR submitted to M/DONER on 029.01.2014
141 | Jorhat | Cultural Affairs | 2013-14 | Developmental works at Auniati Satra, Majuli | 6 | Submitted |  | DPR submitted to M/DONER vide PDP(PP)1/2015/5 dtd.16.02.2015
142 | Morigaon | PWD | 2013-14 | Improvement of Basanaghat Bhuragaon Road (SH-47) Mt &Bt at 8th to 13th KM widening & Strengthening of the Road from single to intermediate lane | 5.31 | Submitted |  | DPR submitted to M/DONER vide PDP(PP)1/2015/5 dtd.18.02.2014