## sectorwise ongoing
Status of ongoing Projects under Non Lapsable Central Pool of Resources (as on February, 2014.)
(Rs. In crore)
Sl. No. | District | Name of project | Year of sanction | Approved cost | Fund released by GOI (90% grant) | UC submitted to DONER | UC pending | % tage of utilisation | Physical progress (%) | Target date of completion | status
Public Works
1 | Tinsukia | Construction of RCC Bridge No.4/3, 10/2 and 14/1 on Pengri Philobari Road in Tinsukia District | 2004-05 | 2.34 | 2.17 | 1.85 | 0.32 | 85.2535 | 79 | 31-12-05 | Out of 3 bridges, 2 bridges completed and construction of one bridge no. 4/3 halted due to cost escalation.Deptt. yet to move for Rs.32 L since 11.9.06. Reminder issued to PWD® on 4-06-2012.
2 | Sibsagar | Construction of RCC Bridge No.6/1, 7/1, 8/1, 8/2, 9/1, 11/1 & 11/2 on Sepon - Suffery Road in Sibsagar Dist. With approaches. | 2005-06 | 4.11 | 2.93 | 2.93 | 0 | 100 | 81 | 2013-12-31 | UC for Rs.293.17 lakh forwarded to M/DoNER on 03-10-2013.
3 | Nalbari | Construction of RCC Bridge No.16/1, 19/1 & 19/3 on Bagals Road in Nalbari Dist. With approaches. | 2005-06 | 4.05 | 2.39 | 2.37 | 0.02 | 99.1632 | 70 | 28-2-07 | Work has been withdrawn from the previous contractor. P&D Dept. has recommended Rs. 12.5233 lakh(S/s) in Feb., 2012. Dept.'s action awaited. 2nd query on UC by M/DoNER on 21-06-2013. Dept. has been requested on 5-07-2013 to submit the same.
4 | Dhemaji | Construction of RCC Bridge No.10/1 on Gogamukh Ghillamara Road in Dhemaji Dist. | 2005-06 | 1.08 | 0.74 | 0.74 | 0 | 100 | 100 | 30-9-07 | 2nd query on UC by M/DoNER on 16-08-2013. Dept. has been requested on 20-08-2013 to submit the same.
5 | Dhemaji | Construction of RCC Bridge No.1/1, 3/1, 3/2 & 4/1 on Bhoirapur - Kulibazar Road in Dhemaji Dist. With approaches. | 2005-06 | 4.66 | 4.16 | 3.27 | 0.89 | 78.6058 | 90 | 31-5-07 | Work has been withdrawn from the previous contractor and allotted to new. EE was asked to complete the project by June, 2013. UC for Rs.67.57 lakh forwarded to M/doNER on 26-09-2013.
6 | Dibrugarh | Construction of RCC Bridge No.2/1on Bamunbari Jariguri Road in Dibrugarh Dist. With approaches. | 2005-06 | 1.08 | 0.78 | 0.56 | 0.22 | 71.7949 | 96 | 31-5-07 | UC awaited from Dept. M.DoNER has expressed concerned on non submission of the same. PWD has been requested on 4-10-2013 to submit the same.
7 | Dibrugarh | Construction of RCC Bridge No.10/1on Khowhng - Bhamun Road in Dibrugarh Dist. With approaches. | 2005-06 | 1.03 | 0.93 | 0.44 | 0.49 | 47.3118 | 52 | 2013-06-30 | P&D Dept. recommended Rs.53.30 lakh(G/s) in May, 2013. UC awaited from dept. MDONER has requested on 3-09-2013 to submit the UC, accordingly PWD has been requested on 4-11-2013 to submit the same.
8 | Dhemaji | Construction of RCC Bridge No.1/1, 5/1, and 3/1 on Bahirjonai-Berachapari Road in Dhemaji District with approaches. | 2005-06 | 5.52 | 3.96 | 2.29 | 1.67 | 57.8283 | 68 | 2013-06-30 | UC for Rs.78.185 lakh forwarded to M/DoNER on 12-12-2013. Revised estimate for completion of balance work prepared. Work withdrawn from original contractor. Tender for balance work under process.
9 | Dhemaji | Construction of RCC Bridge No.1/1, 4/1, and 5/1 on Sripani - Jengrai Road in Dhemaji District with appr. | 2005-06 | 3.02 | 2.17 | 0.95 | 1.22 | 43.7788 | 65 | 31-8-07 | Rs.121.85lakh released as 2nd instlment by M/Doner on 5-7-2013.
10 | Sonitpur | Construction of RCC Bridge No.2/3, 5/1, 9/1, 11/1, 15/3, 16/1,18/1 & 19/4 on Itakhola Pavoi Road in Sonitpur District with approaches. | 2005-06 | 8.57 | 4.56 | 4.56 | 0 | 100 | 79 | 30-4-07 | MDoNER's clarification awaited from PWRD. (B-100%, A-60%). Reply forwarded to M/DoNEr as sought on 8-07-2013. Funds awaited from M/DoNER.
11 | Dhubri | Construction of RCC Bridge No.27/2,28/1,29/1,30/2,32/2,35/1 & 45/1 on Dhubri Kachugaon Road in Dhubri District | 2006-07 | 5.16 | 3.68 | 3.57 | 0.11 | 97.0109 | 85 | 30-11-07 | Deptt yet to move for the balance Rs 11.00 lakh of 2nd instlmnt. (B-85%, A-75%).Retender has been done by the deptt.
12 | Goalpara | Construction of RCC Bridge No.2/1 & 4/2 on Gour Nagar Tikirkilla Road in Goalpara Dist. With approches. | 2006-07 | 3.55 | 2.52 | 1.6 | 0.92 | 63.4921 | 63 | 30-11-07 | Work withdrawn and allotted to another contractor. Query from M/DoNER received on 19-02-2013.Clarification awaited from PWD.
13 | Barpeta | Construction of RCC Bridge No.2/4,6/1 & 8/1 on Dr. Jinaram Das Road in Barpeta Dist. | 2006-07 | 5.36 | 4.66 | 4.02 | 0.64 | 86.2661 | 97 | 2008-01-01 | Rs. 19.23 lakh forwarded to M/doNER on 25-09-2013. Dept. yet to move for release of balance fund.
14 | Cachar | Construction of RCC Bridge No.44/2,38/1,43/1 & 43/2 on Silchar-Hailakandi Road in Cachar Dist. With approaches | 2006-07 | 3.53 | 2.51 | 2.01 | 0.5 | 80.0797 | 96 | 30-11-07 | UC for Rs.0.50 cr., awaited from dept.
15 | Dibrugarh | Construction of Dibrugarh Sapekhati Road from 12th km to 18th km alongwith two RCC bridges No. 18/1 & 19/1 with approaches (bridge over river Buridihing at Saraighat) in Assam, Dibrugarh Dist. | 2007-08 | 21.16 | 18.86 | 15.51 | 3.35 | 82.2375 | 100 | 30-6-09 | UC for Balance amount awaited from dept. MDONER has requested on 3-09-2013 to submit the UC, accordingly PWD has been requested on 5-11-2013 to submit the same.
16 | Cachar | Construction of Rd. and minor bridge from Matinagar to Bhuban Hill Temple(Ph-I) (MP), Cachar District | 2007-08 | 3.26 | 2.94 | 2.3 | 0.64 | 78.2313 | 82 | 31/10/2009 | Rs.59.00 lakh(3rd instlmnt) released by M/DoNER on 10-10-2013.
17 | Cachar | Construction of Road from Bhangarpar to Chandranathpur via Baburbazar.(MP), Cachar District | 2007-08 | 2.49 | 1.8 | 1.4 | 0.4 | 77.7778 | 82 | 31/12/2009 | UC for Rs. 60.17 lakh forwarded to M/DoNER on 5-1-2013. Funds awited from M/DoNER.
18 | Cachar | Construction of RCC major bridge at 7th km. of Kathal Road over river Ghagra (MP), Cachar District. | 2007-08 | 2.5 | 1.79 | 1.79 | 0 | 100 | 96 | 31/03/2010 | Clarification on UC raised by M/DoNER .Reply awaited from deptt.
19 | Darrang | Upgradation of Dolgaon Town to Sialmari via Dekerigaon Kharpunihabi road (MP), Darrang District | 2007-08 | 2.52 | 2.12 | 1.8 | 0.32 | 84.9057 | 100 | 31/10/2009 | work physically completed.CCwill be submitted shortly.
20 | Darrang | Improvement of Batabari Kopati Rd. (MP), Darrang District. | 2007-08 | 2.14 | 1.84 | 1.52 | 0.32 | 82.6087 | 80 | 31/10/2009 | work physically completed.CCwill be submitted shortly.
21 | Dibrugarh | Construction of RCC br. No 57/1 on Gourisagar Moran road and Construction of RCC Br. No 15/2 on Naharkatia- Tingkhong Road in Dibrugarh district with approaches . | 2008-09 | 4.06 | 2.9 | 1.17 | 1.73 | 40.3448 | 70 | 31-05-2010 | P&D Dept. recommended Rs.5.54866 lakh in Feb., 2012. M/DoNER has requested on 19-09-2013 to submit the UC, accordingly PWD has been requested on 25-10-2013 to submit the same.
22 | lakhimpur | Construction of RCC br. No 18/2 over stream Bahanigaon & Br. NO 19/1 over river kachikata on laluk- Narayanpur Road in lakhimpur District with Approaches . | 2008-09 | 2.09 | 1.5 | 1.5 | 0 | 100 | 95 | 31-07-2010 | UC for Rs.84.30 lakh forwarded to M/DoNER on 16-05-2013. Query received from M/DoNER on 24-06-2013. Accordingly informed to the Dept. Reply awaited from PWD.
23 | Dibrugarh | Construction of roadside drain cum Footpath and provision for roadside streetlight illumination in Nahakatia Town in Dibrugarh Dist. under Dibrugarh Rural Road Division . | 2008-09 | 6.45 | 4.54 | 1.99 | 2.55 | 43.8326 | 64 | 28-02-2010 | P&D Dept. recommended Rs 52.13 lakh on Sept 2011. UC awaited from dept.M.DoNER has expressed concerned on 13-09-2013 on non submission of the same. PWD has been requested on 29-10-2013 to submit the same.
24 | Goalpara | Construction of RCC Br. No. 32/1 on A.T. Road (old) including approaches, Protection works, Goalpara in Assam | 2008-09 | 7.39 | 4.62 | 2.31 | 2.31 | 50 | 51 | 31-10-2010 | Rs. 230.51 lakh(2nd instlmnt) received from M/doNER on 1-08-2013. Dept. yet to move for release.
25 | Morigaon | Construction of RCC Br. No. 5/3 on Borbhogia - Mikirbhata Road with approaches in Morigaon distrct | 2008-09 | 2.41 | 1.72 | 0.75 | 0.97 | 43.6047 | 40 | 30-11-2010 | Completion Certificate and UC for Rs.26.86Lakh awaited from Deptt.
26 | Hailakandi | MT &BT of from Swapanpur to Ramchandi Road (MP), Hailakandi District | 2008-09 | 3.8 | 2.73 | 2.71 | 0.02 | 99.2674 | 92 | 31/03/2009 | Reply of query by M/DoNER forwarded to on 04-09-2013. Funds awaited from M/DoNER.
27 | Morigaon | Construction of RCC Br. No 2/1on Nandini Karaimari Road | 2009-10 | 6.58 | 2.04 | 2.04 | 0 | 100 | 23 | 31-02-2011 | Uc for Rs.204.25 lakh forwarded to M/doNER on 8-10-2013. Funds awaited from M/doNER.
28 | Sibsagar | Construction of RCC Br. No 3/2,5/2 & 5/4 on Rupsir Ali | 2009-10 | 2.1 | 1.51 | 0.66 | 0.85 | 43.7086 | 70 | 2012-10-30 | UC awaited from Dept. M.DoNER has expressed concerned on non submission of the same. PWD has been requested on 3-10-2013 to submit the same.
29 | Nagaon | Construction of RCC Br. No 7/1,15/1 & 19/1 on Nagaon- Barapujia Road with approaches in Nagaon Dist | 2009-10 | 4.66 | 1.46 | 0 | 1.46 | 0 | 45 | 31-08-2011 | P&D dept. recommended Rs.146.00 lakh in in Sept., 2012 . UC awaited for the amount.
30 | Morigaon | Construction of RCC Br. No 12/1 on Goroimari-Dewaguri road with approaches in Nagaon Dist | 2009-10 | 3.17 | 1.13 | 0.73 | 0.4 | 64.6018 | 24 | 31-03-2011 | UC forwarded to M/DoNER on 12-07-2013.
31 | Karimganj | Improvement / upgradation of Chenchorie Elgin Road including major RCC bridge over river Ghagra. | 2009-10 | 11.81 | 4.17 | 1.38 | 2.79 | 33.0935 | 73 | 31-10-2011 | P &D has recommended Rs.34.80 lakh(s/s) in May, 2013.UC awaited from dept. 2nd instalmant awaited from M/doNER.
32 | Udalguri | Improvement of Tangla- Bhergaon -ramgaon road in Udalguri District. | 2009-10 | 10.43 | 7.36 | 5.03 | 2.33 | 68.3424 | 75 | 28-02-2013 | Rs. 39.37 lakh recommended in October, 2012. Last Uc for Rs. 51.00 lakh forwarded to M/DoNER on 21-01-2013. U C for the balnce recommended amount awaited from PW Deptt.
33 | Nagaon | Upgradation of Nagaon- Bhuragaon Road via Dhing ( SH-10) in Nagaon | 2009-10 | 11.15 | 8.22 | 8.22 | 0 | 100 | 89 | 30-04-2011 | Last UC for Rs.136.61 lakh submitted to M/DoNER on 23-05-2013. Rs.45.63 lakh (S/s) release by P&D in May, 2013.
34 | Nagaon | Construction of RCC Br. No 6/1 , 9/1 & 10/1 on Ambagaon – Kathpara solmari Singrai Rd. ( NG-17) in Nagaon Dist | 2009-10 | 2.39 | 2.14 | 2.14 | 0 | 100 | 60 | 28-02-2012 | UC submitted to M/DoNER on 29-01-2013. CC awaited from dept.
35 | Dibrugarh | Improvement of Road Net work leading towards Dibru- Choikhowa National Park Construction of RCC Br. No 1/1over river Doomdoma on old A.T road | 2009-10 | 7.47 | 5.38 | 5.38 | 0 | 100 | 76 | 30-04-2013 | Funds awaited from M/DoNER.
36 | Nalbari | Metalling & Black topping of road from Dr. Fakaruuddin Ali Ahmed Path to Dolgobindapur via Nalbari Hindu samshan, Nalbari along with Pucca Drain and RCC Slab Culverts (MP) | 2009-10 | 2.28 | 1.63 | 1.63 | 0 | 100 | 90 | 28/02/2012 | UC submitted to M/DoNER on 29-05-2013. Funds awited from M/DoNER.
37 | Nagaon | Construction of RCC Br. No 4/1 on Dimow-Raidongia road over river Sonai Under Nagaon Rural road Division in Nagaon. | 2010-11 | 2.71 | 0.96 | 0.32 | 0.64 | 33.3333 | 18 | 30-04-2012 | UC for Rs.32.21 lakh forwarded to M/doNER on 03-07-2013.
38 | Jorhat | Street lighting in Jorhat city leading to jorhat Airport | 2010-11 | 2.13 | 1.5 | 0.41 | 1.09 | 27.3333 | 75 | 30-09-2011 | UC for Rs.41.04 lakh forwarded to M/DoNER on 6-12-2013. UC for the balance amount awaited.
39 | Nagaon | Construction of RCC Br. No 3/1 on Majgaon –Santipur Rd. over river sonai with approaches in Nagaon Dist | 2010-11 | 3.33 | 1.19 | 1.19 | 0 | 24 | 50 | 30-06-2012 | UC for Rs.118.76 lakh forwarded to M/DoNER on 07-10-2013. May, 2013. Funds awaited from M/DoNER.
40 | Tinsukia | MT & BT from Borhapjan- samdang Road to Sukanguri L.P. School. | 2010-11 | 3.22 | 2.29 | 2.29 | 0 | 100 | 80 | 31-03-2012 | Funds awaited from M/DoNER . Clarification on UC by M/DoNER received on 17-05-2013. Dept. has been requested on 10-06-2013 for submission of the same.
41 | Tinsukia | MT & BT from Circuit House Tinsukia to NH 37 via Okanimuria Borguri | 2010-11 | 5.24 | 3.7 | 1.86 | 1.84 | 50.2703 | 65 | 28-02-2012 | Rs. 184.34 lakh (2nd installment) has been released by M/DoNER on 26-06-2013. Dept. requested on 6-07-2013 to movce proposal for release of fund.
42 | Sibsagar | Construction of Mahmora Ali with RCC Br.No. 9/2 Sivsagar Dist. | 2010-11 | 7.72 | 2.72 | 0 | 2.72 | 0 | 0 | 28-02-2013 | A/A accorded by P & D Deptt on 05/01/2011. Dept. yet to move for release of Rs. 271.80 lakh.
43 | Bongaigaon | Constuction of RCC Br. No. 1/2over river Aie at Chilapara, Kahibari villages on the road from Kokrajhar NH -31 to Nowgong, Nanikpur NH-31 via Kirtanpar Numberpara villages under Bongaigaon Rural Road Division. | 2010-11 | 40.01 | 14.26 | 0 | 14.26 | 0 | 4 | 30-11-2013 | Delayed due to court case. Now work started. Dept. yet to move for release of fund.
44 | Chirang | Construction of Rcc Br.over river Aie. | 2010-11 | 78.84 | 70.25 | 67.54 | 2.71 | 96.1423 | 95 | 30-11-2013 | last UC for Rs.860.39 lakh submitted to M/DoNER on 23-05-2013. Balance UC awaited from dept.
45 | Dibrugarh | Construction of RCC Br.No.1/2 & 4/1 on old AT Road, Khowng, Dibrugarh | 2010-11 | 2.9 | 2.09 | 2.09 | 0 | 100 | 83 | 30-11-2013 | Clarification alongwith fresh UC & orther documents forwarded to M/DoNER on 11-11-2013.
46 | Dibrugarh | Construction of Mora Netai Road Dibrugarh | 2010-11 | 3.03 | 1.08 | 0 | 1.08 | 0 | 65 | 30-11-2012 | A/A accorded by P & D Deptt on 26-11-2010. P&D Dept. recommended Rs. 106.68236 lakh in Jan, 2012. Uc awaited from Deptt.
47 | Sibsagar | Construction of Tiphuk Jajali Pukhuri Road with Rcc Br. No. 3/3 in Sivsagar. | 2010-11 | 5.6 | 3.96 | 1.99 | 1.97 | 50.2525 | 41 | 30-11-2012 | Rs.196.59 lakh (2nd instlmnt) released by M/DoNER on 04-09-2013. Dept. yet to move for release of fund.
48 | Morigaon | Construction of RCC Bridge No.24/1 on Morigaon Moirabari in Morigaon District. | 2010-11 | 3.16 | 1.12 | 1.12 | 0 | 100 | 46 | 31-07-2012 | UC forwarded to M/DoNER on 22-05-2013. Fund awaited from M/doNER. Rs. 12.44 lakh (S/s) released by P&D in May, 2013.
49 | Jorhat | Construction of RCC Bridge No. 13/1, 13/2, 20/2 on Mohbandha Road. | 2010-11 | 6.14 | 2.19 | 0.91 | 1.28 | 41.5525 | 27 | 31-01-2013 | UC forwarded to M/DoNER on 12-07-2013.((B-9%, 13/2- 40%, 20/2- 100%, Approach-10%). Rs.37.34 lakh (G/s) recommended by P&D in May, 2013.
50 | Cachar | Construction of RCC Br. No.2/2 & 2/3 renamed as 3/1 & 4/1) on Shyamaprasadpur - Dossgram road via Swapnargul over stream Singrai in Cachar District. | 2010-11 | 2.57 | 1.83 | 0.92 | 0.91 | 50.2732 | 70 | 31-07-2012 | Physical 70% progress in Bridge Works.2nd instlment received in end of Feb,2013.
51 | Kamrup(M) | Construction of Zoo Zaparigoog Road , Guwahati. | 2010-11 | 6.2 | 2.23 | 2.23 | 0 | 100 | 75 | 31-12-2012 | UC for Rs. 24.79 lakh forwarded to M/DoNER ON 27-05-2013. Funds awaited.
52 | Sibsagar | Improvement of road network at Sonari Town under Choraideo Rural road Division | 2010-11 | 7.24 | 5.22 | 2.61 | 2.61 | 50 | 62.86 | 30-06-2012 | Rs.260.55 lakh (2nd instlmnt) released by M/DoNER on 22-10-2013. Dept. yet to move for release of fund.
53 | Sibsagar | Construction of RCC Br. (a) No.1/1 and 2/1 on Deroi Rongli road (b) No. 2/1 on Deopling Ramunagar road and No.3/1 Ghilaguri road | 2010-11 | 3.91 | 1.38 | 1.38 | 0 | 100 | 58.33 | 2012-12-31 | UC submitted on 03-04-2013. Funds awaited from M/DoNER.
54 | Nagaon | Construction of Br. No. 2/1 & 4/1 on Raha Barapujia road over river Botamari and Hatibanda with approaches in Nagaon District | 2010-11 | 3.69 | 1.31 | 0 | 1.31 | 0 | 40 | 2013-03-31 | P&D recommended Rs.29.30 lakh. UC awaited.
55 | Jorhat | Improvement of J.B. Road in Jorhat District | 2011-12 | 2.97 | 2.12 | 1.06 | 1.06 | 50 | 50 | 2011-06-30 | Rs.105.82 lakh (2nd instlmnt) received from M/DoNER on 12-08-2013.
56 | Darrang | Construction of Road from Rangamati to Kalaigaon Road (between) Janaram Chowka to Aaola Chowka in Darrang District. | 2011-12 | 5.75 | 2.03 | 0 | 2.03 | 0 | 25 | 2014-05-31 | Rs. 202.77 lakh released as( 1st installment) on 14-02-2012. P&D Dept. recommended Rs. 154.11 lakh(G/s) in May, 2013. UC for the amount awaited.
57 | Dibrugarh | Sessa T.E. to Timona Road in Dibrugarh | 2012-13 | 4.01 | 1.41 | 0 | 1.41 | 0 | 0 | 2014-05-31 | A/A accorded by P & D Deptt on 8-06-2012.
58 | Dibrugarh | Construction of Maijan Thakurbari road to Mukalbari road in Dibrugarh Dist. | 2012-13 | 8.11 | 2.86 | 0 | 2.86 | 0 | 0 | 2014-05-31 | A/A accorded by P & D Deptt on 7-06-2012.
59 | Dibrugarh | Improvement of Road from 1st Km of Demow Dehing Road to Dhaoma Phukhuri (length-10.125Km) with RCC Bridge(length-18.75m) in Demow Rural road Sub division. | 2012-13 | 7.6 | 2.71 | 0 | 2.71 | 0 | 0 | 2014-05-31 | A/A accorded by P & D Deptt on 27-06-2012.
60 | Jorhat | Construction of Slab Culvert by replacing old bridges and slab culvert on kamarbondha road upto 22nd km. | 2012-13 | 7.28 | 2.62 | 0 | 2.62 | 0 | 0 | 31-12-2013 | A/A accorded by P & D Deptt on 27-06-2012. Dept. yet to move for release of fund.
61 | Dhubri | Construction of RCC Br. No.1/11 over Tanghat Channel on NH-31(tanghat to Asharkandi Ghegraralga Road) Dhubri District | 2012-13 | 3.25 | 1.17 | 1 | 0.17 | 85.4701 | 20 | 2014-08-31 | UC for Rs.100.00 lakh forwarded to M/DoNER on 10-06-2013.
62 | Dhubri | Construction of Rcc Br. No.6/2, 7/3, 8/2, 10/1 and 11/1 over branches of river Kaloo on A.P.S. Road, Dhubri District. | 2012-13 | 13.91 | 5.01 | 5.01 | 0 | 100 | 25 | 2014-07-31 | UC for Rs.500.55 lakh forwarded to M/DoNER on 10-06-2013.
63 | Nalbari | Construction of Rangia Dhamdhama Road including RCC Br. No. 18/1, 18/2, 19/2, 20/1 and 20/3. Nalbari Dist. | 2012-13 | 10.55 | 3.8 | 2 | 1.8 | 52.6316 | 36 | 2014-07-31 | UC for Rs.200.23 lakh forwarded to M/DoNER on 10-12-2013.
64 | Nalbari | Construction of Rcc Br. No.3/1 over river Pagladia on U.C. Baruah Road | 2012-13 | 7.3 | 2.63 | 0 | 2.63 | 0 | 0 | 2015-07-31 | AA accorded by P& D Deptt. on 14-09 2012. Deptt. yet to move for release of 1st instalment.
65 | Sibsagar | Improvement of nagnimora Jajoli Road from ch.8.346 km to ch.13.650 km including conversion of SPT bridge no. 14/1 to RCC bridge. | 2012-13 | 4.85 | 1.75 | 0.66 | 1.09 | 37.7143 | 17 | 2014-01-31 | UC for Rs.55.48 lakh forwarded to M/DoNER on 19-08-2013. Uc
66 | Tinsukia | Construction of Kaliapani RCC Bridge No.21/1 over river Dibru on Doomdooma Dighaltarang Natun Gaon Road with approach road in Tinsukia. | 2012-13 | 13.23 | 4.76 | 0 | 4.76 | 0 | 0 | 2015-07-31 | AA accorded by P&D on 20-09-2012. Dept. yet to move for release of fund.
67 | Nagaon | Construction of railway over Bridge at Dhing gate on Nagaon Bhuragaon Road via Dhing at Nagaon | 2012-13 | 21.05 | 7.58 | 0 | 7.58 | 0 | 0 | 2014-01-31 | AA accorded by P&D on 08-10-2012. Rs.757.96lakh released by M/DoNER as 1st instalment. Dept. yet to move for release.
68 | Dibrugarh | Construction of RCC Bridge No.1/1 over River Doomdooma on A.T. Road. | 2012-13 | 4.22 | 1.52 | 0 | 1.52 | 0 | 0 | 2014-09-30 | AA accorded by P&D vide letterNo.PDP(PP)PWD(PP)71/08/49 dtd. 12-10-2012.
69 | Nalbari | Improvement of Kanimara Nannatary road in Nalbari District | 2012-13 | 4.35 | 0 | 0 | 0 |  | 0 | 2014-06-30 | AA accorded by P& D Deptt. on 18-02 2013. Deptt. yet to move for release of 1st instalment.
70 | Morigaon | Construction of RCC Bridge No.29/1 (at Br. Gap) at Kuhimari Bordowa road (SH-15) in Morigaon District. | 2012-13 | 5.01 | 1.8 | 0 | 1.8 | 0 | 0 | 2014-06-30 | New Project. AA accorded by P&D Deptt. Dept. yet to move.
71 | Cachar | Construction of Br.No.1/1 of 170.00 Km including approaches and protection work over Jatinga at Borkhola on Mahasadak to Borkhola road. | 2012-13 | 14.32 | 5.15 | 0 | 5.15 | 0 | 0 | 2015-08-30 | AA accorded by P& D Deptt. on 08-04 2013. Deptt. yet to move for release of 1st instalment.
72 | Hailakandi | Construction of RCC Br. No.6/1 over river Kathalkhal at Ratanpur Ferryghat on Hailakandi, ratanpur road, Hailakandi | 2012-13 | 22.94 | 8.26 | 0 | 8.26 | 0 | 0 | 2015-09-30 | AA accorded by P& D Deptt. on 09-04 2013. Deptt. yet to move for release of 1st instalment.
73 | Barpeta | Construction of RCC Bridge No.1/1 over River Kaldia on Sarumanikpur-Maharani Road | 2012-13 | 4.62 | 1.66 | 0 | 1.66 | 0 | 0 | 2015-02-28 | AA accorded by P& D Deptt. on 01-04 2013. Deptt. yet to move for release of 1st instalment.
74 | Dhemaji | Construction of RCC Bridge No.7/1 on Sissobargaon Amguri Road over Singimari stream | 2012-13 | 4.29 | 1.54 | 0 | 1.54 | 0 | 0 | 2014-08-30 | AA accorded by P& D Deptt. on 01-04 2013. Deptt. yet to move for release of 1st instalment.
75 | Darrang | Construction of Guidebund near RCC Bridge No.8/2 over river Tonganee on the road form NH -52 to Kuwaripukhuri via Fakirapara | 2012-13 | 2.09 | 0.75 | 0 | 0.75 | 0 | 0 | 2013-10-31 | AA accorded by P& D Deptt. on 01-04 2013. Deptt. yet to move for release of 1st instalment.
76 | Darrang | Construction of road from Ramhari to Bherbheri via Chamuakhat (ch.8.00km to 11.50km) including cross drainage works | 2012-13 | 3.46 | 0.79 | 0 | 0.79 | 0 | 0 | 2014-08-30 | AA accorded by P& D Deptt. on 13-03- 2013. Deptt. yet to move for release of 1st instalment.
77 | Sonitpur | Construction of RCC Bridge No.2/1 over river Belsiri on Dhekipelua to Belsiri T.E. connecting NH-52 | 2012-13 | 5.53 | 1.99 | 0 | 1.99 | 0 | 0 | 2015-02-28 | AA accorded by P& D Deptt. on 13-03- 2013. Deptt. yet to move for release of 1st instalment.
78 | Sibsagar | Construction of Road from Banamali Tinali to Rongagorh Tinali with RCC bridge No.2/2 over river Desang and Br.No.8/2 on Mohmora Ali | 2012-13 | 14.22 | 5.12 | 0 | 5.12 | 0 | 0 | 2013-05-31 | New project. AA accorded by P&D Deptt. on 12-04-2013. 1st instlmnt released by M/DoNER on 26-02-2013.
79 | Sibsagar | Improvement of Mridongpara Road under NLCPR | 2013-14 | 6.72 | 0 | 0 | 0 | 0 | 0 | November,2014 | New project.
80 | Nagaon | Construction of RCC Br.No.1/1 on Mohmoria to Kuruabhi via Bebejia Road over river Kalang under Nagaon Rural Road Division (Nagaon District) | 2013-14 | 2.74 | 0.99 | 0 | 0.99 | 0 | 0 | 2014-11-30 | New project.
81 | Darrang | Improvement of Banglagarh Jaberikuchi Road(length-12.5 km) including cross drainage works | 2013-14 | 20.47 |  |  | 0 |  |  | 2015-07-31 | AA accorded by P&D Deptt. on 26-09-2013.
82 | Cachar | Construction of RCC Bridge No.1/1 over River Barak at Sadarghat, Sichar on Silchar Kumbhigram Road | 2013-14 | 59.01 | 21.24 |  | 21.24 |  |  | 2016-04-30 | AA accorded by P&D Deptt. on 11-12-2013. Rs.2124.38 lakh(1st instlmnt) released by M/DoNER on 07-11-2013. Dept. yet to move for release of fund.
83 | Nalbari | Construction of Khetri Dharampur to Hajo Nalbari Road at Morowa via Piplibari, Kakaya, Jagara, Goalpara, Baguhati & kalkuchi | 2013-14 | 10.39 |  |  | 0 |  |  | 2015-11-30 | AA accorded by P&D Deptt. on 17-12-2013.
84 | Dhubri | Construction of road from Kanuri to Binachora(Satghaipara via Nalia including protection works and 4 RCC bridges | 2013-14 | 38.55 |  |  | 0 |  |  | 2015-11-30 | AA accorded by P&D Deptt. on 17-12-2013.
85 | Morigaon | Improvement of Morigaon Pachatia-Damal Dharamtul Road including construction of RCC brifge No. 5/1 over river Kollong under Morigaon District. | 2013-14 | 7.33 | 2.63 |  | 2.63 |  |  | 2016-02-28 | AA accorded by P&D Deptt. on 10-02-2014
|  | Total: |  | 703.13 | 333.73 | 189.71 | 144.02
|  | Power |  |  |  |  | 0
86 | Sonitpur | Construction of 38 km 33 KV line from Balipara to Bhalukpung.,Sonitpur | 2005-06 | 1.33 | 1.33 | 1.33 | 0 | 100 | 0 | 31/07/2007 | Concept Paper of alternative proposal in lieu of the present project forwarded to M/DONER in Jan., 2012. Audited statement of the expenditure incurred in the present project awaited from Power Dept.
87 | Kamrup(R ) | Construction of 220/132 KV Azara (Kukurmara) S/S with 132/33 KV Azara S/S with LILO of 220 KV Agia- Sarusajai Line, 132KV S/C lines to 132/33 KV Boko and Azara S/S in Assam ,Kamrup® | 2007-08 | 36.22 | 26.08 | 26.08 | 0 | 100 | 67 | 30/09/2010 | UC for Rs. 1466.94 lakh alongwith other documents forwarded to M/DoNER on 16-12-2013. Funds awaited from M/DoNER.Meanwhile Rs.289.76 lakh(s/s) recommended by P&D on 10-02-2014. UC for the amount awaited.
88 | Kokrajhar | Construction of 132 KV BTPS -Kokrajhar S/c line and 132 KV Kokrajhar S/C line 132 KV /33 KV sub Station at Kokrajhar. | 2010-11 | 43.58 | 25.58 | 15.38 | 10.2 | 60.1251 | 41 | 30-11-2013 | 22-10-2013 has conveyed the sanction of Rs,1020.13 lakh has been released by M/DoNER as 2nd installment on 22-10-2013. Dept. moved for the same and file under process. Meanwhile, Rs.170.89 lakh (s/s) recommended by P7D on 17-11-2013. UC awaited from dept.
89 | Kokrajhar | Construction of new 33/11KV, 2x5MVA S/S at Thirubari with 45KM 11KV lines and 55Km 33 KV lines from Dhiligaon to Thirubari | 2012-13 | 8.9 | 3.21 | 0 | 3.21 | 0 | 0 | 2013-11-30 | AA accorded by P&D dept. on 13-12-2012. Dept. yet to move for release of fund.
|  | Total: |  | 90.03 | 56.2 | 42.79 | 13.41
|  | Water Resources |  |  |  |  | 0
90 | Dhemaji | Raising & Strengthening of Brahmaputra Dyke from Dizmore to Sonarigaon from 14th to 23.15th km. including closing of Amguri & Arney Nalla. ,Dhemaji | 2003-04 | 11.51 | 9.83 | 9.83 | 0 | 100 | 99 | 31/12/2008 | Recommended for revalidation of A.A for Rs.11.51 crore on 15.02.2012. Detail report not yet received from WR Deptt.
91 | Dibrugarh | A/E measures to protect Dehingpuria village near Margherita town erosion of Buridehing river. | 2012-13 | 5.4 | 2.63 | 0 | 2.63 | 0 | 0 | 2013-08-30 | New Project. AA accorded by P&D Deptt.
92 | Dibrugarh | A/E measures to protect Naharkotia town from the erosion of river Buridehing at Jagun Gaon area. | 2012-13 | 7.31 | 1.94 | 0 | 1.94 | 0 | 0 | 2013-08-30 | New Project. AA accorded by P&D Deptt.
|  | Total: |  | 24.22 | 14.4 | 9.83 | 4.57
|  | Irrigation |  |  |  |  | 0
93 | entire state | 89 Minor Irrigation Schemes (entire state) | 1998-99 | 2.85 | 2.85 | 2.57 | 0.28 | 90.1754 | 100 |  | Work completed. 113 CCs already submitted to M/DoNER. Remaining 7 CC awaited .
94 | Sonitpur | Dokhindhol LIS (MP), Sonitpur | 2007-08 | 2.11 | 1.87 | 1.53 | 0.34 | 81.8182 | 90 | 30/09/2008 | Rs.34.29 lakh( 3rd instalment) recived from M/DoNER in September,2013. Dept. yet to move for release of fund.awaited .
95 | Sonitpur | Belsiri LIS (MP), Sonitpur | 2007-08 | 2.17 | 0.68 | 0.68 | 0 | 100 | 55 | 30/09/2008 | Revised DPR submitted by Deptt.
96 | Nalbari | Burinagar LIS, Nalbari District | 2011-12 | 2.16 | 0.74 | 0 | 0.74 | 0 | 0 | 2013-07-31 | AA accorded by P&D Dept. on 11-07-2011. Dept. yet to move proposal for release.
|  | Total: |  | 9.29 | 6.14 | 4.78 | 1.36
|  | Education |  |  |  |  | 0
97 | Kamrup(M) | Modernisation and Augmentation of infrastructure development of Assam Textile Institue at Guwahati, Assam, Kamrup(M) | 2006-07 | 7.41 | 2.34 | 2 | 0.34 | 85.4701 | 40 | 30/09/2009 | M/DONER was requested to release remaining fund for civil works ( para 8.3 of the NLCPR guidelines). M/DoNER turn down the state govt.'s request vide their letter No.160/2005-NLP(AS) dtd. 31-01-2013.
98 | Darrang | Infrastructural facilities at Kharupetia College - Construction of Building for Classrooms, Computer Laboratory with A.C, Hostels for trainees, electricity facilities, Water Supply & Sanitary facilities installation.(MP), Darrang | 2007-08 | 1.75 | 0.55 | 0 | 0.55 | 0 | 25 | 30/09/2008 | Rs.55.33 lakh released on 17-12-2009 . UC awaited.Reminder issued to submit UC.
99 | Kamrup(M) | Construction of Academic cum Administrative Building of K.K. Handique Govt sanskrit College, Kamrup (M) | 2007-08 | 2.38 | 1.69 | 0.93 | 0.76 | 55.0296 | 65 | 30/06/2009 | P & D agree to revalidate the amount on 25-03-2013.
100 | Kamrup(M) | Assam Institute of Management, Kamrup(M) | 2010-11 | 14.61 | 5.16 | 0 | 5.16 | 0 | 0 | 2012-07-31 | P&D Dept. recommended Rs.500.00 lakh on 19-12-2013. UC for the amount awaited from dept.
101 | Kamrup(M) | State Level Eligibility Test Commsion Assam (SLET), Kamrup(M) | 2010-11 | 3.35 | 1.18 | 0 | 1.18 | 0 | 0 | 2012-11-30 | P&D Dept recommended Rs. 1.18 crore on 01-03-2012. UC for the amount awaited from dept.
|  | Total: |  | 29.5 | 10.92 | 2.93 | 7.99
|  | Health |  |  |  |  | 0
102 | Kamrup(M) | Construction of two storied building of Swahid Jadav nath (SJN) Govt. Homeopathic college & hospital at Panjabari, Guwahati (MP)., Kamrup(M) | 2007-08 | 2.66 | 2.35 | 1.88 | 0.47 | 80 | 88 | 31/10/2010 | UC for Rs. 46.90 lakh (final installment) & CC awaited from dept.
|  | Total: |  | 2.66 | 2.35 | 1.88 | 0.47 | 80
|  | Cultural Affairs |  |  |  |  | 0
103 | Kamrup(M) | Development & Upgradation of Jyoti Chitrobon Film & Television Institute, Kamrup(M) | 2007-08 | 13.47 | 6.93 | 4.18 | 2.75 | 60.3175 | 70 | 30/11/2008 | 2nd instlment received from M/DoNER in Feb, 2013.
104 | Kokrajhar | Construction of Cultural Centre Complex at Dotma (MP), | 2007-08 | 2.21 | 0.99 | 0.99 | 0 | 100 | 86 | 31/12/2009 | UC forwarded to M/DoNER on 6-06-2013.Clarification on UC sought by M/DoNER on 28-06-2013 and dept. has reuqested on 8-07-2013 to submit the same.
105 | Kokrajhar | Bodoland India Indigeneous Tribal Art & Cultural Complex cum Film Studio at Kathalguri, Pt-II, Kokrajhar (MP) | 2007-08 | 4.95 | 1.61 | 0 | 1.61 | 0 | 0 | 31/12/2009 | P&D recommended Rs.1.24 crore. UC awaited
106 | lakhimpur | Construction of Sankar-Madhav Cultural Complex at letekupukhuri, Bhogpur Chariali, Lakhimpur : Assam(MP) | 2007-08 | 4.01 | 1.26 | 1.03 | 0.23 | 81.746 | 43 | 31/10/2009 | Uc for Rs. 103.54 lakh forwarded to M/DoNER on 12-11-2013.
107 | Jorhat | Presrvation of Cultural Hertitage of Majuli Natun Kamlabari Satra (Phase I), Jorhat | 2009-10 | 6.19 | 2.18 | 1.5 | 0.68 | 68.8073 | 30 | 31/04/2011 | Uc for Rs.150.00 lakh forwarded to M/DoNER on 06-06-2013.
108 | Kamrup(M) | Socio Literary Cultural Complex of Bodo Sahitya Sabha at Bathooupuri, Gorchuk, Guwahati, Kamrup(M) | 2010-11 | 8.41 | 5.94 | 2.96 | 2.98 | 49.8316 | 40 |  | Rs. 296.82 lakh received as 2nd instalment on 10-07-2013 from M/doNER. Dept. has been requested on 18-07-2013 to move proposal for release of fund.
109 | Kamrup(M) | Government Art & Craft College, Kamrup(M) | 2011-12 | 5 | 1.79 | 0 | 1.79 | 0 | 0 | 2013-03-31 | AA accorded by P&D , Deptt. yet to move proposal for release of fund.
110 | Jorhat | Mahapurush Shri Shri Madhav Dev Kalashetra at Dhekia Khowa | 2013-14 | 2.25 | 0.81 | 0 | 0.81 | 0 | 0 | 2015-07-31 | AA accorded by P&D Deptt. on 07-10-2013. Rs.80.95 lakh (1st instlmnt) released by M/DoNER on 05-07-2013. Deptt. yet to move proposal for release of fund.
|  | Total: |  | 46.49 | 21.51 | 10.66 | 10.85
|  | Guwahati Development |  |  |  |  | 0
111 | Kamrup(M) | Construction of Multi Level Parking at Ambari, Guwahati, Kamrup(M) | 2008-09 | 11 | 3.47 | 1.35 | 2.12 | 38.9049 | 0 | 31/01/2010 | P&D recommended the release of Rs.205.61 Lakh on 15.09.2012. UC awaited. As advised by DONEr Rs. 175.60Lakh adjusted to sub-project at Paltanbazar.
|  | Transport |  |  |  |  | 0
112 | Kamrup(M) | Construction of Multi Level Parking at Paltan Bazar,Guwahati, Kamrup(M) | 2008-09 | 9.24 | 6.56 | 6.56 | 0 | 100 | 80 | 31/01/2010 | Total UC submitted is Rs.8.31Cr. including s/s(as advised by DONEr Rs. 175.60Lakh adjusted to sub-project at Paltanbazar). UC for Rs.41.00Lakh against grant component and Rs.52.42Lakh State share awaited from Deptt. As per information received from Transport Dept. , the project is completed and awaited commissioning.
|  | Urban Development |  |  |  |  | 0
113 | Dhubri | Dhubri Town Water Supply Scheme in Assam, Dhubri | 2006-07 | 10.27 | 8.78 | 6.72 | 2.06 | 76.5376 | 85 | 30/09/2008 | UC for Rs.44.32 lakh submitted to M/DoNER on 23-05-2013. from Dept. The project will be completed by Dec, 2013.
114 | Golaghat | Golaghat Town Water Supply Scheme Phase-II (MP), Golaghat | 2007-08 | 5.05 | 4.41 | 4.41 | 0 | 100 | 95 | 30/05/2009 | P& D Dept. recommended Rs. 37.24 lakh (s/s) on 8-12-2011. Uc awaited.
115 | Sibsagar | Sibsagar Town Water Supply Scheme, Sibsagar | 2007-08 | 16.39 | 11.8 | 7.69 | 4.11 | 65.1695 | 65 | 30/05/2007 | UC for Rs.269.26 lakh submitted to M/DoNER on 23-05-2013. Balance UC awaited from Dept.
116 | Sonitpur | Improvement of Roads and Natural Drainage System within Greater Tezpur Town, Sonitpur | 2007-08 | 25.52 | 3.48 | 3.48 | 0 | 100 | 50 | 29/05/2009 | Drainage work completed.UC forwarded to M/DONER on 25.06.2012. M/DoNER has sought clarification on UC and Dept. has been requested on 23-05-2013 to submit revised estimate of the project.Recast DPR awaited.
117 | Tinsukia | Margherita Piped water Supply scheme, Tinsukia | 2009-10 | 9.34 | 3.29 | 0 | 3.29 | 0 | 0 | 31/04/2012 | P&D Dept. recommended Rs.125.00 lakh in March, 2013. UC awaited. Work order issued.
118 | Darrang | Mangaldoi Water Supply Scheme, Darrang | 2009-10 | 12.61 | 4.45 | 0 | 4.45 | 0 | 0 | 31/04/2013 | P&D Dept. recommended the amount and UC awaited.
119 | lakhimpur | Improvement of Municipal Road in Narayanpur, lakhimpur | 2009-10 | 4.4 | 2.82 | 1.41 | 1.41 | 50 | 40 | 31-01-2012 | Rs.141.17 lakh received as 2nd instalment from M/DoNER.P&D Dept. recommended the sais amount on 20-12-2013. UC for the amount awaited.
120 | Barpeta | Barpeta Bus Terminus, Barpeta | 2010-11 | 1.86 | 0.66 | 0 | 0.66 | 0 | 0 | 31-03-2012 | AA accorded by P&D on 01/12/2010. Fund recommended for release
121 | Darrang | Kharupetia Water Supply Scheme, Darrang | 2010-11 | 19.81 | 6.99 | 0 | 6.99 | 0 | 0 | 28-02-2014 | P&D Dept. recommended the amount in March, 2013. UC awaited .
122 | Bongaigaon | Bongaigaon Town Water Supply Scheme, Bongaigaon | 2010-11 | 32.02 | 11.3 | 0 | 11.3 | 0 | 0 | 28-02-2014 | AA accorded by P&D on 28-01-2011. Dept. yet to move for release.
123 | Golaghat | Sarupathar Piped Water Supply , Golaghat | 2010-11 | 10.29 | 3.63 | 0 | 3.63 | 0 | 0 | 28-02-2013 | AA accorded by P&D on 28-01-2011. Dept. yet to move for release of fund.
124 | Sonitpur | Improvement of Roads in Biswanath chariali Town, Sonitpur | 2010-11 | 11.74 | 4.14 | 0 | 4.14 | 0 | 0 | 2013-03-30 | AA accorded by P&D on 28-01-2011. P&D recommended the 1st instment in March /2011. UC pending due to Public Complaint
125 | Jorhat | Construction of multistoried car parking cum city Hall, Jorhat | 2010-11 | 10.51 | 3.71 | 0 | 3.71 | 0 | 0 |  | Dept. yet to move for release of fund.
126 | Goalpara | Construction of 4 nos. of road including box culverts and pucca drainage in Lakhipur Town | 2010-11 | 14.25 | 5.1 | 0 | 5.1 | 0 | 0 | 2013-06-30 | AA accorded by P&D on 28-01-2012. Dept. yet to move for release of fund.
127 | Nagaon | Construction of Roadside drainage System including of Town roads in Nagaon Urban Area | 2012-13 | 19.25 | 6.93 | 0 | 6.93 | 0 | 0 | 31-09-2014 | AA accorded by P&D on 08-10-2012.
128 | Goalpara | Improvement and Development of Goalpara Town Road Network in Goalpara District | 2013-14 | 17.24 | 6.2 | 0 | 6.2 | 0 | 0 | 2014-11-30 | AA accorded by P&D Dept. on 29-05-2013. P&D Dept. recommended Rs.4.50 lakh in October, 2013. UC for the awaited.
129 | Dhemaji | Development of Roads for Dhemaji Town | 2013-14 | 11.98 |  |  | 0 | 0 | 0 | 2015-11-30 | AA accorded by P&D Deptt. on 11-12-2013.
130 | Dibrugarh | Proposed Town Hall at Dibrugarh | 2013-14 | 14.08 |  |  | 0 | 0 | 0 | 2015-11-30 | AA accorded by P&D Deptt. on 17-12-2013.
131 | Dibrugarh | Construction of Super Market Complex at Moran Revenue Town | 2013-14 | 6.84 |  |  | 0 | 0 | 0 | 2015-06-30 | AA accorded by P&D Deptt. on 02-01-2014.
132 | Tinsukia | Tinsukia Water Supply project (Phase-I) | 2013-14 | 35.83 |  |  | 0 | 0 | 0 | 2016-12-31 | AA accorded by P&D Deptt. on 02-01-2014.
133 | Tinsukia | Tinsukia Water Supply project (Phase -II) | 2013-14 | 35.81 |  |  | 0 | 0 | 0 | 2016-12-31 | AA accorded by P&D Deptt. on 02-01-2014.
|  | Total: |  | 325.09 | 87.69 | 23.71 | 63.98
|  | Public Health Engineering |  |  |  |  | 0
134 | Kamrup(M) | Stabilisation of Dispur Water Supply Scheme., Kamrup(M) | 2008-09 | 7.3 | 5.15 | 5.15 | 0 | 100 | 90 | 31/01/2010 | UC alongwith fund demand forwarded to M/DoNER. Funds (3rd ) awaited from M/DoNER. Target date of completion by Mar., 2014. 3rd instalment awaited form M/DoNER. Main line Pump under installation, TP 88%, UGR, ESR-Dispur Tea auction Centre to Hanuman Mandir.
|  |  |  | 7.3 | 5.15 | 5.15 | 0 | 100
|  | Sports |  |  |  |  | 0
135 | Jorhat | Development of Jorhat Stadium at Jorhat | 2006-07 | 2.69 | 1.93 | 1.93 | 0 | 100 | 95 | 30/07/2009 | UC for Rs.108.40 lakh (2nd) forwarded to M/DoNER on 30-08-2013. Funds awaited from M/DoNER.
136 | Cachar | Construction of Indoor Stadium at Silchar (MP) | 2007-08 | 4.94 | 4.36 | 3.49 | 0.87 | 80.0459 | 80 | 30/06/2009 | P&D Dept. recommended Rs. 87.23 lakh on 5-7-2012. UC for the amount awaited from dept.
137 | Barpeta | Construction of Chandi Barua Stadium at Howly Town, Barpeta (MP), | 2008-09 | 2.9 | 0.9 | 0.9 | 0 | 100 | 53 | 31/07/2010 | Reply to Clarification on UC as sought by M/DoNER awaited from dept..
138 | Dhubri | Construction of District Sports Complex at Jhagrapara , Dhubri (MP) | 2008-09 | 3.78 | 1.17 | 0 | 1.17 | 0 | 0 | 30/04/2010 | UC pending for Rs.116.66 lakh since 10-12-08. Implementing dept. has been asked to submit the UC.
139 | Nagaon | Hojai Stadium | 2013-14 | 5.71 | 2.05 | 0 | 2.05 | 0 | 0 | 2014-09-30 | AA accorded by P&D Dept. on 29-06-2013. Rs.205.30 lakh (1st instlmnt) released by M/DoNER on 8-10-2013.
140 | Hailakandi | Construction of RCC gallery of District Sports Association (Stadium Complex ,Hailakandi) | 2010-11 | 1.77 | 0.64 | 0.64 | 0 | 100 | 45 | 31/05/2012 | Clarification on UC alongwith latest QPR, Inspection Report, photographs forwarded to M/DoNER on 4-09-2013.
|  | Total: |  | 21.79 | 11.05 | 6.96 | 4.09 | 62.9864
|  | Industries & Commerce |  |  |  |  | 0
141 | Sonitpur | Approach Road to Balipara Industrial Growth Centre, Sonitpur | 2005-06 | 2.69 | 2.42 | 2.42 | 0 | 100 | 95 | 31/12/2007 | Completion Certificate and UC for Rs.26.86Lakh the State Share awaited from Deptt. will be submitted soon.
|  | Total: |  | 2.69 | 2.42 | 2.42 | 0 | 100
|  | NERMAC |  |  |  |  | 0
142 | Dhubri | Cashew processing plant at Mancachar, Dhubri | 2006-07 | 2.48 | 2.07 | 1.69 | 0.38 | 81.6425 | 100 | 30/11/2008 | P&D recommended Rs. 38.39 lakh in July, 2012. UC awaited from the dept..
|  | Agriculture |  |  |  |  | 0
143 | Nagaon | Comprehensive Development plan for college of Fisheries for augmentation Human Resources, Nagaon | 2010-11 | 8.75 | 3.09 | 0 | 3.09 | 0 | 0 | 31/06/2012 | Dept. yet to move proposal for release. AA accorded recently.
|  | Hill Areas |  |  |  |  | 0
144 | Dima Hasao | Haflong Water Supply Scheme Raw Water Pumping Main from Robinalla in Assam., Dima Hasao | 2003-04 | 1.42 | 0.72 | 0.72 | 0 | 100 | 34 | 31/07/2005 | DoNER sought clarification on the UC on 09-08-2007. Clarification awaited from dept.Reminder issued on 1-06-2012 & 21-03-2013.
145 | Dima Hasao | Conversion of 100 bedded Civil Hospital to 200 Bedded Hospital with construction of Staff Quarters buildings at Haflong in North Cachar Hills in Assam. | 2004-05 | 11.2 | 10.13 | 4.2 | 5.93 | 41.461 | 60 | 31/12/2006 | P&D recommended Rs.420.00 lakh (out of Rs.592.64 lakh 2nd instlmnt. ) in Jan/09. UC for the amount awaited from dept.Reminder issued on 30-09-2013.
146 | Karbi Anglong | Construction of RCC Bridge No.26/3 on Samar Ali Das Road in Karbi Anglong District in Assam. | 2004-05 | 1.68 | 1.53 | 0.59 | 0.94 | 38.5621 | 70 | 31/12/2005 | HAD yet to move for release of Rs.94.35(2nd instlmnt) since 19-06-07. Reminder issued.
147 | Karbi Anglong | Construction of RCC Bridge No.12/3 on Bakulia Rajapathar Road in Karbi Anglong District in Assam. | 2004-05 | 1.74 | 1.58 | 0.6 | 0.98 | 37.9747 | 70 | 31/12/2005 | HAD yet to move for release of Rs.98.14 lakh(2nd instlmnt) since 16-07-07. Reminder issued.
148 | Karbi Anglong | Construction of RCC Bridge No.1/2 on Manja to Hidim Teron Road in Karbi Anglong District in Assam. | 2004-05 | 1.78 | 1.62 | 0.82 | 0.8 | 50.6173 | 83 | 13/12/2006 | P&D Dept. recommended Rs. 32.88 lakh on 2-07-2012. UC awaited. Reminder issued .
149 | Dima Hasao | Greater Mahur Town Water Supply Scheme., Dima Hasao | 2006-07 | 5.12 | 1.61 | 0 | 1.61 | 0 | 20 | 31/12/2007 | P&D Dept. recommended Rs.100.00 lakh on 22-07-2011. UC awaited for the amount.
150 | Karbi Anglong | Construction of RCC Bridge No. 22/1 over River Diffolloo on Chowkihola – Panjan – Deithor – Malasi – Dirring – Kohora Road (CPDMDK Road) renamed Solonijan Chowkihola Kohora Road (Kohora PWD Division), Karbi Anglong | 2008-09 | 3.04 | 0.95 | 0 | 0.95 | 0 | 18 | 2011-03-04 | P&D Dept. recommended Rs. 28.61 lakh on 28-03-2012. UC for the amount awaited from Dept. Reminder issued on 27-09-2013.
151 | Karbi Anglong | Augmentation of Greater Diphu Water Supply Scheme, Karbi Anglong | 2008-09 | 27.67 | 8.55 | 0 | 8.55 | 0 | 0 | 31/072010 | Amount released directly from Finance dept. and UC awaited from dept.As per decision of meeting chaired by Hon'ble CM on 18-02-2012, the matter would be examined by PHE dept.
152 | Karbi Anglong | Greater Bokajan water supply Scheme, Karbi Anglong | 2008-09 | 10.04 | 3.1 | 0 | 3.1 | 0 | 7 | 17/12/2010 | Rs.3.10 crore directly released by Finance Dept. and UC awaited from deptt.
153 | Dima Hasao | Construction of RCC Bridge No. 28/1 on Dehangi Dayangmukh Road over Thaijuwari Nala & Langlodisa Nala (PWD Roads Haflong Division), Dima Hasao | 2008-09 | 3.55 | 1.12 | 0 | 1.12 | 0 | 35 | 30/09/2010 | P&D Dept. recommended Rs.111.76 lakh on 4-09-2013. UC awaited from dept. Reminder issued on UC on 26-09-2013.
154 | Karbi Anglong | Improvement of BBDC road at 31st km. | 2009-10 | 40.17 | 12.17 | 3.5 | 8.67 | 28.7592 | 30 | 16/06/2011 | Clarification on UC by M/DoNER. HAD is requested to correct the UC for Rs.350.00 lakh. P& D Dept. recommended Rs.866.93 lakh on 29-06-2013. UC for the amount awaited from dept.
155 | Karbi Anglong | Construction of RCC (a)bridge No.8/6 over River Dirring,(b)bridge No.18/1 over River Borjan, ©bridge No.19/1 over river Borjan, (d)bridge No.23/3 over river Donjan,(e)bridge No.27/3 over river Kakosang, (f)Bridge No.48/1 over River Deihori of Chowkihola-Panjan-Deithor-Malasi-Dirring-Kohora road(CPDMDK road),(2)Construction of RCC bridge No.2/1 over River Kohora on Kohora Bagori road, in Assam. | 2009-10 | 11.38 | 3.51 | 0 | 3.51 | 0 | 12 | 14/07/2011 | Administrative Approval accorded by P&D deptt. on 29-07-2009. P&D Dept. recommended Rs. 200.70 lakh on 29-03-2012. UC for the amount awaited from Dept.
156 | Karbi Anglong | Langklangvong Water Supply Scheme | 2009-10 | 5.96 | 2.1 | 0 | 2.1 | 0 | 0 | 2010-02-12 | AA accorded by P&D deptt. on 11-12-2009. Department yet to move for release of fund.
157 | Karbi Anglong | Development of Tourism Infrastructure at Bagori Entry Point of Kaziranga National park | 2009-10 | 3.3 | 2.32 | 1.16 | 1.16 | 50 | 15 | 2012-08-07 | UC for Rs.0.32 lakh balance of 1st instalment awaited from HAD. Rs.116.32 lakh( 2nd instalment) received from M/DoNER in Sept. 2013. P&D Dept. recommended the amount on 12-11-2013.
158 | Karbi Anglong | Deithor Minor Irrigation Project | 2009-10 | 2.22 | 0.78 | 0 | 0.78 | 0 | 14 | 31/12/2012 | P&D Deptt. recommended Rs.78.40 lakh on 15-12-2012.UC awaited from Dept. HAD has been requested to submit the same on 14-08-2012.
159 | Dima Hasao | Metalling & Black Topping of Gunjung- Maibong Road. | 2009-10 | 6.41 | 1.99 | 0 | 1.99 | 0 | 42 | 2012-10-04 | HAD has been requested on 26-07-2013 to correct the UC (Rs.125.00 lakh) as sought by M/Doner. Meanwhile , P&D Dept recommended Rs. 73.71 lakh on 5-07-2013 and UC awaited from deptt.
160 | Karbi Anglong | Construction of road from Hidpi to Lahorijan Goutom Bast Road | 2010-11 | 4.85 | 3.42 | 1.71 | 1.71 | 50 | 40 | 2012-10-04 | Rs.171.86 lakh (2nd instalmnt released by M/doNER on 14-11-2013. Dept. yet to move for release of fund.
161 | Karbi Anglong | Infrastructure Development of Road Transport system under Karbi Anglong Autonomous Council (KAAC) Part-I | 2010-11 | 1.83 | 0.65 | 0 | 0.65 | 0 | 25 | 2012-10-04 | P&D Dept. recommended Rs. 64.85 lakh on 28-03-2012. UC awaited from dept. Reminder issued on 25-09-2013.
162 | Karbi Anglong | Phumen phangcho Minor Irrigation Scheme | 2010-11 | 6.09 | 5.48 | 4.38 | 1.1 | 79.927 | 100 | 2012-10-31 | Rs.109.59 lakh released by M/DoNER as 3rd instlmnt. P& D recommended the amount on 27-08-2013. P&D also recommended Rs. 60.78 lakh (s/s) on 26-11-2013. UC for the amount awaited.
163 | Karbi Anglong | Greater Dokmoka Tekelangjan water supply scheme for fluoride, Arsenic/ iron affected areas from Dikrut, | 2011-12 | 18.66 | 6.71 | 0 | 6.71 | 0 | 0 | 2014-10-31 | AA accorded by P&D dept. on 14-12-2011. Dept. yet to move for release of fund.
164 | Karbi Anglong | Improvement of Ronghang Basti to Thekrajan Road | 2011-12 | 12.76 | 5.05 | 0 | 5.05 | 0 | 0 | 2013-06-30 | P&D Dept. recommended Rs. 504.90 lakh on 30-07-2013. UC awaited from HAD.
165 | Karbi Anglong | Kaku basti Irrigation Scheme | 2012-13 | 8.72 | 6.28 | 3.14 | 3.14 | 50 | 90 | 2013-10-30 | Rs.313.75 lakh (2nd instlmnt) & Rs.87.17 lakh (s/s) recommended by P&D dept. on 27-08-2013 & 28-01-2014. UC for the amount awaited from Dept.
166 | Dima Hasao | Metalling and Blacktopping of Ashalu Diduki Road including WBM(length=18km) under Mahur Road Division | 2012-13 | 6.4 | 2.3 | 0 | 2.3 | 0 | 0 | 2014-06-30 | AA accorded by P&D on 07-07-2012 .Dept. yet to move for release of fund.
167 | Karbi Anglong | Augmentation of donka mokam Piped Water Supply Scheme(PWSS) | 2012-13 | 7.07 | 2.54 | 0 | 2.54 | 0 | 0 | 2014-10-31 | AA accorded by P&D Deptt. on 7.11.2012. Dept. yet to move for release of Rs. 254.30 lakh(1st instlmnt).
168 | Karbi Anglong | Phangcho Basti Irrigation Scheme | 2012-13 | 9.53 | 3.43 | 0 | 3.43 | 0 | 40 | 2014-04-30 | Rs.342.85 lakh recommended by P&D Dept. on 27-08-2013. UC for the amount awaited.
169 | Dima Hasao | Improvement &Strenghtening of Hard Crust Road from Liasong to latko Border Road (Length 30Km) under Mahur Road Division | 2012-13 | 8.35 | 0 | 0 | 0 |  | 0 | 2014-06-30 | New project. AA accorded by P&D Deptt. On 17-01-2013.
170 | Dima Hasao | Construction of RCC Multistoried Auditorium Building attached to Halflong Government College at Halflong in Dima Hasao District. | 2012-13 | 2.3 | 0.83 | 0 | 0.83 |  | 0 | 2015-01-31 | AA accorded by P&D Deptt. on 01.02-2013. P&D Dept. recommended Rs.82.85 lakh on 02-01-2014.
171 | Dima Hasao | Construction of Home for Orphans and Destitute children at Haflong alongwith staff quarters including one Vocational Training Centre for children | 2013-14 | 2.98 | 1.07 | 0 | 1.07 |  |  | 3-0-11-2014 | AA accorded by P&D Deptt. on 29-06-2013.Dept. yet to move for release of fund.
172 | Karbi Anglong | Construction of RCC Bridge No. 4/3 on NH -36 '0' Point to Howragaht Karok Road at Kanki Engti Gaon via Monsing Rongchehon Gaon | 2013-14 | 2.21 | 0.79 |  | 0.79 | 0 | 0 | 2015-01-31 | AA accorded by P&D Dept. on 02-07-2013. Dept. yet to move for release of Rs.79.20 lakh(1st instlmnt)
173 | Karbi Anglong | Improvement of Lahorijan Gautom Basti Road (Ph-II, L-5.50km from Ch.9000.0m to Ch.14500.0m) | 2013-14 | 5.17 | 1.86 |  | 1.86 | 0 | 0 | 2015-03-31 | AA accorded by P&D Dept. on 18-07-2013. Dept. yet to move for release of Rs.186.05 lakh(1st instlmnt)
174 | Karbi Anglong | Langkhailu Irrigation Scheme | 2013-14 | 10.39 | 3.73 |  | 3.73 | 0 | 0 | 2015-09-30 | AA accorded by P&D Dept. on 05-10-2013. Dept. yet to move for release of Rs.373.00lakh(1st instlmnt)
175 | Karbi Anglong | Farkongcho Irrigation Scheme | 2013-14 | 10.22 | 3.68 |  | 3.68 | 0 | 0 | 2015-09-30 | AA accorded by P&D Dept. on 03-10-2013. Rs. 367.70 lakh released as 1st instlmnt by M/DoNER on 24-09-2013. Dept. yet to move for release of fund.
176 |  | Total: |  | 254.21 | 101.6 | 20.82 | 80.78 | 20.4921
177 |  | WPT &BC |  |  |  |  | 0
178 | Udalguri | Improvement of Tangla Kachubill Road . | 2010-11 | 10.8 | 9.62 | 7.7 | 1.92 | 80.0416 | 80 | 30.11.2012 | Rs. 192.32 lakh(final instlmnt) recommended by P&D Dept. in Aug., 2013. UC awaited from dept.
179 | Udalguri | Improvement of Moholiapara Dongapara Borongajuli PWD Road. | 2010-11 | 8.35 | 7.45 | 5.96 | 1.49 | 80 | 32 | 2012-12-31 | Rs.148.85 lakh released as 3rd &final instlmnt recommended by P&D on 26-02-2014. UC for the amount awaited.
180 | Kokrajhar | Upgradation of NT Road through Ramphalbil Bazar to all weather roads of SPT bridge into RCC Bridge (International Border Area) | 2011-12 | 7.64 | 2.7 | 0 | 2.7 | 0 | 0 | 2012-10-31 | AA accorded by P&d dept. on 20-07-2011. 1st instalment (Rs. 269.71 lakh recommended by P&D on 11-02-2014. UC awaited from Dept.
181 | Udalguri | Improvement of Chintagaon Botiamari Road in Udalguri District | 2011-12 | 8.98 | 3.22 | 3.22 | 0 | 100 | 35 | 2013-07-31 | UC for Rs. 321.72 lakh forwarded to M/DoNER on 26-07-2013. Funds awaited from M/DoNER.
182 | Udalguri | Construction of Road with MTBT from UT road at Dimakucji Don- Bosco School to Badlapara via Kalikhola Road, Udalguri | 2011-12 | 6.21 | 2.23 | 0 | 2.23 | 0 | 0 | 2014-06-30 | A/A accorded by P & D Deptt on 26-12-2011. P&d Dept. has recommended Rs. 2.23 crore in March, 2012. UC for the amount awaited.
183 | Kokrajhar | Upgradation of Road from NH-31( C) via Serfenanguri, Nepalpara, Athiabari, Ebargaon, Thaigiriguri and No.2 Hazarkiapara to Kapuragaon | 2011-12 | 7.6 | 2.7 | 0 | 2.7 | 0 | 0 | 2013-12-31 | A/A accorded by P & D Deptt on 27-12-2011. Rs.269.79lakh( 1st installment) released on 15-12-2011 by M/DONER. Fund released directly from Finance dept. Rs.24.80lakh (s/s)
184 | Kokrajhar | Construction of RCC Br.No. 8/1 over Saral Bhanga on Dotmo Balajan Road. | 2011-12 | 12.02 | 4.29 | 0 | 4.29 | 0 | 0 | 2013-08-31 | Rs.428.55 lakh recommended by P&D Dept. on 27-01-2014. UC for the awaited.A/A accorded by P & D Deptt on 6-01-2012.
185 | Chirang | Construction of Fly over at the intersection of Pramathesh Barua Road and N.F. railway Track at Bijni Town | 2011-12 | 19.63 | 7.07 | 5.63 | 1.44 | 79.6322 | 40 | 2013-06-30 | UC for Rs.563.21 lakh forwarded to M/doNER on 21-01-2014. P&D has recommended Rs. 140.00 lakh(S/S) on 27-01-2014. UC for the balance amount(G/S) & S/S awaited.
186 | Udalguri | Flow Irrigation Scheme from River Kulsik at Palashgarh under tangla irrigation Division, Udalguri District | 2011-12 | 19.28 | 13.39 | 6.87 | 6.52 | 51.3069 | 45 | 2013-06-30 | Rs. 652.38 lakh(2nd instlmnt) released by M/DoNER on 07-11-2013. Dept. yet to move for release of fund. Rs.90.00 lakh (S/s) recommended by P&D in July, 2013. UC awaited.
187 | Kokrajhar | Tamulpur Piped Water Supply Scheme | 2011-12 | 2.94 | 1.04 | 0 | 1.04 | 0 | 0 | 2013-12-31 | Amount released and UC awaited from dept.
188 | Baska | Construction of proposed Stadium at Musalpur in Baska Distict. | 2010-11 | 9 | 3.18 | 3.18 | 0 | 100 | 44 | 2013-11-30 | UC for Rs. 317.65 lakh forwarded to M/DoNER on 5-02-2014. Funds awaited from M/DoNER.
189 | Kokrajhar | Khowra Flow Irrigation Scheme | 2012-13 | 3.55 | 1.28 | 0 | 1.28 | 0 | 0 | 2013-10-31 | AA accorded by P&D dept. on 5th July, 2012. P&D Dept. recommended Rs.127.90 lakh on 01-06-2013. UC awaited for the said amount from dept.
190 | Kokrajhar | Conversion of washed out SPT Bridge No.2/1 over river Hell into RCC Bridge on Shialmari Moinaguri Road in Kokrajhar District. | 2012-13 | 19.68 | 7.08 | 0 | 7.08 | 0 | 0 | 2014-12-31 | AA ccorded by P&D Deptt. on 25-01-2013. Rs. 708.15 lakh has been released as 1st installment and dept. has been requested on 10-07-2013 to move proposal for release of fund. | New Project. AA being accorded by P&D Deptt.
191 | Baska | Construction of Road from Rongaichera Bazar to Bhola Bazar | 2012-13 | 3.66 | 0 | 0 | 0 |  | 0 | 2014-06-30 | New Project. AA accorded by P&D Deptt. on 18-02-2013. Dept.yet to move for release of fund. | New Project. AA being accorded by P&D Deptt.
192 | Baska | Construction of Road from Gopalpur(Kekerikuchi) to Niz-Kaurbaha(13.5Km length) including construction of RCC Bridge No. 5/1(15.00m length) under PWD, Musalpur(R&B) Division) | 2012-13 | 11.71 | 4.21 | 0 | 4.21 | 0 | 0 | 2015-02-28 | Rs.250.00 lakh recommended by P& D Dept. on 16-11-2013. UC for the amount awaited.
193 | Kokrajhar | Rajendrapur flow Irrigation Scheme | 2012-13 | 21.47 | 7.73 | 0 | 7.73 | 0 | 0 | 2016-02-28 | New project. AA accorded by P&D Deptt. on 21-03-2013. Dept. yet to move for release of fund.
194 | Udalguri | Construction of Road from paoriputa to Natun Panbari with black topping and construction of RCC Bridge over River Pasnai in Udalguri District. | 2013-14 | 7.68 | 2.76 | 0 | 2.76 | 0 | 0 | 2014-11-30 | AA accorded by P&D Dept. on 29-05-2013. P&D Dept. recommended Rs.2.76 lakh in October, 2013. UC for the awaited.
195 | Kokrajhar | College of Nursing at Kokrajhar | 2013-14 | 14.27 | 5.18 | 0 | 5.18 | 0 | 0 | 2014-05-30 | New project. AA accorded by P&D Dept. on 03-06-2013.
196 | udalguri | Improvement/upgradation of Mangaldoi Bhutiachang Samrang Road fromCH-47722M to CH-48292 and from 50000 to CH-62500M including cross -drainage works | 2013-14 | 29.92 | 10.77 | 0 | 10.77 | 0 | 0 | June,2014 | New project. A accorded by P&D Dept. on 29-05-2013.
197 | Udalguri | Improvement of raod from Budura to Parbahuchuba Dimakuchi PWD road at batabari via Khasiachuba, Barangababari | 2013-14 | 11.09 | 3.99 | 0 | 3.99 | 0 | 0 | 2015-01-31 | New project . AA accorded by P&D Dept. on 20-07-2013.
198 | Udalguri | Construction of RCC Br. No.9/8 over laska on Dauluguri Dotma Road | 2013-14 | 1.75 | 0 | 0 | 0 | 0 | 0 | 2015-07-31 | New project . AA accorded by P&D Dept. on 18-07-2013.
199 | Kokrajhar | Conversion of SPT Br.No.10/1, 12/3, 14/2 and 16/1 into RCC bridge on metd. Kokrajhar, Bahalpur Road. | 2013-14 | 6.99 | 2.51 |  | 2.51 | 0 | 0 | 2015-09-30 | New project . AA accorded by P&D Dept. on 21-10-2013.
200 | Udalguri | Improvement of Road from Kharibari to Jamuguri in Udalguri | 2013-14 | 13.29 | 4.78 |  | 4.78 | 0 | 0 | 2016-10-31 | New project . AA accorded by P&D Dept. on 28-10-2013. Rs.478.30 lakh (1st instlmnt) released by M/DoNER. Dept. yet to move for release of fund.
201 | Baska | Improvement of Kamdaltal Nikashi Road from Kuchi to Bhaldonga | 2013-14 | 4.16 | 1.5 |  | 1.5 | 0 | 0 | 2015-07-31 | New project . AA accorded by P&D Dept. on 5-11-2013. Rs.149.67 lakh (1st instlmnt) released by M/DoNER. Dept. yet to move for release of fund.
|  | BAC Areas Projects implemented by BTC |  |  |  |  | 0
202 | Kokrajhar | Drinking water supply scheme at Gossaigaon, kokrajhar | 2000-01 | 3.63 | 2.57 | 2.57 | 0 | 100 | 80 | 31-07-2005 | M/DoNER directed the state govt. to complete the project from state's own resources . Accordingly, WPT &BC Dept. has been intimated .
203 | Kokrajhar | Special Area Game Centre at Kathalguri, Kokrajhar | 2000-01 | 9.29 | 8.91 | 8.91 | 0 | 100 | 100 | 31-03-2006 | Proposal for S/S not received from WPT&BC Deptt.
204 | Kokrajhar | Gauhati University Campus at Kokrajhar. | 2002-03 | 5 | 4.62 | 4.62 | 0 | 100 | 95 | 31-03-2004 | P&D Dept. recommended Rs.38.50 lakh(S/S). UC & CC awaited from WPT &BC Dept.
|  | Total |  | 279.59 | 124.78 | 48.66 | 76.12 | 38.9966