## Ongoing NLCPR projects
Status of ongoing Projects under Non Lapsable Central Pool of Resources (as on 31st March, 2015.)
(Rs. In crore)
Sl. No. | District | Name of project | Year of sanction | Approved cost | Total Fund released by GOI (90% grant) | Total fund recommended by P&D Dept. | UC submitted to DONER | UC pending (col.6-col.8) | % tage of utilisation | Physical progress (%) | Target date of completion | status
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Public Works
1 | Tinsukia | Construction of RCC Bridge No.4/3, 10/2 and 14/1 on Pengri Philobari Road in Tinsukia District | 2004-05 | 2.34 | 2.17 | 1.85 | 1.85 | 0.32 | 85.2535 | 79 | 31-12-05 | Dept. yet to move for release of Rs.0.32 lakh since 11.9.06. Reminder issued to PWD® on 4-06-2012. Out of 3 bridges, 2 bridges completed and construction of one bridge no. 4/3 halted due to cost escalation.
2 | Karbi Anglong | Construction of RCC Bridge No.26/3 on Samar Ali Das Road in Karbi Anglong District in Assam. | 2004-05 | 1.68 | 1.53 | 0.59 | 0.59 | 0.94 | 38.5621 | 70 | 31/12/2005 | HAD yet to move for release of Rs.94.35(2nd instlmnt) since 19-06-07. Reminder issued.
3 | Karbi Anglong | Construction of RCC Bridge No.12/3 on Bakulia Rajapathar Road in Karbi Anglong District in Assam. | 2004-05 | 1.74 | 1.58 | 0.6 | 0.6 | 0.98 | 37.9747 | 70 | 31/12/2005 | HAD yet to move for release of Rs.98.14 lakh(2nd instlmnt) since 16-07-07. Reminder issued.
4 | Karbi Anglong | Construction of RCC Bridge No.1/2 on Manja to Hidim Teron Road in Karbi Anglong District in Assam. | 2004-05 | 1.78 | 1.62 | 1.15 | 0.98 | 0.64 | 60.4938 | 75 | 13/12/2006 | P&D Dept. recommended Rs. 32.88 lakh on 2-07-2012. UC awaited for Rs.98.27 lakh forwarded to MDoNER on 28-11-2014.
5 | Sibsagar | Construction of RCC Bridge No.6/1, 7/1, 8/1, 8/2, 9/1, 11/1 & 11/2 on Sepon - Suffery Road in Sibsagar Dist. With approaches. | 2005-06 | 4.11 | 2.93 | 2.93 | 2.93 | 0 | 100 | 75 | 2013-12-31 | UC for Rs.293.17 lakh forwarded to M/DoNER on 03-10-2013. six nos. of bridges completed. Rs.29.20 lakh (s/s) recommended by P&D.
6 | Nalbari | Construction of RCC Bridge No.16/1, 19/1 & 19/3 on Bagals Road in Nalbari Dist. With approaches. | 2005-06 | 4.05 | 2.39 | 2.37 | 2.37 | 0.02 | 99.1632 | 70 | 28-2-07 | Work has been withdrawn from the previous contractor. P&D Dept. has recommended Rs. 12.5233 lakh(S/s) in Feb., 2012. Dept.'s action awaited. 2nd query on UC by M/DoNER on 21-06-2013. Dept. has been requested on 18-02-2015 to submit fresh UC alongwith latest QPR.
7 | Dhemaji | Construction of RCC Bridge No.10/1 on Gogamukh Ghillamara Road in Dhemaji Dist. | 2005-06 | 1.08 | 0.94 | 0.94 | 0.74 | 0.2 | 78.7234 | 100 | 30-9-07 | 100% physical progress.Rs.20.56 lakh released by MDoNER in Nov., 2014 and recommended by P&D on 16-02-2015. UC awaited. Rs.10.84 lakh(s/s) recommended by P&D.
8 | Dibrugarh | Construction of RCC Bridge No.2/1on Bamunbari Jariguri Road in Dibrugarh Dist. With approaches. | 2005-06 | 1.08 | 0.78 | 0.78 | 0.78 | 0 | 100 | 86 | 31-5-07 | 3rd installment not yet released. Reply on Query on UC forwarded to MDoNER on 22-09-2014. Rs.17.00 lakh(S/s) recommended by P&D.
9 | Dibrugarh | Construction of RCC Bridge No.10/1on Khowhng - Bhamun Road in Dibrugarh Dist. With approaches. | 2005-06 | 1.03 | 0.93 | 0.82 | 0.82 | 0.11 | 88.172 | 100 | 2013-06-30 | UC for Rs. 38.24 lakh forwarded to MDoNER on 13-02-2014. Rs.7.90 lakh(S/s) recommended by P&D.
10 | Dhemaji | Construction of RCC Bridge No.1/1, 5/1, and 3/1 on Bahirjonai-Berachapari Road in Dhemaji District with approaches. | 2005-06 | 5.52 | 3.96 | 2.29 | 2.29 | 1.67 | 57.8283 | 68 | 2013-06-30 | UC for Rs.78.185 lakh forwarded to M/DoNER on 12-12-2013. Revised estimate for completion of balance work prepared. Work withdrawn from original contractor. Tender for balance work under process.
11 | Dhemaji | Construction of RCC Bridge No.1/1, 4/1, and 5/1 on Sripani - Jengrai Road in Dhemaji District with appr. | 2005-06 | 3.02 | 2.17 | 2.17 | 1.9 | 0.27 | 87.5576 | 100 | 31-8-07 | UC for Rs.94.36829 lakh out of Rs.121.85lakh(2nd instlmnt) forwarded to MDoner on 18-07-2014.
12 | Sonitpur | Construction of RCC Bridge No.2/3, 5/1, 9/1, 11/1, 15/3, 16/1,18/1 & 19/4 on Itakhola Pavoi Road in Sonitpur District with approaches. | 2005-06 | 8.57 | 6.24 | 5.83 | 4.56 | 1.68 | 73.0769 | 79 | 30-4-07 | UC of 1st Inst submitted in July’12 &2nd Inst released in july’13(gap of one year) Recommended by P&D. Rs.50.71 lakh recommended by P&D.Rs.105.49169 (G/s) recommended by P&D on 23-3-2015.
13 | Dhubri | Construction of RCC Bridge No.27/2,28/1,29/1,30/2,32/2,35/1 & 45/1 on Dhubri Kachugaon Road in Dhubri District | 2006-07 | 5.16 | 3.68 | 3.57 | 3.57 | 0.11 | 97.0109 | 85 | 30-11-07 | PWD has been reminded for submission of fresh documents inrespect of UC for Rs. 41.99 lakh on 30-09-2013.Render has been done by the deptt. Rs. 41.304 lakh (S/s) recommended by P&D on 5-02-2015. UC for the amount awaited.
14 | Goalpara | Construction of RCC Bridge No.2/1 & 4/2 on Gour Nagar Tikirkilla Road in Goalpara Dist. With approches. | 2006-07 | 3.55 | 2.52 | 2.52 | 2.24 | 0.28 | 88.8889 | 63 | 30-11-07 | Work withdrawn and allotted to another contractor. UC submitted on 12.12.13. PW Deptt yet to furnish information. Query on UC from M/DoNER awaited from PW dept. since 18-01-2014. Rs.16.124 lakh(S/S) recommended by P&D.
15 | Cachar | Construction of RCC Bridge No.44/2,38/1,43/1 & 43/2 on Silchar-Hailakandi Road in Cachar Dist. With approaches | 2006-07 | 3.53 | 2.51 | 2.51 | 2.51 | 0 | 80.0797 | 96 | 30-11-07 | Reply to query on UC alogwith fresh UC was forwarded to MDoNER on 16-09-2013. 3rd instalment awaited from MDoNER.3rd instalment awaited from MDoNER.
16 | Cachar | Construction of Rd. and minor bridge from Matinagar to Bhuban Hill Temple(Ph-I) (MP), Cachar District | 2007-08 | 3.26 | 2.94 | 2.34 | 2.34 | 0.6 | 79.5918 | 87 | 31/10/2009 | Rs.59.00 lakh(3rd instlmnt) released by M/DoNER on 10-10-2013. Rs.14.24 lakh(S/s) recommended by P&D.
17 | Cachar | Construction of Road from Bhangarpar to Chandranathpur via Baburbazar.(MP), Cachar District | 2007-08 | 2.49 | 1.8 | 1.64 | 1.4 | 0.4 | 77.7778 | 82 | 31/12/2009 | UC for Rs. 60.17 lakh forwarded to M/DoNER on 5-1-2013. Funds awited from M/DoNER.
18 | Cachar | Construction of RCC major bridge at 7th km. of Kathal Road over river Ghagra (MP), Cachar District. | 2007-08 | 2.5 | 2.25 | 2.23 | 1.79 | 0.46 | 79.5556 | 96 | 31/03/2010 | Rs.46.15 lakh (3rd) instlmnt received on 13-12-2013 and recommended by P&D. Rs.24.93 lakh (S/s) recommended by P&D.
19 | Darrang | Upgradation of Dolgaon Town to Sialmari via Dekerigaon Kharpunihabi road (MP), Darrang District | 2007-08 | 2.52 | 2.12 | 2.12 | 1.8 | 0.32 | 84.9057 | 100 | 31/10/2009 | work physically completed. CCwill be submitted shortly.
20 | Dibrugarh | Construction of RCC br. No 57/1 on Gourisagar Moran road and Construction of RCC Br. No 15/2 on Naharkatia- Tingkhong Road in Dibrugarh district with approaches . | 2008-09 | 4.06 | 2.9 | 2.74 | 1.17 | 1.73 | 40.3448 | 50 | 31-05-2010 | P&D Dept. recommended Rs.5.54866 lakh in Feb., 2012. M/DoNER has requested on 19-09-2013 to submit the UC, accordingly PWD has been requested on 25-10-2013 to submit the same.
21 | lakhimpur | Construction of RCC br. No 18/2 over stream Bahanigaon & Br. NO 19/1 over river kachikata on laluk- Narayanpur Road in lakhimpur District with Approaches . | 2008-09 | 2.09 | 1.5 | 1.5 | 1.5 | 0 | 100 | 95 | 31-07-2010 | Could not complete as final Inst. yet to receive.parawise reply furnished on 11/11/13 raised on UC of 2nd Inst. No correspondence from M/Doner yet 3rd Inst.not yet received as shown in the statement. Rs.20.43 lakh (S/s) nrecommended by P&D.
22 | Dibrugarh | Construction of roadside drain cum Footpath and provision for roadside streetlight illumination in Nahakatia Town in Dibrugarh Dist. under Dibrugarh Rural Road Division . | 2008-09 | 6.45 | 4.54 | 4.54 | 4.54 | 0 | 100 | 42.51 | 28-02-2010 | UC for Rs. 255.43 lakh forwarded to MDoNER on 4-09-2014. Funds awaited.
23 | Goalpara | Construction of RCC Br. No. 32/1 on A.T. Road (old) including approaches, Protection works, Goalpara in Assam | 2008-09 | 7.39 | 4.62 | 4.62 | 3.07 | 1.55 | 66.4502 | 57 | 31-10-2010 | Could not complete as final Inst yet to receive.UC for Rs. 21,42644 lakh forwarded to MDoNER on 8-12-2014. Rs.17.26 lakh (s/s) & Rs.22.26365 lakh (G/s)recommended by P&D on 6-08-2013 & 10-09-2014. PWD has been requested on 23-03-2015 to submit Fresh cumulative UC alongwith UC &latest QPR and other documents.
24 | Hailakandi | MT &BT of from Swapanpur to Ramchandi Road (MP), Hailakandi District | 2008-09 | 3.8 | 2.73 | 2.73 | 2.73 | 0 | 100 | 92 | 31/03/2009 | 2nd instalment awaited from MDoNER. Query raised by MDoNER on 11-12-2013 regarding physical progress, project delayed inordinately and to furnish latest documents. Reply of query by M/DoNER forwarded to on 04-09-2013. Funds awaited from M/DoNER.
25 | Morigaon | Construction of RCC Br. No 2/1on Nandini Karaimari Road | 2009-10 | 6.58 | 2.04 | 2.04 | 2.04 | 0 | 100 | 23 | 31-02-2011 | 2nd instalment awaited from MDoNER. Query raised by MDoNER on 11-12-2013 regarding physical progress, project delayed inordinately and to furnish latest documents. Reply awaited from deptt. Rs.22.694 lakh(S/s) recommended by P&D Dept. on 31-07-2014.
26 | Sibsagar | Construction of RCC Br. No 3/2,5/2 & 5/4 on Rupsir Ali | 2009-10 | 2.1 | 1.51 | 1.51 | 1.28 | 0.23 | 84.7682 | 70 | 2012-10-30 | 3rd installment yet to be received.
27 | Nagaon | Construction of RCC Br. No 7/1,15/1 & 19/1 on Nagaon- Barapujia Road with approaches in Nagaon Dist | 2009-10 | 4.66 | 1.46 | 1.46 | 1.46 | 0 | 100 | 60 | 31-08-2011 | Last UC for Rs. 23.26807 alakh forwarded to MDoNER on 6-02-2015. Funds awaited from MDoNER.
28 | Morigaon | Construction of RCC Br. No 12/1 on Goroimari-Dewaguri road with approaches in Nagaon Dist | 2009-10 | 3.17 | 1.13 | 1.13 | 1.13 | 0 | 100 | 40 | 31-03-2011 | UC for Rs. 1.13 crore forwarded to M/DoNER on 9-06-2014.
29 | Karimganj | Improvement / upgradation of Chenchorie Elgin Road including major RCC bridge over river Ghagra. | 2009-10 | 11.81 | 8.18 | 4.17 | 4.17 | 4.01 | 50.978 | 73 | 31-10-2011 | Rs.401.42 lakh (2nd instalment) received from MDoNER on 26-09-2014. Dept. yet to move for release.Rs. 73.56 lakh(S/s) recommended by P&D.
30 | Udalguri | Improvement of Tangla- Bhergaon -ramgaon road in Udalguri District. | 2009-10 | 10.43 | 9.2 | 9.2 | 7.36 | 1.84 | 80 | 98 | 28-02-2013 | Rs.184.14 lakh(3rd instalment) received from MDoNER on 12-09-2014. Rs.184.079 lakh recommended by P&D on 10-11-2014. Rs.102.29 lakh(S/s) recommended by P&D.
31 | Nagaon | Upgradation of Nagaon- Bhuragaon Road via Dhing ( SH-10) in Nagaon | 2009-10 | 11.15 | 10.27 | 10.22 | 9.1 | 1.17 | 88.6076 | 99 | 30-04-2011 | Last UC for Rs.87.89 lakh submitted to M/DoNER on 9-6-2014. Rs.110.31 lakh (S/s) recommended by P&D . UC awaited.
32 | Nagaon | Construction of RCC Br. No 6/1 , 9/1 & 10/1 on Ambagaon – Kathpara solmari Singrai Rd. ( NG-17) in Nagaon Dist | 2009-10 | 2.39 | 2.14 | 2.14 | 2.14 | 0 | 100 | 60 | 28-02-2012 | UC submitted to M/DoNER on 29-01-2013. CC awaited from dept.
33 | Dibrugarh | Improvement of Road Net work leading towards Dibru- Choikhowa National Park Construction of RCC Br. No 1/1over river Doomdoma on old A.T road | 2009-10 | 7.47 | 5.38 | 5.38 | 5.19 | 0.19 | 96.4684 | 94 | 30-04-2013 | Rs.17.78 lakh(G/S) recommended by P&D on 26-06-2014. UC awaited. Clarification on UC forwarded to MDoNER on 17-11-2014. 3rd instalment to receive.Rs.40.00 lakh recommended by P&D.
34 | Nagaon | Construction of RCC Br. No 4/1 on Dimow-Raidongia road over river Sonai Under Nagaon Rural road Division in Nagaon. | 2010-11 | 2.71 | 0.96 | 0.96 | 0.96 | 0 | 100 | 40 | 30-04-2012 | UC for Rs.96.50 lakh forwarded to M/doNER on 25-07-2014. Funds awaited from MDoNER.
35 | Jorhat | Street lighting in Jorhat city leading to jorhat Airport | 2010-11 | 2.13 | 1.5 | 1.5 | 1.5 | 0 | 100 | 75 | 30-09-2011 | UC for Rs.33.84 lakh forwarded to M/DoNER on 26-112014. Funds awaited from MDoNER.
36 | Nagaon | Construction of RCC Br. No 3/1 on Majgaon –Santipur Rd. over river sonai with approaches in Nagaon Dist | 2010-11 | 3.33 | 1.19 | 1.19 | 1.19 | 0 | 24 | 80 | 30-06-2012 | UC for Rs.118.76 lakh forwarded to M/DoNER on 07-10-2013. May, 2013. Funds awaited from M/DoNER.
37 | Tinsukia | MT & BT from Borhapjan- samdang Road to Sukanguri L.P. School. | 2010-11 | 3.22 | 2.29 | 2.29 | 2.29 | 0 | 100 | 87 | 31-03-2012 | UC submitted but query raised by MDoNER. 3rd instalment awaited from MDoNER.
38 | Tinsukia | MT & BT from Circuit House Tinsukia to NH 37 via Okanimuria Borguri | 2010-11 | 5.24 | 3.7 | 3.26 | 1.86 | 1.84 | 50.2703 | 65 | 28-02-2012 | Rs. 184.34 lakh (2nd installment) has been released by M/DoNER on 26-06-2013. Dept. requested on 6-07-2013 to move proposal for release of fund.
39 | Sibsagar | Construction of Mahmora Ali with RCC Br.No. 9/2 Sivsagar Dist. | 2010-11 | 7.72 | 2.72 | 0.4 | 0 | 2.72 | 0 | 0 | 28-02-2013 | Work in progress. Rs.40.25 lakh recommended and UC is being submitted.
40 | Bongaigaon | Constuction of RCC Br. No. 1/2over river Aie at Chilapara, Kahibari villages on the road from Kokrajhar NH -31 to Nowgong, Nanikpur NH-31 via Kirtanpar Numberpara villages under Bongaigaon Rural Road Division. | 2010-11 | 40.01 | 14.26 | 12.61 | 5.21 | 9.05 | 36.5358 | 24 | 30-11-2013 | Delayed due to court case. Now work started. UC for RS.5.21 crore submitted to MDoNER. Rs.740.192 lakh recommended by P&D on 19-11-2014. UC for the amount awaited.
41 | Chirang | Construction of Rcc Br.over river Aie. | 2010-11 | 78.84 | 70.25 | 70.25 | 67.54 | 2.71 | 96.1423 | 95 | 30-11-2013 | last UC for Rs.860.39 lakh submitted to M/DoNER on 23-05-2013. Balance UC awaited from dept.
42 | Dibrugarh | Construction of RCC Br.No.1/2 & 4/1 on old AT Road, Khowng, Dibrugarh | 2010-11 | 2.9 | 2.09 | 2.09 | 2.09 | 0 | 100 | 80 | 30-11-2013 | Clarification on UC sought by MDoNER & PWD requested on 6-5-2014. 3rd instalment awaited
43 | Dibrugarh | Construction of Mora Netai Road Dibrugarh | 2010-11 | 3.03 | 2.14 | 2.14 | 1.67 | 0.47 | 78.0374 | 76 | 30-11-2012 | 2nd instalment released by MDoNER on 23-08-2012. Query on UC submitted to MDoNER on 28-12-2012.
44 | Sibsagar | Construction of Tiphuk Jajali Pukhuri Road with Rcc Br. No. 3/3 in Sivsagar. | 2010-11 | 5.6 | 3.96 | 2.88 | 1.99 | 1.97 | 50.2525 | 41 | 30-11-2012 | Query on UC forwarded to MDoNER on 5-08-2013. Balance UC awaited from dept. Rs.25.00 lakh recommended by P&D.
45 | Morigaon | Construction of RCC Bridge No.24/1 on Morigaon Moirabari in Morigaon District. | 2010-11 | 3.16 | 2.24 | 1.71 | 1.12 | 1.12 | 100 | 46 | 31-07-2012 | UC for Rs.113.11 lakh forwarded to M/DoNER on 12-12-2014.. . Rs. 12.44 lakh (S/s) released by P&D in May, 2013.
46 | Jorhat | Construction of RCC Bridge No. 13/1, 13/2, 20/2 on Mohbandha Road. | 2010-11 | 6.14 | 2.19 | 2.19 | 2.19 | 0 | 100 | 27 | 31-01-2013 | Last UC for Rs. 28.054 lakh(G/s) and Rs.24.35 lakh(S/s) submitted to MDonEr on 19-03-2015.
47 | Cachar | Construction of RCC Br. No.2/2 & 2/3 renamed as 3/1 & 4/1) on Shyamaprasadpur - Dossgram road via Swapnargul over stream Singrai in Cachar District. | 2010-11 | 2.57 | 1.83 | 1.83 | 1.83 | 0 | 100 | 100 | 31-07-2012 | Project completd. CC under process for onward submission to MDoNER. MDoNER sought updated QPR & status ending March, 2014.
48 | Kamrup(M) | Construction of Zoo Zaparigoog Road , Guwahati. | 2010-11 | 6.2 | 4.46 | 4.46 | 4.46 | 0 | 100 | 80 | 31-12-2012 | UC for Rs. 2.23 crore forwarded to M/DoNER on 11-06-2014.MDoNER sought clarification on 12-06-2014 and deptt. has been requested on 5-12-2014 to submit the same. Funds awaited. Rs.24.79 lakh(S/s) recommended by P&D.
49 | Sibsagar | Improvement of road network at Sonari Town under Choraideo Rural road Division | 2010-11 | 7.24 | 5.22 | 3.86 | 2.61 | 2.61 | 50 | 62.86 | 30-06-2012 | Rs.260.55 lakh (2nd instlmnt) released by M/DoNER on 22-10-2013. Dept. yet to move for release of fund.
50 | Nagaon | Construction of Br. No. 2/1 & 4/1 on Raha Barapujia road over river Botamari and Hatibanda with approaches in Nagaon District | 2010-11 | 3.69 | 2.57 | 2.57 | 2.57 | 0 | 100 | 85 | 2013-03-31 | UC for Rs.126.33 lakh forwarded to MDoNER on 19-02-2015. Funds awaited from MDoNER. Rs.35.60 lakh (S/s) recommended by P&D.
51 | Jorhat | Improvement of J.B. Road in Jorhat District | 2011-12 | 2.97 | 2.12 | 2.12 | 1.06 | 1.06 | 50 | 50 | 2011-06-30 | UC for Rs.105.82 lakh 2nd instalment awaited from Deptt.. Rs.11.76 lakh(S/s) recommended by P&D.
52 | Darrang | Construction of Road from Rangamati to Kalaigaon Road (between) Janaram Chowka to Aaola Chowka in Darrang District. | 2011-12 | 5.75 | 3.94 | 3.94 | 2.03 | 1.91 | 51.5228 | 65 | 2014-05-31 | 2nd instalment of Rs.191.21 L released by MdoNER in October, 2014 & recommended by P&D Deptt. Rs.14.317 l akh(S/s) recommended by P&D on 30-10-2014. Rs.79.86 lakh(G/s) recommended by P&D on 24-2-2015.
53 | Dibrugarh | Sessa T.E. to Timona Road in Dibrugarh | 2012-13 | 4.01 | 2.84 | 1.41 | 1.41 | 1.43 | 49.6479 | 70 | 2014-05-31 | Rs.142.66 lakh (2nd instlmnt) received from MDoNER. Rs. 15.61 lakh (S/s) recommended by P&D.
54 | Dibrugarh | Construction of Maijan Thakurbari road to Mukalbari road in Dibrugarh Dist. | 2012-13 | 8.11 | 2.86 | 1.44 | 1.44 | 1.42 | 50.3497 | 33 | 2014-05-31 | UC for Rs.144.24 lakh forwarded to MDoNEr on 18-03-2015.
55 | Dibrugarh | Improvement of Road from 1st Km of Demow Dehing Road to Dhaoma Phukhuri (length-10.125Km) with RCC Bridge(length-18.75m) in Demow Rural road Sub division. | 2012-13 | 7.6 | 2.71 | 0 | 0 | 2.71 | 0 | 0 | 2014-05-31 | A/A accorded by P & D Deptt on 27-06-2012. Work in progress. UC for Rs.270.77 lakh awaited from PWD. Rs.23.00 lakh(S/s) recommended by P&D.
56 | Jorhat | Construction of Slab Culvert by replacing old bridges and slab culvert on kamarbondha road upto 22nd km. | 2012-13 | 7.28 | 2.62 | 1.64 | 0 | 2.62 | 0 | 45 | 31-12-2013 | Work in progress. Rs. 164.11 laklh recommended by P&D on 31-10-2014. UC awaited from PWD.
57 | Dhubri | Construction of RCC Br. No.1/11 over Tanghat Channel on NH-31(tanghat to Asharkandi Ghegraralga Road) Dhubri District | 2012-13 | 3.25 | 2.34 | 2.34 | 2.34 | 0 | 100 | 90 | 2014-08-31 | Clarification submitted to MDoNER in March, 2015. Funds awaited from MDoNER.
58 | Nalbari | Construction of Rangia Dhamdhama Road including RCC Br. No. 18/1, 18/2, 19/2, 20/1 and 20/3. Nalbari Dist. | 2012-13 | 10.55 | 7.55 | 7.55 | 3.78 | 3.77 | 50.0662 | 66 | 2014-07-31 | Rs.86.11 lakh recommended by P&D on 24-06-2014. UC for balance amount awaited. Rs.42.19 lakh(S/s) recommended by P&D.
59 | Nalbari | Construction of Rcc Br. No.3/1 over river Pagladia on U.C. Baruah Road | 2012-13 | 7.3 | 2.63 | 1.27 | 1.27 | 1.36 | 48.289 | 40 | 2015-07-31 | UC for Rs.127.03 lakh forwarded to MDoNER on 6-12-2014. Rs.40.569 lakh(G/s) and Rs.29.20 lakh(S/s) recommended by P&D on 29-01-2015. UC awaited from deptt. Rs.51.54394 lakh (G/s) recommended by P&D on 20-03-2015.
60 | Sibsagar | Improvement of nagnimora Jajoli Road from ch.8.346 km to ch.13.650 km including conversion of SPT bridge no. 14/1 to RCC bridge. | 2012-13 | 4.85 | 1.75 | 1.75 | 1.75 | 0 | 100 | 90 | 2014-01-31 | UC for Rs.174.75 lakh forwarded to M/doNER on 7-05-2014. MDoNER sought clarification on UC on 7-07-2014 and deptt has been request on 15-07-2014 to submit the same.Rs.19.41 lakh(S/s) recommended by P&D . Funds awaited from M/doNER.
61 | Tinsukia | Construction of Kaliapani RCC Bridge No.21/1 over river Dibru on Doomdooma Dighaltarang Natun Gaon Road with approach road in Tinsukia. | 2012-13 | 13.23 | 4.76 | 2.58 | 2.58 | 2.18 | 54.2017 | 30 | 2015-07-31 | UC for Rs.86.11 lakh forwarded to MDoNER on 12-12-2014. Deptt, yet to move for balance amount. Rs.44.555 lakh(s/s) recommended by P&D.
62 | Nagaon | Construction of railway over Bridge at Dhing gate on Nagaon Bhuragaon Road via Dhing at Nagaon | 2012-13 | 21.05 | 14.61 | 14.61 | 14.61 | 0 | 100 | 84 | 2014-01-31 | UC forRs.703.04 lakh forwarded to MDoNER on 21-02-2015. Rs.184.22 lakh (s/s) recommended by P&D. Funds awaited from MDoNER.
63 | Tinsukia | Construction of RCC Bridge No.1/1 over River Doomdooma on A.T. Road. | 2012-13 | 4.22 | 1.52 | 0 | 0 | 1.52 | 0 | 0 | 2014-09-30 | AA accorded by P&D vide letterNo.PDP(PP)PWD(PP)71/08/49 dtd. 12-10-2012.Tender under process.
64 | Nalbari | Improvement of Kanimara Nannatary road in Nalbari District | 2012-13 | 4.35 | 3.12 | 3.12 | 1.56 | 1.56 | 50 | 40 | 2014-06-30 | . 2nd instalment of Rs.156.34L released by MDoNER in October, 2014. Rs. 114.35465 lakh and Rs.12.706 lakh recommended by P&D on 4-02-2015. Rs.41.98535 lakh(G/s) & Rs.4.664 lakh(S/s) recommended by P&D on 23-03-2015. UC for the amount awaited.
65 | Morigaon | Construction of RCC Bridge No.29/1 (at Br. Gap) at Kuhimari Bordowa road (SH-15) in Morigaon District. | 2012-13 | 5.01 | 1.8 | 0.27 | 0.27 | 1.53 | 15 | 0 | 2014-06-30 | UC for Rs.26.93 lakh forwarded to MDoNER on 28-07-2014.
66 | Cachar | Construction of Br.No.1/1 of 170.00 Km including approaches and protection work over Jatinga at Borkhola on Mahasadak to Borkhola road. | 2012-13 | 14.32 | 5.15 | 5.15 | 5.15 | 0 | 100 | 39.99 | 2015-08-30 | 2nd instalment awaited. Rs.61.266 lakh(s/s) recommended by P&D.
67 | Hailakandi | Construction of RCC Br. No.6/1 over river Kathalkhal at Ratanpur Ferryghat on Hailakandi, ratanpur road, Hailakandi | 2012-13 | 22.94 | 8.26 | 8.26 | 0 | 8.26 | 0 | 18 | 2015-09-30 | Total Rs.429.40 lakh recommended by P&D and UC awaited from department.
68 | Barpeta | Construction of RCC Bridge No.1/1 over River Kaldia on Sarumanikpur-Maharani Road | 2012-13 | 4.62 | 1.66 | 1.66 | 0 | 1.66 | 0 | 0 | 2015-02-28 | AA accorded by P& D Deptt. on 01-04 2013. Rs.166.05 lakh(G/s) and Rs.18.45 lakh(s/s) recommended by P&D on 20-12-2014 & 19-03-2015. UC for the amount awaited.
69 | Dhemaji | Construction of RCC Bridge No.7/1 on Sissobargaon Amguri Road over Singimari stream | 2012-13 | 4.29 | 1.54 | 0 | 0 | 1.54 | 0 | 0 | 2014-08-30 | AA accorded by P& D Deptt. on 01-04 2013. Deptt. yet to move for release of 1st instalment.
70 | Darrang | Construction of Guidebund near RCC Bridge No.8/2 over river Tonganee on the road form NH -52 to Kuwaripukhuri via Fakirapara | 2012-13 | 2.09 | 0.75 | 0 | 0 | 0.75 | 0 | 0 | 2013-10-31 | AA accorded by P& D Deptt. on 01-04 2013. Deptt. yet to move for release of 1st instalment.This scheme is to be dropped as there is similar work in Irrigation Deptt.
71 | Darrang | Construction of road from Ramhari to Bherbheri via Chamuakhat (ch.8.00km to 11.50km) including cross drainage works | 2012-13 | 3.46 | 0.79 | 0.79 | 0.79 | 0 | 100 | 40 | 2014-08-30 | UC for Rs.79.40 lakh(G/s) and Rs.8.822 (s/s) lakh forwarded to MDoNER Funds awaited from MDoNER.
72 | Sonitpur | Construction of RCC Bridge No.2/1 over river Belsiri on Dhekipelua to Belsiri T.E. connecting NH-52 | 2012-13 | 5.53 | 1.99 | 1.07 | 0 | 1.99 | 0 | 0 | 2015-02-28 | AA accorded by P& D Deptt. on 13-03- 2013. Rs.106.68471 lakh(G/s) recommended by P&D on 16-03-2015. UC awaited from dept. Work in progress.
73 | Sibsagar | Construction of Road from Banamali Tinali to Rongagorh Tinali with RCC bridge No.2/2 over river Desang and Br.No.8/2 on Mohmora Ali | 2012-13 | 14.22 | 5.12 | 0 | 0 | 5.12 | 0 | 0 | 2013-05-31 | AA accorded by P&D Deptt. on 12-04-2013. 1st instlmnt released by M/DoNER on 26-02-2013.Dept. yet to move.
74 | Kamrup(R) | Improvement of singimari Sualkuchi Road including cross Drainage Works and Road Side Drains in kamrup District. | 2012-13 | 18.28 | 6.58 | 6.58 | 0 | 6.58 | 0 | 35 | 2015-03-31 | AA accorded by P&D on 9-03-2013. Rs.402.05007 lakh & Rs. 256.00 lakh recommended by P&D on 13-08-2014 & 06-02-2015. UC awaited from Department.
75 | Sibsagar | Improvement of Mridongpara Road under NLCPR | 2013-14 | 6.72 | 2.41 | 0 | 0 | 2.41 | 0 | 0 | November,2014 | AA accorded by P&D on 25/07/2013. Rs.241.69 lakh released as 1st instalment. Dept yet to move for release
76 | Nagaon | Construction of RCC Br.No.1/1 on Mohmoria to Kuruabhi via Bebejia Road over river Kalang under Nagaon Rural Road Division (Nagaon District) | 2013-14 | 2.74 | 0.99 | 0.99 | 0.99 | 0 | 0 | 40 | 2014-11-30 | Uc for Rs.98.32Lakh forwarded to MDoNER on 07/07/2014. 2nd installment yet to be received. Rs. 10.94 alakh(S/s) recommended by P&D.
77 | Darrang | Improvement of Banglagarh Jaberikuchi Road(length-12.5 km) including cross drainage works | 2013-14 | 20.47 | 7.36 | 6.55 | 3.65 | 3.71 | 49.5924 | 35.57 | 2015-07-31 | UC for Rs. 144.41 lakh forwarded to MDoNER on 3-01-2014. Rs.290.149 lakh(G/s) & Rs.72.794 lakh(S/s) recommended by P&D on 30-12-2014. Another amount Rs.81.346 lakh(G/s) and Rs.9.036 lakh (S/s) recommended by P&D on 17-03-2015. UC awaited from dept.
78 | Cachar | Construction of RCC Bridge No.1/1 over River Barak at Sadarghat, Sichar on Silchar Kumbhigram Road | 2013-14 | 59.01 | 21.24 | 0 | 0 | 21.24 | 0 | 0 | 2016-04-30 | AA accorded by P&D Deptt. on 11-12-2013. Rs.2124.38 lakh(1st instlmnt) released by M/DoNER on 07-11-2013. Department yet to move for demand. EE,APDCL Silchar has been requested to furnish a formal letter confirming about feasibility alongwith time required for shifting of utility servicesincluding overhead electrical line both HT and LT falling under the alignment of project site to an alernate location for facilitating the construction of bridge over river Barak at Sadarghat, Silchar.
79 | Nalbari | Construction of Khetri Dharampur to Hajo Nalbari Road at Morowa via Piplibari, Kakaya, Jagara, Goalpara, Baguhati & kalkuchi | 2013-14 | 10.39 | 3.74 | 3.74 | 0 | 3.74 | 0 | 0 | 2015-11-30 | AA accorded by P&D Deptt. on 17-12-2013. Rs.256.049 lakh (G/s) & Rs.28.449 lakh(S/s) recommended by P&D on 2-03-2015.Meanwhile P&D recommended Rs.114.97587 lakh(G/s) & Rs.12.77510 lakh(s/s) 0n 21-03-2015. UC for the amount awaited.
80 | Nalbari | Construction of road with RCC Bridge (2nos.) from Pazipur Dhurkuchi to Borbari Narapara Road. | 2013-14 | 5.86 | 3.69 | 2.5 | 2.11 | 1.58 | 57.1816 | 40 | 2015-12-31 | Rs.157.75 lakh (2nd instlmnt) released by MDoNER. Rs. 38.95 lakh recommended by P&D on 16-02-2015.Rs. 23.45 lakh (S/s)& Rs.17.52777lakh recommended by P&D on 8-09-2014 & 16-02-2015. UC for the amount awaited. P&D agree to proposal of re-appropriation of Rs.118.80 lakh on 24-02-2015.
81 | Goalpara | Construction of Road from ranghuli IB to Kherkuta via Bechimari Road with RCC Bridge No. 1/1, 1/3 and 5/3. | 2013-14 | 7.34 | 2.64 | 2.64 | 0 | 2.64 | 0 | 0 | 2015-11-30 | AA accorded by P&D on 22-10-2013.Rs.263.60 lakh(G/s) recommended by P&D on 23-3-2015.
82 | Bongaigaon | Construction of RCC Bridge No. 5/1 over river Manas at connecting Goalpara and Numberpara village on the road Tulungia at NH-31(B) to Manikpaur at NH-31 Borghola Lirtanpara and Chakia. | 2013-14 | 17.94 | 6.46 | 0 | 0 | 6.46 | 0 |  | 2016-07-30 | AA accorded by P&D on 31-07-2013.
83 | Dhubri | Construction of road from Kanuri to Binachora(Satghaipara via Nalia including protection works and 4 RCC bridges | 2013-14 | 38.55 | 13.87 | 9.34 |  | 13.87 | 0 | 0 | 2015-11-30 | AA accorded by P&D Deptt. on 17-12-2013. Rs.933.75029 lakh(G/s) recommended by P&D Dept on 17-03-2015.
84 | Morigaon | Improvement of Morigaon Pachatia-Damal Dharamtul Road including construction of RCC brifge No. 5/1 over river Kollong under Morigaon District. | 2013-14 | 7.33 | 2.63 | 0 | 0 | 2.63 | 0 | 0 | 2016-02-28 | AA accorded by P&D Deptt. on 10-02-2014. Dept yet to move for release of fund.
85 | Tinsukia | Widening and Improvement of Barbora -Minirgon-Chapkhowa Road including conversion of SPT bridge No. 7/1 in Tinsukia District. | 2013-14 | 9.89 | 3.59 | 0 | 0 | 3.59 | 0 | 0 | 2016-02-20 | AA accorded by P&D on 26-05-2014.Dept. yet to move for release.
86 | Dibrugarh | Construction and Widening of Road from Khowang Chariali to Chenimari in Assam, dibrigarh | 2013-14 | 8.54 | 3.07 | 0 | 0 | 3.07 | 0 | 0 | 28-02-2016. | AA accorded by P&D on 19-05-2014..Dept. yet to move for release.
87 | Dibrugarh | Improvement of Namati to Sukhani Road under PWD Dibrugarh Rural Road Division | 2013-14 | 6.32 | 2.59 | 0 | 0 | 2.59 | 0 | 0 | 28-02-20-16 | AA accorded by P&D on 26-05-2014..Dept. yet to move for release.
88 | Cachar | Construction of road from Udharbond to Banaskandi under Silchar Rural Road Division | 2013-14 | 3.12 | 1.12 | 0 | 0 | 1.12 | 0 | 0 | 2015-11-30 | AA accorded by P&D Dept. Dept. yet to move for release.
89 | Tinsukia | Widening & strenghtening of Lahowal Bordubi Tinsukia Road in Tinsukia | 2013-14 | 9.98 | 3.59 | 0 | 0 | 3.59 | 0 | 0 | 2015-11-30 | AA accorded by P&D Deptt. on 20-12-2013. Dept. yet to move for release.
90 | Karimganj | Construction of Road from 52 km point of NH 154 -Katicherra Grant of District Hailakndi to Veterbond Dullavcherra Nec road of District Karimganj | 2014-15 | 16.17 | 5.82 | 5.82 | 0 | 5.82 | 0 | 0 | 2015-12-31 | AA accorded by P&D Dept.on 9-07-2014. P&D recommended the amount on on 7-03-2015.
| Darrang | Improvement of Kharupetia Udalguri Road from Ch.0.00 km to (EW, GSB, BM & SDBC, Pavemewnt length - 15.00 km, carraige way width =5.50m) including RCC drains in the Bazar Portion under Darrang District. | 2014-15 | 27.13 | 0 | 0 | 0 | 0 | 0 | 0 | 2017-02-20 | AA accorded by P&D on 8-04-2015.
|  | Total: |  | 783.07 | 400.05 | 307.95 | 230.81 | 169.24
PWD(Building)
91 | Jorhat | Mahapurush Shri Shri Madhav Dev Kalashetra at Dhekia Khowa | 2013-14 | 2.25 | 0.81 | 0 | 0 | 0.81 | 0 | 0 | 2015-07-31 | AA accorded by P&D Deptt. on 07-10-2013. Rs.80.95 lakh (1st instlmnt) released by M/DoNER on 05-07-2013. Deptt. yet to move proposal for release of fund.
92 | Kamrup(M) | Srimanta Sankardev Bhavan & Research Centre at Rupnagar, Guwahati | 2013-14 | 9.98 | 3.59 | 0 | 0 | 3.59 | 0 | 0 | 2016-02-28 | AA accorded by P&D Deptt. on 21-02-2014. Rs.358.95 lakh (1st instlmnt) released by M/DoNER on 21-02-2014. Deptt. yet to move proposal for release of fund.
93 | Nagaon | Construction of Hojai, Construction of swimming pool type-II with RCC Building, Indoor Hall type-II | 2013-14 | 5.71 | 2.05 | 0 | 0 | 2.05 | 0 | 0 | 2014-09-30 | AA accorded by P&D Dept. On 29/06/2013. Rs.205.30L released by M/DoNER on 8/10/2013 at 1st instalment.
94 | Dibrugarh | Construction of Moran Sports Complex | 2013-14 | 8.88 | 3.2 | 0 | 0 | 3.2 | 0 | 0 | 2016-02-29 | AA accorded by P&D Dept. On 19/05/2014. Rs.3.20 crore released by M/DoNER on 9/6/2014 at 1st instalment.
95 | Dibrugarh | Improvement of Road by lanes of Chabua Town | 2013-14 | 9.06 | 3.26 | 3.26 | 0 | 3.26 | 0 | 0 | 2015-07-31 | Rs.326.00lakh recommended on 27.11.14.UC awaited from dept..
|  | Total: |  | 35.88 | 12.91 | 3.26 | 0 | 12.91
Power
96 | Sonitpur | Construction of 38 km 33 KV line from Balipara to Bhalukpung.,Sonitpur | 2005-06 | 1.33 | 1.33 | 1.33 | 1.33 | 0 | 100 | 0 | 31/07/2007 | Concept Paper of alternative proposal in lieu of the present project forwarded to M/DONER in Jan., 2012. Audited statement of the expenditure incurred in the present project awaited from Power Dept.
97 | Kamrup(R) | Construction of 220/132 KV Azara (Kukurmara) S/S with 132/33 KV Azara S/S with LILO of 220 KV Agia- Sarusajai Line, 132KV S/C lines to 132/33 KV Boko and Azara S/S in Assam ,Kamrup® | 2007-08 | 36.22 | 26.08 | 26.08 | 26.08 | 0 | 100 | 72 | 30/09/2010 | Rs.289.76 lac (s/s) released. 3rd instalment awaited from MDoNER. Query raised by MDoNER on overall physical progress, release of state share. Dept. has been requested on 16-07-2014 to submit the same.Reminder issued imn March, 2015.
98 | Kokrajhar | Construction of 132 KV BTPS -Kokrajhar S/c line and 132 KV Kokrajhar S/C line 132 KV /33 KV sub Station at Kokrajhar. | 2010-11 | 43.58 | 25.58 | 25.58 | 15.38 | 10.2 | 60.1251 | 50 | 30-11-2013 | Rs.170.89 lakh (s/s) released. Rs.1020.13 lakh(2nd G/s) recommended in 27-10-2014. UC awaited from dept. Reminder issued imn March, 2015.
99 | Kokrajhar | Construction of new 33/11KV, 2x5MVA S/S at Thirubari with 45KM 11KV lines and 55Km 33 KV lines from Dhiligaon to Thirubari | 2012-13 | 8.9 | 3.21 | 0 | 0 | 3.21 | 0 | 3 | 2013-11-30 | Rs.320.65 lakh (G/s) and Rs. 44.55lakh (s/s) recommended by P&D Dept. on 17-7-2014 and 28-8-2014. UC awaited from deptt.Reminder issued imn March, 2015.
|  | Total: |  | 90.03 | 56.2 | 52.99 | 42.79 | 13.41
Water Resources
100 | Dhemaji | Raising & Strengthening of Brahmaputra Dyke from Dizmore to Sonarigaon from 14th to 23.15th km. including closing of Amguri & Arney Nalla. ,Dhemaji | 2003-04 | 11.51 | 9.83 | 9.83 | 9.83 | 0 | 100 | 99 | 31/12/2008 | Recommended for revalidation of A.A for Rs.11.51 crore on 15.02.2012. Detail report not yet received from WR Deptt.
101 | Dibrugarh | A/E measures to protect Dehingpuria village near Margherita town erosion of Buridehing river. | 2012-13 | 5.4 | 3.88 | 3.88 | 1.94 | 1.94 | 50 | 100 | 2013-08-30 | Rs.194.40 lakh recommended by P&D on 3-01-2015. UC awaited from deptt. Completion Certificate already submitted to MDoNER.
102 | Dibrugarh | A/E measures to protect Naharkotia town from the erosion of river Buridehing at Jagun Gaon area. | 2012-13 | 7.31 | 6.85 | 6.85 | 2.63 | 4.22 | 38.3942 | 100 | 2013-08-30 | Rs.394.99 lakh recommended by P&D on 3-01-2015. UC awaited from deptt.. Completion Certificate already submitted to MDoNER.
|  | Total: |  | 24.22 | 20.56 | 20.56 | 14.4 | 6.16
Irrigation
103 | entire state | 89 Minor Irrigation Schemes (entire state) | 1998-99 | 2.85 | 2.85 | 2.85 | 2.57 | 0.28 | 90.1754 | 100 |  | Work completed. 113 CCs already submitted to M/DoNER. Remaining 7 CC awaited .
104 | Sonitpur | Belsiri LIS (MP), Sonitpur | 2007-08 | 2.17 | 0.68 | 0.68 | 0.68 | 0 | 100 | 55 | 30/09/2008 | Rs 6.84 lac(s/s) released. Revised DPR for Rs 167.00 lac submitted to M/DoNER vide letter dated11/9/13, remaining fund yet to receive.
105 | Nalbari | Burinagar LIS, Nalbari District | 2011-12 | 2.16 | 0.74 | 0 | 0 | 0.74 | 0 | 0 | 2013-07-31 | Earlier work order has been cancelled & now work is in progress.
106 | Morigaon | Thengari Barhola Pathar Irrigation Scheme | 2014-15 | 4.1 | 1.48 |  |  | 1.48 | 0 | 0 | 2016-06-30 | AA accorded by P&D on 08-07-2014.
107 | Sonitpur | DTW Irrigation Scheme at 30 points under Borsola Development Block, Sonitpur Dist. | 2014-15 | 18.08 | 6.51 |  |  | 6.51 | 0 | 0 | 2017-01-31 | New project
|  | Total: |  | 29.36 | 12.26 | 3.53 | 3.25 | 9.01
Education
108 | Kamrup(M) | Modernisation and Augmentation of infrastructure development of Assam Textile Institue at Guwahati, Assam, Kamrup(M) | 2006-07 | 7.41 | 2.34 | 2 | 2 | 0.34 | 85.4701 | 51 | 30/09/2009 | Cm& Secy.,Education dept. Was requested to submit latest status report of the project on 11.8.2014 demand for S/s from dept. awaited
109 | Darrang | Infrastructural facilities at Kharupetia College - Construction of Building for Classrooms, Computer Laboratory with A.C, Hostels for trainees, electricity facilities, Water Supply & Sanitary facilities installation.(MP), Darrang | 2008-09 | 1.75 | 0.55 | 0.55 | 0.55 | 0 | 100 | 40 | 30/09/2008 | UC for Rs.55.00 lakh forwarded to MDoNER on 3-03-2015.
110 | Kamrup(M) | Construction of Academic cum Administrative Building of K.K. Handique Govt sanskrit College, Kamrup (M) | 2007-08 | 2.38 | 1.69 | 1.69 | 1.69 | 0 | 100 | 65 | 30/06/2009 | 2nd instalmnt awaited from DoNER. Query raised. Dept. Was requested to furnish reply on querry on 23.6.2014. demand for S/s from dept. awaited
111 | Kamrup(M) | Assam Institute of Management, Kamrup(M) | 2010-11 | 14.61 | 5.16 | 5 | 5 | 0.16 | 96.8992 | 44 | 2012-07-31 | UC for Rs.500.00Lakh sent to M/DONER on18.11.2014. Rs.73.00 lakh (S/s) recommended by P&D. fund awaited
112 | Kamrup(M) | State Level Eligibility Test Commission Assam (SLET), Kamrup(M) | 2010-11 | 3.35 | 1.18 | 1.18 | 0 | 1.18 | 0 | 0 | 2012-11-30 | P&D Dept recommended Rs. 1.18 crore on 01-03-2012. UC for the amount awaited from dept.
|  | Total: |  | 29.5 | 10.92 | 10.42 | 9.24 | 1.68
Cultural Affairs
113 | Kamrup(M) | Development & Upgradation of Jyoti Chitrobon Film & Television Institute, Kamrup(M) | 2007-08 | 13.47 | 6.93 | 6.93 | 5.77 | 1.16 | 83.2612 | 85 | 30/11/2008 | Funds (3rd) awaited from MDoNER.
114 | Kokrajhar | Construction of Cultural Centre Complex at Dotma (MP), | 2007-08 | 2.21 | 0.99 | 0.99 | 0.99 | 0 | 100 | 90 | 31/12/2009 | Funds(2nd ) awaited from MDoNER. Query on reply forwarded to M/DoNER on 15/07/2014.
115 | Kokrajhar | Bodoland India Indigeneous Tribal Art & Cultural Complex cum Film Studio at Kathalguri, Pt-II, Kokrajhar (MP) | 2007-08 | 4.95 | 1.61 | 1.61 | 1.61 | 0 | 100 | 78 | 31/12/2009 | Funds(2nd ) awaited from MDoNER. Quey raised. Department has been requested on 2-03-2015 to submit the latest QPR, photographs and status opf release of state share.
116 | lakhimpur | Construction of Sankar-Madhav Cultural Complex at letekupukhuri, Bhogpur Chariali, Lakhimpur : Assam(MP) | 2007-08 | 4.01 | 1.26 | 1.04 | 1.04 | 0.22 | 82.5397 | 43 | 31/10/2009 | Problem with building materials due to ban on Forest materials.Uc for Rs. 103.54 lakh forwarded to M/DoNER on 12-11-2013. P&D recoomened Rs/22.94 lakh on 2-01-2015. UC awaited.
117 | Jorhat | Presrvation of Cultural Hertitage of Majuli Natun Kamlabari Satra (Phase I), Jorhat | 2009-10 | 6.19 | 2.18 | 2.18 | 1.5 | 0.68 | 68.8073 | 30 | 31/04/2011 | Uc for Rs.150.00 lakh forwarded to M/DoNER on 06-06-2013. Uc for the balance amount awaited.MDONER received & dept requested on 6-11-2013 to submit the same.Reminder issued on 19-02-2015.
118 | Kamrup(M) | Socio Literary Cultural Complex of Bodo Sahitya Sabha at Bathooupuri, Gorchuk, Guwahati, Kamrup(M) | 2010-11 | 8.41 | 5.94 | 5.94 | 5.94 | 0 | 100 | 80 | 2014-03-31 | Rs.65.95 lakh (S/s) released on 1.11.14. Funds(3rd) awaited from MDoNER. Query raised by M/DONER. Dept. has been requested on 26-06-2014.
119 | Kamrup(M) | Government Art & Craft College, Kamrup(M) | 2011-12 | 5 | 1.79 | 0.26 | 0 | 1.79 | 0 | 10 | 2013-03-31 | P&D recommended Rs.26.05Lakh on 15.3.14. UC awaited.
|  | Total: |  | 44.24 | 20.7 | 18.95 | 16.85 | 3.85
Guwahati Development
120 | Kamrup(M) | Construction of Multi Level Parking at Ambari, Guwahati, Kamrup(M) | 2008-09 | 11 | 1.71 | 1.71 | 1.71 | 0 | 100 | 60 | 31/01/2010 | UC for Rs. 171.40 lakh forwarded to M/DoNER in March, Funds awaited from MDoNER.
Urban Development
121 | Dhubri | Dhubri Town Water Supply Scheme in Assam, Dhubri | 2006-07 | 10.27 | 8.78 | 8.77 | 7.06 | 1.72 | 80.41 | 82 | 30/09/2008 | UC for Rs. 34.54 lakh forwarded to MDoNER on 15-07-2014. Release of State share under process.The project will be completed by Dec, 2014.
122 | Golaghat | Golaghat Town Water Supply Scheme Phase-II (MP), Golaghat | 2007-08 | 5.05 | 4.41 | 4.41 | 4.41 | 0 | 100 | 90 | 30/05/2009 | P& D Dept. recommended Rs.50.46 lakh (s/s) on 8-12-2011. Uc awaited.
123 | Sibsagar | Sibsagar Town Water Supply Scheme, Sibsagar | 2007-08 | 16.39 | 11.8 | 8.86 | 8.86 | 2.94 | 75.0847 | 65 | 30/05/2007 | UC for Rs.116.53 lakh forwarded to MDoNER on 15-07-2014. Rs.131.00 lakh (S/s) recommended by P&D.. Approval for replacement of pumping berge awaited from MDoNER.
124 | Sonitpur | Improvement of Roads and Natural Drainage System within Greater Tezpur Town, Sonitpur | 2007-08 | 25.52 | 3.48 | 3.48 | 3.45 | 0.03 | 99.1379 | 74(drain) | 29/05/2009 | 74% drainage work completed. Revised working estimate as sought by DONER not yet received from Dept.S/s demand not received from deptt.
125 | Tinsukia | Margherita Piped water Supply scheme, Tinsukia | 2009-10 | 9.34 | 3.29 | 1.21 | 0 | 3.29 | 0 | 0 | 31/04/2012 | P&D Dept. recommended Rs.121.00 lakh in March, 2013. UC awaited. Rs. 47.00 lakh FOC released by Finance. UC under process Work order issued.
126 | Darrang | Mangaldoi Water Supply Scheme, Darrang | 2009-10 | 12.61 | 4.45 | 4.45 | 0 | 4.45 | 0 | 0 | 31/04/2013 | Department is requested to resubmit the UC for Rs.138.99 lakh.
127 | lakhimpur | Improvement of Municipal Road in Narayanpur, lakhimpur | 2009-10 | 4.4 | 2.82 | 2.82 | 2.82 | 0 | 100 | 84 | 31-01-2012 | UC for Rs.141.17 lakh forwarded to MDoNER on 17-07-2014. Rs.40.00Lakh (s/s) recommended by P&D. Funds awaited from DoNER.
128 | Barpeta | Barpeta Bus Terminus, Barpeta | 2010-11 | 1.86 | 0.66 | 0.66 | 0.66 | 0 | 100 | 40 | 31-03-2012 | UC for Rs.65.63 lakh forwarded to M/DoNER .Query on UC sought by MDoNER on 27-05-2014 and deptt has been requested on 16-07-2014 to submit the same. Funds awaited from MDoNER.
129 | Darrang | Kharupetia Water Supply Scheme, Darrang | 2010-11 | 19.81 | 6.99 | 6.99 | 0.51 | 6.48 | 7.2961 | 35 | 28-02-2014 | UC for RS.50.74 lakh forwarded to MDoNER on 15-07-2014.
130 | Bongaigaon | Bongaigaon Town Water Supply Scheme, Bongaigaon | 2010-11 | 32.02 | 11.3 |  | 0 | 11.3 | 0 | 0 | 28-02-2014 | AA accorded by P&D on 28-01-2011. Dept. yet to move for release.
131 | Golaghat | Sarupathar Piped Water Supply , Golaghat | 2010-11 | 10.29 | 3.63 | 3.63 | 0 | 3.63 | 0 | 0 | 28-02-2013 | P&D recommended the amount and UC awaited from UDD.
132 | Sonitpur | Improvement of Roads in Biswanath chariali Town, Sonitpur | 2010-11 | 11.74 | 8.13 | 4.14 | 4.14 | 3.99 | 50.9225 | 54 | 2013-03-30 | Rs.41.44Lakh (s/s) released. Rs.398.48 lakh (2nd instalment received) from MDoNER. Dept. yet to move for release..
133 | Jorhat | Construction of multistoried car parking cum city Hall, Jorhat | 2010-11 | 10.51 | 3.71 | 3.71 | 3.71 | 0 | 100 | 40 | 2014-02-28 | Uc for the recommended amount awaited from dept..
134 | Goalpara | Construction of 4 nos. of road including box culverts and pucca drainage in Lakhipur Town | 2011-12 | 14.25 | 5.1 | 0 | 0 | 5.1 | 0 | 0 | 2013-06-30 | AA accorded by P&D on 28-01-2012. Work not yet allotted due to court case.
135 | Nagaon | Construction of Roadside drainage System including of Town roads in Nagaon Urban Area | 2012-13 | 19.25 | 6.93 | 6.93 | 0 | 6.93 | 0 | 0 | 31-09-2014 | Dept. Is requested to implement the project as per schedule date.UC awaited from deptt.
136 | Goalpara | Improvement and Development of Goalpara Town Road Network in Goalpara District | 2013-14 | 17.24 | 6.2 | 4.5 | 0 | 6.2 | 0 | 12 | 2014-11-30 | P&D Dept. recommended Rs.4.50 lakh in October, 2013. UC under process.
137 | Dhemaji | Development of Roads for Dhemaji Town | 2013-14 | 11.98 | 4.31 | 4.31 |  | 4.31 | 0 | 0 | 2015-11-30 | AA accorded by P&D Deptt. on 11-12-2013. Rs.431.25lakh recommended on 26.11.14. UC awaited from dept.
138 | Dibrugarh | Proposed Town Hall at Dibrugarh | 2013-14 | 14.08 | 5.07 | 0 | 0 | 5.07 | 0 | 0 | 2015-11-30 | AA accorded by P&D Deptt. on 17-12-2013. A/A revalidated on 1.9.2014.
139 | Dibrugarh | Construction of Super Market Complex at Moran Revenue Town | 2013-14 | 6.84 | 2.46 |  |  | 2.46 | 0 | 0 | 2015-06-30 | A/A accorded by P&D on 19.5.2014.
140 | Tinsukia | Tinsukia Town Water Supply project (Phase-I) | 2013-14 | 35.83 | 12.9 |  |  | 12.9 | 0 | 0 | 2016-12-31 | AA accorded by P&D Deptt. on 02-01-2014. Pending due to code of conduct.
141 | Tinsukia | Tinsukia Town Water Supply project (Phase -II) | 2013-14 | 35.81 | 12.75 |  |  | 12.75 | 0 | 0 | 2016-12-31 | AA accorded by P&D Deptt. on 02-01-2014. Pending due to code of conduct.
142 | Tinsukia | Improvement of Roads in Tinsukia Master Plan Area., Tinsukia | 2013-14 | 15.46 | 5.56 |  |  | 5.56 | 0 | 0 | 2016-09-30 | AA accorded by P&D Deptt. on 20-05-2014. UDD issued A/A in oct.,2014. Fund not yet released from MDoNER.
143 | Tinsukia | Construction of Roads at Tinsukia Town. | 2013-14 | 14.61 | 5.25 |  |  | 5.25 | 0 | 0 | 2016-02-28 | AA accorded by P&D Deptt. on19-05-2014. UDD Issued A/A in oct.,2014. Fund not yet released from MDoNER.
144 | Dibrugarh | Improvement of Drainages system of Dibrugarh Town | 2013-14 | 23.81 | 8.57 |  |  | 8.57 | 0 | 0 | 2017-02-28 | AA accorded by P&D Deptt. on19-05-2014. UDD issued AA in Nov., 2014. Dept yet to move for release of fund.
| Tinsukia | Margherita | 2014-15 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | AA accorded by P&D on
|  | Total: |  | 378.97 | 148.55 | 68.87 | 35.62 | 112.93
|  | Public Health Engineering | [5 empty] | 0
145 | Kamrup(M) | Stabilisation of Dispur Water Supply Scheme., Kamrup(M) | 2008-09 | 7.3 | 5.15 | 5.15 | 5.15 | 0 | 100 | 90 | 31/01/2010 | UC alongwith fund demand forwarded to M/DoNER. Funds (3rd ) awaited from M/DoNER. Target date of completion by Mar., 2014. 3rd instalment awaited form M/DoNER. Main line Pump under installation, TP 88%, UGR, ESR-Dispur Tea auction Centre to Hanuman Mandir.
|  |  |  | 7.3 | 5.15 | 5.15 | 5.15 | 0 | 100
Sports
146 | Jorhat | Development of Jorhat Stadium at Jorhat | 2007-08 | 2.69 | 1.93 | 1.93 | 1.93 | 0 | 100 | 95 | 30/07/2009 | UC for Rs.108.40 lakh (2nd) forwarded to M/DoNER on 30-08-2013. P&D has revalidated the amount in April, 2014. Funds awaited from M/DoNER.
147 | Barpeta | Construction of Chandi Barua Stadium at Howly Town, Barpeta (MP), | 2008-09 | 2.9 | 0.9 | 0.9 | 0.9 | 0 | 100 | 53 | 31/07/2010 | Submission of UC is under process.
148 | Dhubri | Construction of District Sports Complex at Jhagrapara , Dhubri (MP) | 2008-09 | 3.78 | 1.17 | 1.17 | 0 | 1.17 | 0 | 0 | 30/04/2010 | UC pending for Rs.116.66 lakh since 10-12-08. UC under process.
149 | Hailakandi | Construction of RCC gallery of District Sports Association (Stadium Complex ,Hailakandi) | 2010-11 | 1.77 | 0.96 | 0.64 | 0.64 | 0.32 | 66.6667 | 45 | 31/05/2012 | Rs.6.37 Lakh(s/s) released. UC awaited. 2nd instalmnt received from MDoNER. Dept. yet to move for release.
|  | Total: |  | 11.14 | 4.96 | 4.64 | 3.47 | 1.49 | 69.9597
Industries & Commerce
150 | Sonitpur | Approach Road to Balipara Industrial Growth Centre, Sonitpur | 2005-06 | 2.69 | 2.42 | 2.42 | 2.42 | 0 | 100 | 95 | 31/12/2007 | Completion Certificate and UC for Rs.26.86Lakh the State Share awaited from Deptt. will be submitted soon.
|  | Total: |  | 2.69 | 2.42 | 2.42 | 2.42 | 0 | 100
NERMAC
151 | Dhubri | Cashew processing plant at Mancachar, Dhubri | 2007-08 | 2.48 | 2.07 | 2.07 | 1.69 | 0.38 | 81.6425 | 100 | 30/11/2008 | P&D recommended Rs. 38.39 lakh in July, 2012. CC & UC awaited from the dept..
Agriculture
152 | Nagaon | Comprehensive Development plan for college of Fisheries for augmentation Human Resources, Nagaon | 2010-11 | 8.75 | 3.09 |  | 0 | 3.09 | 0 | 0 | 31/06/2012 | Dept. yet to move proposal for release. AA revalidated. Dept. yet to move for fund.
Hill Areas
153 | Dima Hasao | Haflong Water Supply Scheme Raw Water Pumping Main from Robinalla in Assam., Dima Hasao | 2003-04 | 1.42 | 0.72 | 0.72 | 0.72 | 0 | 100 | 34 | 31/07/2005 | DoNER sought clarification on the UC on 09-08-2007. Clarification awaited from dept.Reminder issued on 1-06-2012 & 21-03-2013.
154 | Dima Hasao | Conversion of 100 bedded Civil Hospital to 200 Bedded Hospital with construction of Staff Quarters buildings at Haflong in North Cachar Hills in Assam. | 2004-05 | 11.2 | 10.13 | 8.4 | 4.2 | 5.93 | 41.461 | 88 | 31/12/2006 | P&D recommended Rs.420.00 lakh (out of Rs.592.64 lakh 2nd instlmnt. ) in Jan/09. UC for the amount awaited from dept.Reminder issued on 30-09-2013.
155 | Karbi Anglong | Diphu Sports Complex at Diphu, Karbi Anglong | 2004-05 | 5.01 | 4.69 | 3.22 | 1.75 | 2.94 | 37.3134 | 70 | 2005-03-31 | Rs.146.80 lakh recommended out of Rs.294.00 lakh (2nd instlmnt) on 20-09-2008. UC awaited from Dept. (PROJECT HAS BEEN DROPPED BY MDONER)
156 | Dima Hasao | Greater Mahur Town Water Supply Scheme., Dima Hasao | 2006-07 | 5.12 | 1.61 | 1 | 0 | 1.61 | 0 | 30 | 31/12/2007 | P&D Dept. recommended Rs.100.00 lakh on 22-07-2011. UC awaited for the amount.
157 | Karbi Anglong | Construction of RCC Bridge No. 22/1 over River Diffolloo on Chowkihola – Panjan – Deithor – Malasi – Dirring – Kohora Road (CPDMDK Road) renamed Solonijan Chowkihola Kohora Road (Kohora PWD Division), Karbi Anglong | 2008-09 | 3.04 | 0.95 | 0.29 | 0 | 0.95 | 0 | 25 | 2011-03-04 | P&D Dept. recommended Rs. 28.61 lakh on 28-03-2012. UC for the amount awaited from Dept. Reminder issued on 27-09-2013. Retendering of work.
158 | Karbi Anglong | Augmentation of Greater Diphu Water Supply Scheme, Karbi Anglong | 2008-09 | 27.67 | 8.55 |  | 0 | 8.55 | 0 | 50 | 31/072010 | HAD will submit UC and take action against the officers that are involved in this irregularities.
159 | Karbi Anglong | Greater Bokajan water supply Scheme, Karbi Anglong | 2008-09 | 10.04 | 3.1 | 3.1 | 0 | 3.1 | 0 | 81 | 17/12/2010 | Rs.3.10 crore directly released by Finance Dept. and UC awaited from deptt.
160 | Dima Hasao | Construction of RCC Bridge No. 28/1 on Dehangi Dayangmukh Road over Thaijuwari Nala & Langlodisa Nala (PWD Roads Haflong Division), Dima Hasao | 2008-09 | 3.55 | 1.12 | 1.12 | 0 | 1.12 | 0 | 35 | 30/09/2010 | P&D Dept. recommended Rs.111.76 lakh on 4-09-2013. UC awaited from dept. Reminder issued on UC on 26-09-2013.
161 | Karbi Anglong | Improvement of BBDC road at 31st km. | 2009-10 | 40.17 | 12.17 | 12.17 | 3.5 | 8.67 | 28.7592 | 42 | 16/06/2011 | P& D Dept. recommended Rs.866.93 lakh on 29-06-2013. UC for the amount awaited from dept.
162 | Karbi Anglong | Construction of RCC (a)bridge No.8/6 over River Dirring,(b)bridge No.18/1 over River Borjan, ©bridge No.19/1 over river Borjan, (d)bridge No.23/3 over river Donjan,(e)bridge No.27/3 over river Kakosang, (f)Bridge No.48/1 over River Deihori of Chowkihola-Panjan-Deithor-Malasi-Dirring-Kohora road(CPDMDK road),(2)Construction of RCC bridge No.2/1 over River Kohora on Kohora Bagori road, in Assam. | 2009-10 | 11.38 | 3.51 | 2.01 | 0 | 3.51 | 0 | 42 | 14/07/2011 | P&D Dept. recommended Rs. 200.70 lakh on 29-03-2012.HAD has been requested to submit the clarification about drawal & release of Rs.200.70 lakh on 27-02-2014. UC for the amount awaited from Dept.
163 | Karbi Anglong | Langklangvong Water Supply Scheme | 2009-10 | 5.96 | 2.1 | 0 | 0 | 2.1 | 0 | 0 | 2010-02-12 | AA accorded by P&D deptt. on 11-12-2009. Department yet to move for release of fund.
164 | Karbi Anglong | Development of Tourism Infrastructure at Bagori Entry Point of Kaziranga National park | 2009-10 | 3.3 | 2.32 | 2.32 | 2.32 | 0 | 100 | 80 | 2012-08-07 | 3rd instalmnt awaited from MDoNER. P&D recommended Rs.32.96 lakh(S/s) on 25-03-2014. UC awaited from dept.
165 | Karbi Anglong | Deithor Minor Irrigation Project | 2009-10 | 2.22 | 0.78 | 0.78 | 0 | 0.78 | 0 | 68 | 31/12/2012 | P&D Deptt. recommended Rs.78.40 lakh on 15-12-2012.UC awaited from Dept. HAD has been requested to submit the same on 14-08-2012. Reminder issued for UC on 26-09-2013.
166 | Dima Hasao | Metalling & Black Topping of Gunjung- Maibong Road. | 2009-10 | 6.41 | 1.99 | 0.74 | 0 | 1.99 | 0 | 47 | 2012-10-04 | HAD has been requested on 26-07-2013 to correct the UC (Rs.125.00 lakh) as sought by M/Doner. Meanwhile , P&D Dept recommended Rs. 73.71 lakh on 5-07-2013 and UC awaited from deptt. Reminder issued for subvmission of clarification/UC/move proposal for S/s
167 | Karbi Anglong | Construction of road from Hidpi to Lahorijan Goutom Bast Road | 2010-11 | 4.85 | 3.42 | 3.42 | 1.71 | 1.71 | 50 | 70 | 2012-10-04 | P&D Dept. recommended Rs.171.86 lakh (2nd instalmnt) in March, 2014. UC awaited from dept.
168 | Karbi Anglong | Infrastructure Development of Road Transport system under Karbi Anglong Autonomous Council (KAAC) Part-I | 2010-11 | 1.83 | 0.65 | 0.65 | 0.65 | 0 | 100 | 50 | 2012-10-04 | UC for Rs.64.85 lakh forwarded to M/DoNER on 2-06-2014. Clarification on UC also forwarded to MDoNER.Funds awaited from M/doNER.
169 | Karbi Anglong | Greater Dokmoka Tekelangjan water supply scheme for fluoride, Arsenic/ iron affected areas from Dikrut, | 2011-12 | 18.66 | 6.71 | 6.71 | 0 | 6.71 | 0 | 25 | 2014-10-31 | P&D Dept. recommended Rs.670.74 lakh on 7-3-2014. UC awaited from dept.
170 | Karbi Anglong | Improvement of Ronghang Basti to Thekrajan Road | 2011-12 | 12.76 | 5.05 | 5.05 | 0 | 5.05 | 0 | 37 | 2013-06-30 | P&D Dept. recommended Rs. 504.90 lakh on 30-07-2013. UC awaited from HAD.
171 | Karbi Anglong | Kaku basti Irrigation Scheme | 2012-13 | 8.72 | 6.28 | 6.28 | 6.28 | 0 | 100 | 100 | 2013-10-30 | UC for Rs.313.75 lakh (2nd instlmnt)forwarded to MDONER on 7-03-2014. Meanwhile UC for Rs.87.17 lakh (s/s) recommended by P&D dept. on 2014 awaited. Funds awaited from MDoNER.
172 | Dima Hasao | Metalling and Blacktopping of Ashalu Diduki Road including WBM(length=18km) under Mahur Road Division | 2012-13 | 6.4 | 2.3 |  | 0 | 2.3 | 0 | 0 | 2014-06-30 | AA accorded by P&D on 07-07-2012 .Dept. yet to move for release of fund.
173 | Karbi Anglong | Augmentation of donka mokam Piped Water Supply Scheme(PWSS) | 2012-13 | 7.07 | 2.54 | 0 | 0 | 2.54 | 0 | 0 | 2014-10-31 | AA accorded by P&D Deptt. on 7.11.2012. Dept. yet to move for release of Rs. 254.30 lakh(1st instlmnt).
174 | Karbi Anglong | Phangcho Basti Irrigation Scheme | 2012-13 | 9.53 | 3.43 | 3.43 | 3.43 | 0 | 100 | 40 | 2014-04-30 | UC for Rs.342.85 lakh forwarded to MDoNER on 6-03-2014. Clarification on UC sought by MDONER and HAD has requested to submit the same on 23-05-2014. Rs. 47.83lakh recommended by P&D.
175 | Dima Hasao | Improvement &Strenghtening of Hard Crust Road from Liasong to latko Border Road (Length 30Km) under Mahur Road Division | 2012-13 | 8.35 | 3 | 3 | 3 | 0 | 100 | 5 | 2014-06-30 | UC forwarded to MDoNER on 20-12-2014.
176 | Dima Hasao | Construction of RCC Multistoried Auditorium Building attached to Halflong Government College at Halflong in Dima Hasao District. | 2012-13 | 2.3 | 0.83 | 0.83 | 0.83 | 0 | 100 | 40 | 2015-01-31 | UC forwarded to MDoNER on 11-12-2014. Rs.11.51 lakh(s/s) recommended by P&D.
177 | Dima Hasao | Construction of Home for Orphans and Destitute children at Haflong alongwith staff quarters including one Vocational Training Centre for children | 2013-14 | 2.98 | 1.07 | 0 | 0 | 1.07 | 0 | 5 | 3-0-11-2014 | AA accorded by P&D Deptt. on 29-06-2013.Dept. yet to move for release of fund.
178 | Karbi Anglong | Construction of RCC Bridge No. 4/3 on NH -36 '0' Point to Howragaht Karok Road at Kanki Engti Gaon via Monsing Rongchehon Gaon | 2013-14 | 2.21 | 0.79 | 0 | 0 | 0.79 | 0 | 0 | 2015-01-31 | AA accorded by P&D Dept. on 02-07-2013. Dept. yet to move for release of Rs.79.20 lakh(1st instlmnt)
179 | Karbi Anglong | Improvement of Lahorijan Gautom Basti Road (Ph-II, L-5.50km from Ch.9000.0m to Ch.14500.0m) | 2013-14 | 5.17 | 1.86 | 1.8 | 0 | 1.86 | 0 | 36 | 2015-03-31 | P&D Dept. recommended Rs 180.00 lakh on 14-03-2014.UC awaited from dept.
180 | Karbi Anglong | Langkhailu Irrigation Scheme | 2013-14 | 10.39 | 3.73 | 3.73 | 0 | 3.73 | 0 | 40 | 2015-09-30 | AA accorded by P&D Dept. on 05-10-2013.P&D Dept.recommended Rs.37.00 lakh on 17-02-2015.
181 | Karbi Anglong | Farkongcho Irrigation Scheme | 2013-14 | 10.22 | 7.34 | 7.34 | 3.4 | 3.94 | 0 | 70 | 2015-09-30 | Rs.394.05 lakh (2nd) released by MDoNER on 4-12-2014. . Rs. 51.10 lakh (S/S) recommended by P&D.Rs.394.05 lakh recommended by P&D on2-3-2015.
182 | Karbi Anglong | Dikanshi Irrigation project | 2013-14 | 10.25 | 3.69 | 0 | 0 | 3.69 | 0 | 0 | 2016-02-28 | AA accorded by P&D Dept. on 24-02-2014. Rs. 389.05 lakh released as 1st instlmnt by M/DoNER on 20-02-2014. Dept. yet to move for release of fund.
183 | Dima Hasao | Infrastructure Development of Haflong Government College, Haflong | 2014-15 | 10.05 | 3.62 | 0 | 0 | 3.62 | 0 | 0 | 2017-01-31 | New project
|  | Total: |  | 268.23 | 110.05 | 78.11 | 31.79 | 78.26 | 28.8869
|  | WPT &BC | [5 empty] | 0
184 | Udalguri | Improvement of Tangla Kachubill Road . | 2010-11 | 10.8 | 9.62 | 9.62 | 7.7 | 1.92 | 80.0416 | 98 | 30.11.2012 | Rs. 192.32 lakh(final instlmnt) recommended by P&D Dept. in Aug., 2013. UC awaited from dept. UC for Rs.37.94 lakh(G/s) received and returned
185 | Udalguri | Improvement of Moholiapara Dongapara Borongajuli PWD Road. | 2010-11 | 8.35 | 7.45 | 7.45 | 5.96 | 1.49 | 80 | 100 | 2012-12-31 | Rs.148.85 lakh released as 3rd &final instlmnt recommended by P&D on 26-02-2014. UC &CC received,but returned back for necessary correction.
186 | Kokrajhar | Upgradation of NT Road through Ramphalbil Bazar to all weather roads of SPT bridge into RCC Bridge (International Border Area) | 2011-12 | 7.64 | 2.7 | 2.7 | 0 | 2.7 | 0 | 40 | 2012-10-31 | AA accorded by P&d dept. on 20-07-2011. 1st instalment (Rs. 269.71 lakh recommended by P&D on 11-02-2014. UC awaited from Dept.WPT&BC dept. is requested to re-submit proposal for SS with UC vide endorsement dtd.28-01-15.
187 | Udalguri | Improvement of Chintagaon Botiamari Road in Udalguri District | 2011-12 | 8.98 | 6.44 | 6.44 | 3.22 | 3.22 | 50 | 58 | 2013-07-31 | P&D recommended Rs.321.72 lakh on UC for Rs. 321.72 lakh forwarded to M/DoNER on 26-07-2013. Funds awaited from M/DoNER. P&D Dept. recommended Rs. 35.75 lakh(s/s) on 26-08-2013, Rs. 35.75 lakh(s/s) on 19-03-2014 and Rs.17.88 lakh 20-10-2014.
188 | Udalguri | Construction of Road with MTBT from UT road at Dimakucji Don- Bosco School to Badlapara via Kalikhola Road, Udalguri | 2011-12 | 6.21 | 4.46 | 2.23 | 2.23 | 2.23 | 50 | 45 | 2014-06-30 | Rs. 223.17 lakh (2nd) instalment recived from MDoNER 24-02-2015. Meanwhile, P&D Dept. also recommended Rs. 24.80 lakh(s/s) on5-02-2014. UC for the amount awaited.
189 | Kokrajhar | Upgradation of Road from NH-31( C) via Serfenanguri, Nepalpara, Athiabari, Ebargaon, Thaigiriguri and No.2 Hazarkiapara to Kapuragaon | 2011-12 | 7.6 | 2.7 | 2.7 | 2.02 | 0.68 | 74.8148 | 60 | 2013-12-31 | A/A accorded by P & D Deptt on 27-12-2011. Rs.269.79lakh( 1st installment) released on 15-12-2011 by M/DONER. Fund of Rs.250.00lakh released directly from Finance dept. E&M div.submited report. P&D recommended Rs.19.79 lakh of remaining G/S on 17-11-2014. UC for Rs.202.19 lakh forwarded to MDoNER on 19-11-2014.
190 | Kokrajhar | Construction of RCC Br.No. 8/1 over Saral Bhanga on Dotmo Balajan Road. | 2011-12 | 12.02 | 4.29 | 4.29 | 4.29 | 0 | 100 | 60 | 2013-08-31 | UC for Rs.428.55 lakh forwarded to MDoNER on 20-01-2015. Funds awaited from DoNER. P&D recommended Rs.60.12 lakh as state share on 19-09-2014.
191 | Chirang | Construction of Fly over at the intersection of Pramathesh Barua Road and N.F. railway Track at Bijni Town | 2011-12 | 19.63 | 13.49 | 13.49 | 7.06 | 6.43 | 52.3351 | 77 | 2013-06-30 | AA accorded by P&D on 17-01-2010.Clarification on the U/C is forwarded to M/DoNER on 11-07-2014.State share of Rs.140.00lakh recommended by P&D on 24-01-2014.Rs.641.90 lakh recommended by P&D on 15-09-2014. P&D recommended Rs.17.00 lakh as S/S on 17-11-2014.
192 | Udalguri | Flow Irrigation Scheme from River Kulsik at Palashgarh under tangla irrigation Division, Udalguri District | 2011-12 | 19.28 | 17.34 | 17.34 | 13.4 | 3.94 | 77.278 | 90 | 2013-06-30 | P&D recommended Rs.394.12 lakh(2nd ) on10-11-2014 and Rs.186.00lakh (S/s) recommended by P&D in July & Dec, 2013. UC awaited.
193 | Kokrajhar | Tamulpur Piped Water Supply Scheme | 2011-12 | 2.94 | 1.04 | 1.04 | 1.04 | 0 | 100 | 85 | 2013-12-31 | Latest inspection report is forwarded to M/DoNER on 28-07-2014. S/S of Rs.14.68 lakh recommended on 30-10-2014.WPT&BC dept. is requested to submit the proposal for recommendation of Rs.105.96lakh on 8-1-2015.
194 | Baksa | Construction of proposed Stadium at Musalpur in Baska Distict. | 2010-11 | 9 | 6.36 | 5.38 | 3.18 | 3.18 | 50 | 44 | 2013-11-30 | Rs. 317.65 lakh(2nd instlmnt) received from MDoNER. Rs.220.00 recommended by P&D on 21-10-2014. P&D Dept. recommended Rs. 90.00 lakh(s/s) on 20-02-2014. UC for the amount awaited.
195 | Kokrajhar | Khowra Flow Irrigation Scheme | 2012-13 | 3.55 | 2.56 | 2.56 | 1.28 | 1.28 | 50 | 80 | 2013-10-31 | AA accorded by P&D dept. on 5th July, 2012.S/Sof Rs.35.42 lakh recommended on 22-07-2014 by P&D.C.UC of Rs.163.32 forwarded to M/DoNER on 6/1/15WPT&BC dept. is requested to submit UC for 2nd installment.
196 | Kokrajhar | Conversion of washed out SPT Bridge No.2/1 over river Hell into RCC Bridge on Shialmari Moinaguri Road in Kokrajhar District. | 2012-13 | 19.68 | 7.08 | 0 | 0 | 7.08 | 0 | 39 | 2014-12-31 | AA ccorded by P&D Deptt. on 25-01-2013. Rs. 708.15 lakh has been released as 1st installment on 21-05-2014.uc awaited.S/S Rs.98.38 lakh recommended on 27-10-2014. | New Project. AA being accorded by P&D Deptt.
197 | Baksa | Construction of Road from Rongaichera Bazar to Bhola Bazar | 2012-13 | 3.66 | 1.32 | 1.32 | 0 | 1.32 |  | 0 | 2014-06-30 | AA accorded by P&D Deptt. on 18-02-2013. P&D Dept. recommended the amount in March, 2014. UC awaited from Dept. | New Project. AA being accorded by P&D Deptt.
198 | Baksa | Construction of Road from Gopalpur(Kekerikuchi) to Niz-Kaurbaha(13.5Km length) including construction of RCC Bridge No. 5/1(15.00m length) under PWD, Musalpur(R&B) Division) | 2012-13 | 11.71 | 4.21 | 4.21 | 4.21 | 0 | 100 | 65 | 2015-02-28 | UC for Rs.421.40 lakh(G/s) & Rs.45.00 Lakh(S/s) forwarded to MDoNER on 24-02-2015. Funds awaited from MDoNER.
199 | Kokrajhar | Rajendrapur flow Irrigation Scheme | 2012-13 | 21.47 | 15.46 | 15.46 | 7.73 | 7.73 | 50 | 50 | 2016-02-28 | Rs.772.60 lakh(2nd) recommended by P&D Dept. UC awaited from dept.
200 | Udalguri | Construction of Road from paoriputa to Natun Panbari with black topping and construction of RCC Bridge over River Pasnai in Udalguri District. | 2013-14 | 7.68 | 2.76 | 2.76 | 0 | 2.76 | 0 | 0 | 2014-11-30 | AA accorded by P&D Dept. on 29-05-2013. P&D Dept. recommended Rs.2.76crore in October, 2013. UC for the awaited.
201 | Kokrajhar | College of Nursing at Kokrajhar | 2013-14 | 14.27 | 5.18 | 5.18 | 0 | 5.18 | 0 | 0 | 2014-05-30 | AA accorded by P&D Dept. on 03-06-2013. Rs.517.79 alkh recommended by P&D on 21-10-2014.
202 | udalguri | Improvement/upgradation of Mangaldoi Bhutiachang Samrang Road fromCH-47722M to CH-48292 and from 50000 to CH-62500M including cross -drainage works | 2013-14 | 29.92 | 10.77 | 10.77 | 0 | 10.77 | 0 | 0 | June,2014 | AA accorded by P&D Dept. on 29-05-2013.P&D Dept. recommended Rs. 10.77 crore(G/s) on 06-09-2013. UC for Rs.7.08 crore received and returned back for correction. File sent to judicial dept. for advice regarding countersignature on UC by P&D Dept. on 13-01-2014.
203 | Udalguri | Improvement of raod from Budura to Parbahuchuba Dimakuchi PWD road at batabari via Khasiachuba, Barangababari | 2013-14 | 11.09 | 3.99 | 0.55 | 0 | 3.99 | 0 | 0 | 2015-01-31 | AA accorded by P&D Dept. on 20-07-2013. Dept yet to move for release of fund. Rs.398.00 lakh directly drawn from Finance Dept. UC for the said amount received but returned back on 25-09-2014 for necessary correction. Rs.55.45 lakh(S/s) recommended by P&D on 8-09-2014.
204 | Udalguri | Construction of RCC Br. No.9/8 over laska on Dauluguri Dotma Road | 2013-14 | 1.75 | 0.63 | 0.63 | 0 | 0.63 | 0 | 0 | 2015-07-31 | AA accorded by P&D Dept. on 18-07-2013.Rs.62.90 lakh recommended by P&D on 11-09-2014. UC for the amount awaited.
205 | Kokrajhar | Conversion of SPT Br.No.10/1, 12/3, 14/2 and 16/1 into RCC bridge on metd. Kokrajhar, Bahalpur Road. | 2013-14 | 6.99 | 2.51 | 2.51 | 0 | 2.51 | 0 | 30 | 2015-09-30 | New project . AA accorded by P&D Dept. on 21-10-2013.P&D recommended Rs.125.00lakh & Rs.126.35 lakh recommended Rs.126.35 lakh on 21-07-2014 & 4-11-2014.UC awaited for the amount.
206 | Udalguri | Improvement of Road from Kharibari to Jamuguri in Udalguri | 2013-14 | 13.29 | 4.78 | 4.78 | 0 | 4.78 | 0 | 0 | 2016-10-31 | AA accorded by P&D Dept. on 28-10-2013. Rs.478.30 lakh (1st instlmnt) released by M/DoNER. P&D recommended Rs.478.30 lakh on 6-02-2015.
207 | Baksa | Improvement of Kamdaltal Nikashi Road from Kuchi to Bhaldonga | 2013-14 | 4.16 | 1.5 | 1.5 | 0 | 1.5 | 0 | 0 | 2015-07-31 | AA accorded by P&D Dept. on 5-11-2013. P&D Dept. recommended Rs. 149.67 lakh (1st instlmnt) on 14-03-2014 and Rs.20.80 lakh recommended by on 08-09-2014. Uc for the amount awaited.
208 | chirang | Construction of RCC bridge No. 15/2 over river Burisuti on Patadaha Panbari Road. | 2013-14 | 7.19 | 2.59 | 2.59 | 0 | 2.59 | 0 | 0 | 2015-07-31 | AA accorded by P&D Dept. on 28-02-2014. Rs.258.90 lakh (1st instlmnt) released by M/DoNER. P&D recommended Rs.258.90 lakh on 19-09-2014.UC awaited.
209 | Baksa | Improvement of Road from Barama Dhamdhama Tamulpur | 2013-14 | 8.47 | 3.05 | 3.05 | 0 | 3.05 | 0 | 0 | 2016-02-28 | AA accorded by P&D Dept. on 19-05-2014. Rs.304.76 lakh recommended by P&D on 11-06-2014. UC awaited.
210 | Kokrajhar | Mt. & Bt. Of Road from Jaipur NH-31 C to Amguri JD Road Dumbruguri to Amguri) including construction of RCC Bridges & Culverts, Kokrajhar | 2014-15 | 14.71 | 5.3 | 0 | 0 | 5.3 | 0 | 0 | 2017-01-31 | New project
211 | chirang | Construction of Road from Borobazar to Gumergaon via Chawdhuripar in Chirang District | 2014-15 | 16.68 | 6 | 0 | 0 | 6 | 0 | 0 | 2017-01-31 | New project
212 | Baksa | Sujit Narzary road from Tihu Chowk to Barimakha via Belguri Pathar. | 2014-15 | 31.36 | 11.29 | 0 | 0 | 11.29 | 0 | 0 | 2017-01-31 | AA accorded by P&D Dept. on 17-03-2015.. Rs.1128.89 lakh released as 1st instalment . Dept. yet to move for release.
|  | BAC Areas Projects implemented by BTC | [5 empty] | 0
213 | Kokrajhar | Drinking water supply scheme at Gossaigaon, kokrajhar | 2000-01 | 3.63 | 2.57 | 2.57 | 2.57 | 0 | 100 | 80 | 31-07-2005 | M/DoNER directed the state govt. to complete the project from state's own resources . Accordingly, WPT &BC Dept. has been intimated .
214 | Kokrajhar | Special Area Game Centre at Kathalguri, Kokrajhar | 2000-01 | 9.29 | 8.91 | 8.91 | 8.91 | 0 | 100 | 100 | 31-03-2006 | Proposal for S/S not received from WPT&BC Deptt.
215 | Kokrajhar | Gauhati University Campus at Kokrajhar. | 2002-03 | 5 | 4.62 | 4.62 | 4.62 | 0 | 100 | 95 | 31-03-2004 | P&D Dept. recommended Rs.38.50 lakh(S/S). UC & CC awaited from WPT &BC Dept.
|  | Total |  | 358 | 182.97 | 146.65 | 79.42 | 103.55 | 43.406

## deptt.wise summary
Ongoing Projects under Non Lapsable Central Pool of Resources (excluding dropped projects & BTC Package) (as on 31st March, 2015)
(Rs. in crore)
Sl. No. | Department | No. of projects sanctioned by M/DoNER | Approved cost | Fund released by GOI (90% grant) | Amount recommended by P&D | UC submitted to DONER | UC pending | % tage of utilisation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
1 | PWD (Roads) | 91 | 783.07 | 400.05 | 307.95 | 230.81 | 169.24 | 57.6953
2 | PWD(Building) | 5 | 35.88 | 12.91 | 3.26 | 0 | 12.91 | 0
2 | POWER | 4 | 90.03 | 56.2 | 52.99 | 42.79 | 13.41 | 76.1388
3 | WATER RESOURCES | 3 | 24.22 | 20.56 | 20.56 | 14.4 | 6.16 | 70.0389
4 | IRGN. MINOR | 11 | 29.36 | 12.26 | 3.53 | 3.25 | 9.01 | 26.509
5 | AGRICULTURE | 1 | 8.75 | 3.09 | 0 | 0 | 3.09 | 0
6 | EDUCATION | 5 | 29.5 | 10.92 | 10.42 | 9.24 | 1.68 | 84.6154
7 | CULTURAL AFFAIRS | 7 | 44.24 | 20.7 | 18.95 | 16.85 | 3.85 | 81.401
8 | GDD | 1 | 11 | 1.71 | 1.71 | 1.71 | 0 | 100
9 | URBAN DEVELOPMENT | 24 | 378.97 | 148.55 | 68.87 | 35.62 | 112.93 | 23.9785
10 | PHE | 1 | 7.3 | 5.15 | 5.15 | 5.15 | 0 | 100
11 | SPORT & YOUTH WELFARE | 4 | 11.14 | 4.96 | 4.64 | 3.47 | 1.49 | 69.9597
12 | INDUSTRIES | 1 | 2.69 | 2.42 | 2.42 | 2.42 | 0 | 100
13 | NERAMAC | 1 | 2.48 | 2.07 | 2.07 | 1.69 | 0.38 | 81.6425
14 | Hill Areas | 31 | 268.23 | 110.05 | 78.11 | 31.79 | 78.26 | 28.8869
15 | WPT & BC | 32 | 358 | 182.97 | 146.65 | 79.42 | 103.55 | 43.406
| TOTAL: | 222 | 2084.86 | 994.57 | 727.28 | 478.61 | 515.96 | 48.1223